An Evaluation of the Derbyshire and Nottinghamshire Collaborative Outreach Programme

Final Report May 2019

Dr Jill Hanson, Lewis Clark

Contents

List of Figures	6

List of Tables	6

Executive Summary	9

The Context	9

Aim/Methods	9

Key Findings	9

Recommendations	10

Introduction	11

Evaluation aims and objectives	15

Literature Review	17

Introduction to outreach and widening access	17

The History of Widening Access and Collaborative Networks	17

Who is the focus of widening access?	19

What underpins decision making regarding attending HE?	20

What works in outreach?	22

Design matrices	26

Networks	31

Effective Collaboration	33

Methodology	37

Evaluation Framework	37

Design	47

Timeline	47

Participants	47

Methods	52

Findings and Analysis	53

1. The structure of the network and the collaborative partnerships	53

Who is involved?	53

How is DANCOP structured and what are the roles?	54

Features and Outcomes of DANCOP	60

Structure	60

Central v decentralised employment	61

Collaboration	62

2. DANCOP’s progress against Targets	63

The engagement of schools into the network/collaborative partnerships	65

How many have engaged?	65

Activities delivered	71

3. Impact of DANCOP on learners	77

A. Learner feedback on activities	77

Short term Changes in learners knowledge, intentions and attitudes	80

1. Summated feedback for all activities	81

2. Feedback on providers	85

3. Feedback on specific activities	97

Summary of Learner short term changes	102

B. Think for the Future case study	102

Why?	103

How?	103

Who?	104

Outcomes?	105

Conclusions	110

C. DANCOP v non DANCOP learners Over time	111

Learner characteristics and demographics	112

Aspirations	113

Key Influences	116

Confidence, motivation and academic fit	117

Knowledge of higher education	119

D. Parental Feedback	124

E. Teacher and other staff Feedback	125

Activity teacher feedback	125

ICEGS Survey	127

F. Feedback from Staff in DANCOP funded roles	132

Summary of impacts	132

4. Enablers, challenges and innovations	134

What worked and why?	134

Blended professionals	134

Individual development	134

Inclusion	135

Hubs, colleges and third parties	135

Developing a clear offering	135

Steering group	135

The IPG	136

Experimentation	137

DANCOP funded roles	137

Summary of ‘What works’	138

Challenges	138

Starting from new	138

OFS	138

Working with schools	140

DANCOP Structures and processes	142

Crossover and competition	143

Communication and coordination	144

Summary of challenges	145

Innovations	146

Network/collaboration	146

Activities	146

SUMMARY of innovations	146

Conclusions	148

Recommendations	149

References	149

Appendices	155

Focus Group Schedule (Think for the future mentoring)	155

Interview Questions for the central project team/committees	156

The Steering Group	156

The Governance Board	157

Innovations and Partner Group	158

Central Project Team	160

Hub Teams	162

Interview/Questionnaire Questions for Teachers (and HE Progression Officers –not yet implemented)	164

Interview schedule for activity providers	165

HEFCE – NCOP Impact Evaluation: participant baseline survey – Older Learners (Years 12-13) – DANCOP	167

HEFCE – NCOP Impact Evaluation: participant baseline survey – Younger Learners (years 9 and 10) – DANCOP	177

# List of Figures

Figure 1 Geographical remit of DANCOP (Target wards highlighted in red)	12

Figure 2 The NEURPI framework’s aims	31

Figure 4 Typical network structure	33

Figure 5 Expanded Kirkpatrick model of evaluation	37

Figure 6 Proposed DANCOP structure	55

Figure 7 Actual DANCOP Structure	57

Figure 8 DANCOP Sessions	128

Figure 9 Year groups	129

Figure 10 Effectiveness of DANCOP sessions	129

Figure 11 Relevance of DANCOP sessions	130

Figure 12 Changes in attitudes	131

Figure 13 Changes in behaviour, attendance and knowledge	131

# List of Tables

Table 1 DANCOP Targets	14

Table 2 DEMO strategies and associated characteristics	28

Table 3 Approaches to collaborating	34

Table 4 DANCOP Logic model with preconditions and assumptions	38

Table 5 Data Requirements	41

Table 6 Participant types and numbers to April 2018	47

Table 7 DANCOP schools and percentage of DANCOP learners in each	49

Table 8 Number of participants to date by assessment tool	52

Table 9 Institutions and their representatives on management groups.	54

Table 10 Wards and learners reached by DANCOP to August 2019	63

Table 11 Percentage of DANCOP learners in each school with number of activities delivered and number of engagements	66

Table 12 Percentages of schools engaged with mapped against priority status	70

Table 13 Activity types	73

Table 14 Delivery teams/partnerships and the number of activities they delivered	73

Table 15 delivery teams	76

Table 16 Assessing impact: participants and methods	77

Table 17 Activity ratings and percentage of respondents (empty cells represent 0%)	78

Table 18 Mean responses to before/after questions from all learners and all activities and paired sample t-test results.	81

Table 19 Mean responses and paired sample t-tests on before/after questions for Central/Widening access activities	86

Table 20 Mean responses to before/after questions for Derby hub activities	87

Table 21 Mean responses to before/after questions for Mansfield Hub activities	88

Table 22 Mean responses to before/after questions for Nottingham Hub activities	89

Table 23 Mean responses to before/after questions for UoD Widening Access activities	90

Table 24 Paired sample t-test results for Derby College deliveries	92

Table 25 Mean responses to before/after questions for WNC Outreach activities	93

Table 26 Mean responses and paired sample t-test results for before/after questions for IntoUniversity	94

Table 27 Paired sample t-test results for Performance in education deliveries	95

Table 28 Paired sample t-test results for The Access Project deliveries	96

Table 29 Significant and non significant changes in measures after undertaking activities	99

Table 30 School's % of DANCOP learners and numbers of DANCOP and non-DANCOP learners who participated in the survey	111

Table 31 Learner characteristics	112

Table 32 Preferred options at year 1 and year 2	114

Table 33 DANCOP  versus non DANCOP learners intentions to apply to HE at age 18/19 for year 1 and 2	115

Table 34 Greatest influences on decision making for DANCOP and non DANCOP learners in year 1 and 2	116

Table 35 Mean ratings for DANCOP v non DANCOP learners in year 1 and 2	117

Table 36 Mixed ANOVA results showing main and interaction effects for learner status and year with estimated effect sizes using partial eta squared.	118

Table 37 Knowledge of aspects of HE in DANCOP and non DANCOP learners at year 1 and year 2	121

Table 38 Mean impact ratings for DANCOP and non DANCOP learners at year 1 and 2	122

Table 39 Mixed ANOVA results for potential impacts of HE by DANCOP learner status and Year	123

Table 40 Parental ratings of activities	124

Table 41 Mean responses for parent respondents	124

Table 42 Delivery teams, activities and number of respondents	125

Table 43 Teacher ratings of activities	126

# Acknowledgements

The International Centre for Guidance Studies would like to thank the schools, colleges, learners and school and staff who participated in the research. In particular we would like to thank all of the staff members of DANCOP who were immeasurably helpful in the provision of information and data and were extremely giving of their time and insight. In particular we would like to thank Anna Davey and Vicky Cotterill for their help with data collection and analysis as well as Megan Hubbard and Alice Goodall on their helpful feedback and comments on previous drafts of this report.

# Executive Summary

## The Context

The National Collaborative Outreach Programme (NCOP) was developed to support the Government in meeting three goals:

- Double the proportion of young people from disadvantaged backgrounds in higher education (HE) by 2020

- Increase by 20 per cent the number of learners in HE from ethnic minority groups

- Address the under-representation of young men from disadvantaged backgrounds in HE.

In the East Midlands the NCOP consortia is the Derbyshire and Nottinghamshire Collaborative Outreach Programme (DANCOP) which is a progression of NEMCON (North East Midlands Collaborative Outreach Network) and is comprised from several universities and colleges of further education. DANCOP’s initial two goals were:

- Raise learners’ motivation to work hard and their understanding of the importance of education in their future:

- Equip learners to plan for progression and make appropriate choices for post-16 study and HE.

## Aim/Methods

This report includes an extensive review of literature on widening access, collaboration and networks and details a formative and summative evaluation undertaken by The International Centre for Guidance Studies (iCeGS) using data collected from February 2017 to May 2019. It reports on the progress made by DANCOP up until April 2019 with respect to:

- The development of the collaborative network

- The extent to which schools and learners have been engaged

- The perceived impact of activities on learners, feedback from learners, teachers and parents and distance travelled with respect to knowledge/attitudes/intentions pertaining to future options and in particular higher education

- Innovations in collaborative working and widening access

The evaluation has captured data from surveys, interviews and focus groups from DANCOP team members, management group members, learners, teaching and school staff, session deliverers and third party providers.

## Key Findings

- The network is well established amongst the HEIs, external stakeholders and FE colleges

- DANCOP has surpassed its targets with respect to school engagement and learner interactions

- It took a long time to establish the central and hub teams and recruit college based roles, partly because of the policies and processes inherent in HEIs and FECs but also because of non-competitive salaries and short term contracts.

- It took a long time to build awareness in schools and develop good working relationships so that activities could be delivered. In short term funded programmes this is a problem.

- DANCOP could work more quickly if legal, recruitment and financial issues and executive sign off could be facilitated.

- Collaborative work has been supported by:

  - Representation of key partners across different management groups

  - The structural and physical location of teams and individuals

  - An agile Steering Group and inclusion of further education colleges through the IPG

  - ‘Blended Professionals’ who have significant experience, knowledge and skills and are able to cross boundaries to get work done

- Key innovations have been the IPG, a small but agile steering group and using funding for longer term resources such as skills study coaches in colleges and the STEM Centre.

- With respect to activities, feedback has been almost entirely positive, and this includes learners, teachers, DANCOP staff funded roles and parents. This has been the case across the wide range of different activities which have been delivered, across year groups and across delivery teams.

- Activity evaluations show participants report significant increases in knowledge about HE and confidence.

- Comparisons of knowledge, attitudes and intentions between DANCOP and non DANCOP learners suggest there have been the desired changes in DANCOP learners. They have shown increased likelihood of attending FE and HE, increased sense of academic fit, increased confidence and increased knowledge of HE.

## Recommendations

- Longer funding cycles to allow time to develop, grow and refine the collaborative partnership, relationships with schools and provision as well as facilitating evaluation

- Clear guidelines and information about funding both from OFS and from central management to hubs and schools

- Employment of all staff through one institute

- Support services that are fit for purpose

- Time and space for establishing what works, for whom and which contexts

- Using third party providers for specialist activities

# Introduction

The National Collaborative Outreach Programme (NCOP) was developed to support the Government in meeting three goals:

- Double the proportion of young people from disadvantaged backgrounds in higher education (HE) by 2020

- Increase by 20 per cent the number of learners in HE from ethnic minority groups

- Address the under-representation of young men from disadvantaged backgrounds in HE.

NCOP began 2016/17 and will continue until 2021. It is comprised from 29 consortia who work collaboratively to deliver outreach activity in geographical areas where fewer than expected young people participate in HE. In this report we typically use the term Widening Access (WA) to refer to outreach or widening participation activity that seeks to fulfil the above aims. The consortia are made up from HE providers, colleges of further education, schools and other stakeholder organisations which include third sector organisations and Local Enterprise Partnerships (LEPs). Consortia are funded by HEFCE (now the Office For Students) who provided £30 million to support initialisation of programmes, £60 million per year in 2017/2018 and further funding is available (up to July 2021) should consortia demonstrate they have made progress in attaining the Government’s goals (https://www.officeforlearners.org.uk/advice-and-guidance/promoting-equal-opportunities/national-collaborative-outreach-programme-ncop/). These have in most cases built upon outreach networks developed through the National Networks of Collaborative Outreach (NNCO) which ran from 2014 until 2016. Their aim was broadly similar to NCOP and it worked by developing a single point of contact for schools in a region who coordinated outreach and provided advice and guidance to schools.

In the east midlands the NCOP consortia is the Derbyshire and Nottinghamshire Collaborative Outreach Programme (DANCOP) which technically was a progression of NEMCON (North East Midlands Collaborative Outreach Network) but in actuality began as a completely new collaboration that was built from scratch. DANCOP is comprised from several universities and colleges of further education situated in the region:

- University of Derby

- University of Nottingham

- Nottingham Trent University

- Derby College

- Nottingham College

- Buxton and Leek College

- Chesterfield College

- Stephenson College

- Vision West Nottinghamshire College

DANCOP’s provision aims to “inform learners and parents about all aspects of higher education, including college-based provision and higher and degree apprenticeships” (www.teamDANCOP.co.uk/about/) across a wide geographical area (see Figure 1 – HE participation gap wards are highlighted in red).

Figure 1 Geographical remit of DANCOP (Target wards highlighted in red)

This area has been described as the worst performing region in the country on a range of key indicators (Ofsted, 2016): Derby and Nottingham were among the ten lowest ranking local authority areas nationally for GSCE examinations – only 47.6% and 42.4% of learners respectively achieved the benchmark five or more A* to C grades including English and maths in 2015. The Chief Inspector of Ofsted at that time (Sir Michael Wilshaw, 2016) pointed out that there are very few high-performing multi-academy trusts in the region, while the support and challenge to schools from local authorities has not led to rapid enough improvement.

Whilst the NNCO NEMCON had made some positive progress, DANCOP argued that there were still several issues that influenced poor participation in HE in the region. These included:

- competing pressures in teachers’ workloads, leaving little time to organise participation in HE progression programmes

- competing priorities for schools, under pressure to improve GCSE attainment

- perceived lack of relevance of our current programmes in areas of low attainment and low aspirations

- lack of understanding of HE provision in FECs

- practicalities of travel: many schools and colleges are located rurally and therefore some distance from the nearest large university site, with limited public transport.

Thus DANCOP’s initial proposal had four main priorities:

- Establishing a central team to develop, coordinate and support the delivery of outreach on behalf of all partners

- Building schools’ capacity to engage with outreach and other progression-related activity by funding HE Progression Coordinator posts within schools

- Delivery of specialist targeted activity by third parties (including third sector organisations) to raise aspirations and attainment and to re-engage learners

- Promoting diversity and innovation in outreach, including the extension of outreach to remote gap areas, and supporting the capacity of FE partners to deliver outreach, through a fund into which FE partners can bid.

DANCOP’s initial two goals were:

1. Raise learners’ motivation to work hard and their understanding of the importance of education in their future:

2. Equip learners to plan for progression and make appropriate choices for post-16 study and HE.

These goals were developed into targets, see Table 1 below.

Table 1 DANCOP Targets

| Objectives | Milestones | Measurables |
| --- | --- | --- |
| Have a presence and impact in all 63 target wards. | Evidence engagement in all wards by the end of the academic year 2017/18. | Hubs to keep a register of learners engaged with each event and report back to Central team. |
| Engage with 3000 learners from target cohorts in the first academic year of the programme and 7000 in the second. | 3000 in year one and 7000 by end of year two | Collection of registers for all activities with name, date of birth and postcode of each participant and use of EMWPREP to track learners' engagements with the programme |
| Use targeting information to effectively prioritise time and resource | Engage with 80% of the highest priority schools in phase 1. Engage with 50% of the medium priority schools in phase 1. Engage with 25% of the low priority schools in phase 1 | Hubs to keep a register of learners engaged with each event and report back to Central team. Hubs to update monitoring returns on a monthly basis on the number of interactions with learners, teachers and parents. Targeting of appropriate cohorts by Hubs |

# Evaluation aims and objectives

The evaluation of DANCOP has five aims, each with a number of objectives:

- To produce a comprehensive mapping of the DANCOP structure and network in relation to its features and characteristics.

  - To what extent has the central DANCOP team worked effectively?

  - What roles have the steering group, governance board and IPG played in supporting the central team and how effective have they been achieving their aims?

  - What has the communication and division of roles between partners, hubs and the central development team been? Has it been effective?

  - How have DANCOP funded roles been implemented and what progress have they made?

  - Did the outreach programme reach remote areas and increase in diversity?

  - Has the network developed and piloted any innovative approaches to collaboration and outreach? To what extent have the IPG facilitated this? Has there been any wider learning and best practice that can be shared?

  - Has the network enabled any economies of scale, efficiencies in operation and service and reduction of duplication?

- Assess DANCOP’s progress against their stated targets.

- To assess the impact of the delivery of outreach in target wards

- Have learners developed positive attitudes, aspirations and motivations

- Have learners increased knowledge of career options, pathways and progressing to HE?

- Have learners increased knowledge and awareness of funding and support in progression routes/destinations?

- Have learners increased knowledge of how to study and revise?

- Have learners increased confidence?

- Assess perceived value and benefit

    - What do ‘users’ (schools and colleges) consider the value of this scheme to be? How were the activities perceived in terms of:

      - Relevance

      - Interest

      - Delivery

      - Effectiveness in achieving their aims

    - What did partners and stakeholders of the network perceive the value of it to be?

- Identify enablers, barriers and innovations: what has been good practice and what are the areas for improvement (formative assessment)

  - What has worked and why?

  - What were the key challenges?

  - What were the key innovations?

# Literature Review

## Introduction to outreach and widening access

Widening access and outreach refers to projects and activities that attempt to widen access to university for those learners who are under-represented in higher education. This encompasses learners from low participation neighbourhoods and disadvantaged and low income backgrounds. It also includes targeted groups such as looked after children/care leavers, disabled learners, young adult carers, adult learners, asylum seeking and refugee learners and learners from ethnic minority backgrounds. Widening access activities and projects are delivered in primary schools but are more commonly found in secondary schools where they are tailored to target the different needs of different age groups. Such activities encompass a range of different activities from one off class based workshops (where the focus might be on developing knowledge and understanding of HE), to serial, one to one mentoring interventions (designed to raise aspirations and change behaviour). Widening access activities are delivered by individual FE or HE institutions but are more commonly delivered by third party providers (often charities or social enterprises).

## The History of Widening Access and Collaborative Networks

The widening of participation in HE became prominent in the UK policy agenda in 1997 with the election of ‘New Labour’ who aimed to develop a highly skilled work force and promote social mobility (Whitty et al. 2015). At this time UK participation rates for young people in HE were low compared with international levels (OECD, 2005) and participation rates were particularly low for those from lower socioeconomic backgrounds (Wilkins & Burke, 2015). To combat this the government offered first the Excellence in Cities programme which aimed to (and succeeded to some extent) change motivation and behaviour in school aged children as well as improve learning and attainment (Kendall et al., 2005). This was closely followed by AimHigher: Excellence Challenge, launched in 2001 (becoming simply AimHigher in 2004 and running until 2011), a joint HEFCE and Department for Business, Innovation and Skills initiative. AimHigher provided funding to HE Institutes (HEI’s) which was used primarily for outreach work that aimed to 1. Recruit more individuals from disadvantaged backgrounds and 2. Provide them with financial support (Wilkins & Burke, 2015). West et al. (2005) demonstrated that participation in AimHigher: Excellence Challenge was related to increased attainment and increased year 11’s intentions to progress to HE. Passy & Morris (2010) conducted a national evaluation of AimHigher and were able to show that participation in AimHigher for some targeted groups of learners was associated with raised aspirations and improved attainment and progression (but could not demonstrate this was a causal relationship). However, schools and colleges who had taken part reported higher than predicted GCSE attainment and qualitative data suggested that the learners enjoyed participation and were more interested in entering HE. One element that appeared to be effective was the provision of learning mentors which research suggested did impact positively on mentees progression and attainment.

AimHigher was wound up by the coalition government in 2012 but the widening access imperative was maintained despite tuition fee caps being lifted in 2010. The coalition government instituted additional funding for learners from low income families and launched the National Scholarship Programme whereby universities offered extra financial help to learners from disadvantaged backgrounds. Further to this any university that wished to charge tuition fees in the bracket of £6000-£9000 was required to have an access agreement approved by the independent Director of Fair Access (Department for Business, Innovation & Skills, 2011). In 2014 the coalition government published their national strategy for access and learner success which was developed by Higher Education Funding Council for England (HEFCE) and the Office for Fair Access (OFFA) – the primary action within the strategy was the proposal for the National Network of Collaborative Partnerships (NNCOs).

The NNCO was a £22 million government funded scheme that ran from 2014 until 2016. The scheme, managed by HEFCE, aimed to widen participation into HE by forming local networks of universities and further education colleges to coordinate outreach work and by developing the Higher Education Access Tracker (HEAT) system for these networks to use to establish the longer term progression of learners. These collaborative networks were designed to bring universities and colleges together around the common issue of lack of participation in HE by some groups and support institutes in the shared design and delivery of outreach activities.

Within the networks the partnerships were tasked with coordinating programmes of outreach that aimed to reach all state funded schools and colleges. The NNCO scheme produced 38 networks comprised from 200 universities and colleges of further education who, between them, reached 98% of schools and colleges (Stevenson et al., 2017). Networks were encouraged to work with, and often did, local authorities and the relatively newly established Local Enterprise Partnerships (LEPs). Networks were required to establish a single point of contact who was tasked with establishing relationships with schools and colleges and who would coordinate the provision of accurate and quality information, advice and guidance to learners, teachers and other professionals working with young people (Stevenson et al., 2017). The national level evaluation team from The Sheffield Institute of Education at Sheffield Hallam University (Stevenson, et al.  2017) evaluated the NCCOs on a number of criteria:

- Their features/characteristics and the extent to which they were built on pre-existing partnerships

- Their engagement with LEPs and leverage of European Social Funds

- The extent to which networks ensured all state funded schools and colleges understood how to access HE outreach activity

- Whether networks were able to harness economies of scale, efficiencies in operation and service and reduce duplication

- Whether networks developed and piloted new or innovative approaches to outreach work

- Whether users, partners and stakeholders considered the scheme to be valuable

- Which elements were sustainable beyond the funding life cycle

Stevenson et al’s evaluation found that of the 38 networks established 16 were new, there was only limited engagement with LEPs (these were very newly established) and there was no use of the European Social Fund. However multiple partners were engaged with. The networks had established contact with all the schools and colleges within their remit however the extent to which schools engaged with the networks was variable. Whilst IAG was readily accessible, outreach activity was delivered in only targeted schools and groups. This was done to afford economies and efficiencies with work being delivered with those groups who were most in need. Efficiencies were also made through the use of social media and technology and innovations were made in terms of new knowledge, resources, best practice and access to these. Schools reported that the networks had impacted on learning and valued the opportunities. Networks reported that schools responded with organizational changes that would support the strategic use of outreach. Partners and stakeholders also perceived the networks to be of value. Overall the NNCO’s facilitated a more strategic approach with stronger relationships and collaboration and this had value for schools and learners. The main challenges appeared to be related to organizational structures/systems and communication.

The Government has since enacted the Higher Education and Research Act 2017, establishing a new regulator, the Office for Learners (OfS). Their remit is to encourage greater choice and establish further equality in access to, and participation in, higher education. To inform their decision making the DfE has published Securing Success (Dec, 2017) and has also published their strategy - Unlocking Talent, Fulfilling Potential - for developing social mobility. This strategy includes the National Collaborative Outreach Programme (NCOP) which has been awarded £120 million funding by HEFCE for outreach and widening access in 2018/19.

## Who is the focus of widening access?

In their comprehensive review, Moore, Sanders & Higham (2013) show that the individuals who are less likely to apply to and attend HE are typically:

- From low income households (as assessed through whether they qualify for free school meals (FSM), although this is in part due to differences in attainment)

- Live in POLAR3 (Participation of Local Areas) wards in the lowest quintile

- From families where parents have not attended HE

- State funded school or college attendees as opposed to independent school attendees

- White males from disadvantaged areas

- Adult learners (mature learners)

- Part-time learners

- From an ethnic minority group

- Vocational and work-based learners

- Disabled

- Care leavers

The Sutton Trust (2010) reported that learners who attended independent schools were 6 times more likely to attend a top university than those who attended a state school and 22 times more likely to attend a top university than learners who both attended a state school and were entitled to free school meals. They were 55 times more likely to achieve a place at Oxford or Cambridge University. One reason for these continuing differences is suggested by the Social Market Foundation who projected in 2016 that the government would fail to double the proportion of young people from disadvantaged backgrounds in higher education by 2020. They state that the strongest predictor of progression into HE is GCSE attainment but suggest that the target learners of widening access and outreach work continue to lag behind their counterparts on GCSE performance (Education Policy Institute, 2018). Consequently, the OECD (2016) has pointed out that widening access has to target deficits in underlying skills such as numeracy, reading, and writing (OECD, 2016).

Reed, King & Whiteford (2015) note that there is a growing body of evidence in widening access research that suggests that cultural and social factors are significant barriers to accessing HE. Many European governments and policy initiatives look to widen participation through financial incentives/support or through increasing block funding to universities but these approaches do not tackle the cultural and social barriers (Reed et al. 2015). Furthermore, funding is often done in short cycles but Reed et al 2015 argue that what is actually needed is a “longer term, holistic approach” (pp. 393) to actually achieve significant impact.

## What underpins decision making regarding attending HE?

#### Socio-cultural influences

Chowdry et al (2012) conducted a large scale, longitudinal study using national data sets and the data revealed the strongest predictor of whether a learner would progress to HE or not was the grades they achieved in secondary school. However, those who typically attained lower grades were also typically from lower socioeconomic backgrounds. Furthermore, these differences in attainment emerged early on; that is to say the effects of differences in socio economic backgrounds influenced future possibilities from an early age. This implies that social factors play an important role.

A predominant theoretical approach to understanding HE applicant behaviour is based on Bourdieu’s social theory, particularly the concepts of habitus and capital. Habitus refers to a disposition to think, act and behave in a given way but that the individual is not consciously aware of. It is the product of the social context in which the individual lives and for children this will typically refer primarily to the familial and school context. There is individual level habitus and class levels habitus and Reay et al. (2005) argue that educational institutes can also demonstrate habitus. There is evidence that familial and institutional habitus effects decision making regarding HE (Reay, 1998; Diamond et al. 2014).  Capital refers to formal and informal attributes that people may possess directly because of their familial, social and cultural background, for example language skills, cultural knowledge, educational qualifications or levels of confidence (Diamond et al. 2014, Perna & Titus, 2005). Social capital represents the benefits that individuals acquire from being part of established and enduring social relationships or networks (Bourdieu, 1985). Cultural capital refers to a person's education (their knowledge and intellectual capital) which can facilitate social mobility (Bourdieu, 1985). Social and cultural capital may be particularly important in terms of facilitating knowledge of HE as well as for the application process e.g. when writing a personal statement. Baars et al (2016) found that white working class boys found this to be a significant barrier during admissions. Perna & Titus (2005) found that levels of parental involvement (which they operationalised as a measure of social capital) were related to the likelihood of applying to university - Gorard et al (2012) found that parental involvement was related to educational attainment. Kettley & Whitehead (2012) argue that working class young people may be less likely to apply to university and particularly a top university not because working class parents are not supportive, but because the parents are unfamiliar with HE and the processes surrounding applications and fees (lack cultural capital). Cunningham & Lewis (2012) point out that some teachers can discourage working class learners from applying to the very top universities as they have a reputation for being selective both in terms of grades and in terms of social standing. Baars et al (2016) found that white working class families are less familiar with HE both in terms of what it involves and in the benefits it can bring. They are less likely to consider this as a viable option for their children even if they hold it as an aspiration for them. Thus white working class boys have real difficulty in accessing information and role models who might convey this.

A recent study by Gao & Ng (2017) provides initial evidence that social and cultural forms of capital have a multiplicative effect. The authors demonstrated that social capital moderated the effect of cultural capital on the educational aspirations of learners:

“the building of social capital (e.g. the direct and indirect communication between parents and the learner regarding college/university) could positively facilitate the development of cultural capital (e.g. parents’ and learners’ predisposition) and ultimately affected the odds of university enrolment” (pp. 16).

Thus, whilst there has been progress in widening access in HE, social class continues to be a strong determinant of educational attainment and progression (Whitty et al. 2015) and current findings still show that in the UK, family background has a significant effect on whether an individual will apply to and attend HE (Vignoles & Murray, 2016). This is particularly true of HE institutes at the top of the league tables where the number of entrants from widening access groups remains largely static (Whitty et al. 2015).

#### Cost-benefit analyses

An alternative approach to considering decision making regarding HE is to apply a rational choice cost benefit analysis framework. University degrees do not have equal economic value – both the subject studied and the type of university attended effect labour market outcomes and therefore wage benefits (Conlon & Chevalier, 2003; Iftikhar et al., 2009) with modern post 1992 institutes attracting a lower return on investment. Research suggests that learners from lower socio economic backgrounds are not only less likely to feel that HE is ‘for people like them’ (Archer, Hollingworth & Halsall, 2007) but are also less likely to apply to a top university (Harrison & Hatt, 2011). When they do apply it is more likely to be a modern ‘post-1992’ university (Connor, 2001).

White working class boys are particularly underrepresented in HE. They perform poorly compared to others in compulsory education and this partly explains why they are less likely to attend university (Baars et al, 2016) but other factors also contribute and this includes financial barriers (Baars et al. 2016); white working class boys have concerns that a university degree is not a worthwhile investment and this is an even stronger influence than the actual initial costs of studying (Baars et al. 2016).

The introduction of course fees has inevitably led to fees and finance becoming a focus for researchers (e.g. Atherton, Jones & Hall, 2015; Dunnet, Moorhouse, Walsh & Barry, 2012; Davies, Mangan & Hughes, 2009; Connor, 2001). Connor (2001) found that for those qualified to enter HE, deciding whether to attend or not was a complex process with learners being concerned about whether the costs of attending HE would realise sufficient benefits. Those choosing not to attend HE did so primarily because of a desire to go into employment and earn money more quickly. Dunnet et al (2012) found that although the introduction of fees had retained its relatively low importance as an influencer, it had led to ‘non-traditional’ learners (those whose parents had not attended university) having a greater loss of utility associated with attending university. Davies, Mangan & Hughes (2009) also report that learners who were ‘unsure’ that they would apply to HE were more pessimistic about a good degree enabling them to get a good job and were also more pessimistic about being able to gain a good degree in the first place.

## What works in outreach?

#### Designing evaluation of widening access and outreach

The last decade has seen an increasing importance attached to the evaluation of widening access from initial monitoring and tracking of interventions and spending, to identifying ‘what works’ to share good practice, through determining return on investment to meta-evaluation where evaluations themselves are evaluated (Crockford, 2019). Funding bodies now require institutes to write evaluation into their strategies and bids (Crockford, 2019) and assess the equality of that evaluation to demonstrate that the vast sums of money being invested are being spent on activities that work. The earlier AimHigher programme had been much criticised for its over reliance on qualitative and cross-sectional research which did not permit the attribution of causality to programmes of activities (Crockford, 2019) and now evaluations can be expected to aim at achieving the so called ‘gold standard’ of evaluation which is the RCT (Randomised Control Trial). However, it is important to note that evaluators have different approaches to considering what constitutes robust evidence in relation to WA and there has been a divergence in thinking (Crockford, 2019).

There remains a strong interest in evaluating WA interventions using experimental methods - RCT’s - where participants are randomly allocated to either an experimental group (who receives an intervention) or a control group (who does not). Whilst this allows the researcher to potentially control for extraneous variables which might account for variation in outcomes, the complexity of the social environment in which these interventions are delivered is such that it is unlikely that all these variables can be controlled for. There are a number of other methodological and ethical issues with using RCT’s in this context (Harrison & McCaig, 2017):

- The ethics of withholding interventions from some learners in order to facilitate an RCT

- The law of unmeasured consequences – RCT’s may focus on a small set of outcomes and neglect unintended outcomes

- Passage of time and overlapping interventions – the long term goals of WA interventions are to increase the number of individuals attending HE, however, the longer the time between an intervention and the desired outcome (which is effectively the case for some if not all WA interventions), the less able the research is to attribute the outcome to the intervention because of ever increasing confounding variables being introduced. Additionally, when learners are participating in a number of different activities, which is likely with the introduction and operationalisation of the Gatsby Benchmarks of good career guidance, it is impossible to unpick the effects of these different activities.

- Experimentation effects – these might include participant and researcher biases for example which in a medical RCT would be controlled for through double blind placebo protocol. The feasibility of this in an educational context is slim.

- Over-expectation – of large effect sizes which are unrealistic in such complex contexts

- Crude-utilitarianism – the use of averages in quantitative data to demonstrate outcomes can mask negative outcomes.

An alternative to running the RCT is to conduct a quasi-experimental study where the participants are not randomly selected into different conditions. However, whilst this design negates some of the ethical considerations it doesn’t remove the methodological ones. As Crockford (2019) notes whilst these ‘experimental’ designs might, if very well designed and implemented, be able to establish a causal relationship between intervention and outcome, they cannot explain why it has had this effect, thus “it is not capable of isolating what is effective and, crucially, generalizable, in WP outreach practice” (Crockford, 2019, p. 56). A focus on a small set of outcomes rather than understanding if the intervention has had an effect and if so on whom, and why, means that if the intervention is generalized there is no guarantee that it will have similar outcomes. In turn this can result in a waste of funding and indeed possible negative outcomes for learners (Crockford, 2019).

In response to this is a movement towards a ‘white box’ approach where a mixed methods evaluation attempts to consider the context in which the intervention is taking place and understand what the effects have been, for whom and why they might have occurred. Harrison & Waller (2016) have suggested that evaluations need to consider the interim changes that take place in learner’s cognitions, attitudes and behaviours before the long term outcomes to understand how WA might work. This approach fits nicely with a theory driven approach to evaluation which makes use of theories of change to hypothesise about what will work, for whom, in which context and why. The Widening Participation Research and Evaluation Unit (WPREU) based in the University of Sheffield have begun to adopt this approach in their work, a summary of which can be found in Crockford, Baker, Brown, Hordósy, Liskill & Miller (2019). Their key findings are discussed in the following section along with those from other evaluations.

#### Reviews of widening access and outreach

There have been a number of reviews of widening access/outreach work; Moore, Saunders & Higham (2013), Harvill et al. (2012), See, Gorard & Torgerson (2012), Torgerson et al (2008) and very recently a systematic review by Younger et al (2018). This latest review examined the findings of four previous systematic reviews and twelve experimental studies. The systematic review studies discussed by Younger et al looked at college access programmes in the USA (Harvill et al. 2012 and What Works Clearinghouse, 2006) and at post-16 participation and retention of ethnic minority learners in the UK (See, Gorard & Torgerson, 2012 and Torgerson et al., 2008). Both of the American reviews (specifically meta-analyses) found evidence for the effectiveness of so called 'black box' interventions - these are multi-activity interventions whereby the specific effects of particular activities cannot be isolated so any positive impacts cannot be attributed to a particular activity, just the combination of events. The What Works clearinghouse review found that taking part in the Talent Search intervention increased the likelihood of graduating high school by 17 percentage points as assessed via a quasi-experimental design evaluation (Younger et al. 2018). Harvill et al (2012) also found that college access programmes increased high school graduation as well as increased HE enrolment rates, and found evidence to support financial incentive programmes. However, they found that the size of these effects was dependent upon study design. Those studies employing less rigorous designs (e.g. quasi-experimental design as opposed to a randomised control trial) demonstrated larger effects.

The UK based review by See et al (2012) which was an updated version of Torgerson et al (2008) examined a group of fourteen studies comprised from a number of RCT's and other methodologies in both school and FE contexts. Their conclusions included consistent evidence that financial incentive programmes encouraged academic attainment in school contexts and that in both school and FE contexts, staff - learner mentoring improved academic attainment and retention (but peer mentoring did not) (Younger et al. 2018). The single studies Younger et al (2018) reviewed, which were predominantly American, examined a range of black box interventions in relation to a range of outcomes including academic attainment at school, likelihood of enrolling in HE, actual enrolments in HE, retention in/drop out from HE and quality of HE institute. The programmes examined included:

- the EXCEL tailored support programme (it provides enrichment activities such as mentoring, university campus visits, writing support and application support throughout high school and guarantees a scholarship to the sponsoring university)

- Talent Search (this offers academic, career, and financial guidance to support high school completion and enrolment into HE).

- Upward Bound (offers academic instruction, mentoring, cultural enrichment, work-study programmes and education/counselling services)

- Washington State Achievers programme (a whole school programme that provides mentoring and offers scholarships to eligible learners)

The impacts of these different programmes were mixed - some neutral, some positive. The most common outcome found was an increased likelihood of attending HE after completing maths and science elements of the Upward Bound course; this was using a quasi-experimental design. The EXCEL programme did result in a significant increase in enrolment at sponsoring institutes (see Younger et al. 2018) but the sample size was only 83. Evaluations of the WSA programme, whilst suffering from high attrition rates and lack of rigorous methodological design, suggest participants reported higher college aspirations and attendance and were significantly more likely to attend a high quality HE institution (Younger et al. 2018).

Studies examining the influence of single activity interventions reported a number of positive impacts. An RCT and several quasi-experimental design studies indicated that participants of financial aid interventions showed small but statistically significant increments in attainment, increased enrolment rates and increased retention (Younger et al. 2018).

An RCT designed evaluation of counselling in 'big picture' schools in America (these are schools whose curriculum focuses more on personal development and practical skill learning) was found to have significant impacts on college enrolment and type of course enrolled for, with counselling addressing personal issues such as aspirations and emotional issues as well as financial aid application.

Finally, one study (Niu & Tienda, 2010; cited in Younger et al. 2018), examined the impact of a change of state law to provision of guaranteed university places to the top 10% academic performers in high schools. This did not increase participation in HE from minority populations such as Hispanic or disadvantaged learners but did increase participation within the whole population.

The majority of the evidence discussed above is derived from America. Work by the WPREU at Sheffield includes evaluation of more than 10 different WA programmes in England using a variety of designs and methods. With respect to pre-16 evaluations their findings suggest that participants typically value the interventions they take part in and report increased academic skills and self-confidence. Of the WA deliverers they encounter, learner ambassadors appear to be particularly well received and are seen as ‘engaging and supportive facilitators’ (Crockford, 2019, p. 62.). One of the main problems encountered in conducting effective WA work pre-16 is the development and maintenance of personal networks with schools and the flow of information to parents and participants. These can be challenging at the best of times but the nature of the school sector which experiences rapid change, means this is even more difficult (Crockford, 2019). In evaluating sustained post-16 interventions Crockford reports that learner ambassadors are again valued and can be fundamental to fostering a sense of belonging. Social elements of sustained programmes are also important for positive outcomes because they facilitate the development of supportive networks. Programmes which provided participants with individualised segments to meet their own personal needs were also likely to be received positively. Where these things occurred, participants were likely to report that they valued the interventions and they perceived increased academic ability, increased employability and/or positive changes to attitudes.

There is a growing body of work then that uses a variety of approaches to evaluation and reports some positive outcomes. Whilst there is a lot of work from the USA, which demonstrates significant differences in education systems, minority groups and policies to the UK, it is nonetheless likely that many of the reasons underpinning decisions to not attend HE are similar to those in the UK. These include aspirations, confidence, attainment and financial concerns. The findings that black box interventions, financial incentives and counselling are effective to some extent in the USA is likely also relevant here. Of particular interest are the impacts of multi-faceted programmes, despite being unable to ascertain which features of the programmes might be responsible for impacts. Many institutes offer multi-faceted programmes and events that combine several different activities and indeed it is an aim of collaborative networks, e.g. DANCOP, to work with schools to produce programmes of activities delivered over time. When we also take the work from the UK, which adopts a range of approaches into account, there is evidence to suggest that some WA interventions can result in positive changes to academic ability, employability, attitudes and intentions. More research which explores the contextual and social factors which underpin these causal relationships would be extremely beneficial.

## Design matrices

As has already been noted, researching widening access interventions are varied and diverse. A number of authors have proposed matrices for the design, and evaluation, of widening access.

##### Anderson & Vervoon (1983)

Anderson & Vervoon (1983) state there are four conditions of entry to university:  Availability, Accessibility, Achievement and Aspiration. This matrix has been used as a framework for Gale et al’s study because it moves beyond the deficit model of widening access and takes into account structural barriers to participation erected by institutions, governments and systems.

##### DEMO

An Australian project examining outreach (Gale, Sellar, Parker, Hattam, Comber, Tranter & Bills, 2010) developed a design and evaluation matrix for university outreach programmes (DEMO). They concluded that effective programmes are long term, beginning in the final years of primary school or early on in secondary (Gale et al. 2010). Effective pre-year 11 (or year 10 in the U.K.) outreach work had 10 characteristics which sit under four strategies (see Table 2) and are aligned with three perspectives.

- Strategies:

    - Assembling resources – providing resources (human, money and time) to support and implement outreach

    - Engaging learners – learning and teaching of various orders

    - Working together – cooperation and partnership at various levels

    - Building confidence – in learners regarding themselves and what HE entails

Table 2 DEMO strategies and associated characteristics

| Strategy | Characteristics |
| --- | --- |
| Assembling resources | People-rich – enabling young people to develop ongoing relationships with those who can offer them guidance, support, mentoring and advice that is pertinent to their situation and capacities |
|  | Financial support and/or incentives - addressing the economic challenges or difficulties of specific groups |
|  | Early, long-term, sustained programmes – starting early, potentially in primary school, and continuing through secondary |
| Engaging learners | Recognition of difference – disadvantaged learners bring their own set of knowledge and learning capacities to education that should be recognised and considered as an asset. |
|  | Enhanced academic curriculum – developing and supporting ongoing high quality lessons throughout school and preparing learners for FE or HE |
|  | Research-driven interventions – these make use of the research capacity and ability within the university to underpin WA programmes, their implementation, their evaluation and the dissemination of this |
| Working together | Collaboration – amongst universities, colleges, WA providers and other stakeholders to support programme design and delivery |
|  | Cohort-based – engagement with whole classes, or even larger cohorts of young people in a school or region to change culture within that cohort |
| Building confidence | Communication and information – providing information about university, university life, how to apply and finance |
|  | Familiarisation/site experiences – university visits that include activities there which might inspire and familiarise the young people with HE, what learning at university is like and what facilities and support there is. |

The three perspectives that Gale et al (2010) argue should underpin outreach work are:

1. Unsettling deficit views

This refers to the premise that WA should be about working with others and not on them and it should be about working with those learners who are furthest away from HE and not those who have potential. Crucially however this perspective means having the same high academic achievement expectancies of all learners. WA learners who should come to perceive themselves as capable and HE as attainable but not at the cost of ‘watering down’ curricula. These learners therefore need programmes which have an ‘in-depth, intensive and long-term focus on rigorous and rewarding learning to build academic disposition’ (pp. 11). The programmes need to be intellectually challenging and have high expectations for the production of high quality work.

2. Researching ‘local knowledge’ and negotiating local interventions

This perspective acknowledges the importance of understanding the particular conditions of the local communities when designing interventions. Essentially this entails forming relationships with surrounding schools and communities and understanding their learners, backgrounds and particular issues before designing programmes. Furthermore there should also be scope for schools to negotiate what activities might take place

3. Building capacity in communities, schools and universities

This refers to the need to develop ‘cultures of possibility’ where the beliefs of learners and their parents are challenged and hopefully changed. This requires increased capacity in communities, schools and universities which includes more funding from government. Programmes should begin very early in school life especially in areas of high disadvantage to ‘generate cultural and dispositional shifts in learners, families and teachers in relation to aspiration and achievement’ (p.11).

Gale et al (2010) argue that effective programmes combine a number of characteristics from a balance of strategies and adopt as many of the perspectives discussed above as possible. Programme strength is therefore a function of the number of characteristics they have (this gives them depth) and the number of strategies that these characteristics are distributed across (this gives them breadth) (pp. 14):

- Weak programmes: have three or less characteristics from strategy or two characteristics from two strategies

- Moderate programmes comprise three or more characteristics drawn from at least two strategies

- Strong programmes comprise four or more characteristics drawn from at least three strategies

- Very strong programmes comprise five or more characteristics drawn from all four strategies

##### NERUPI framework

Hayton & Bengry-Howell (2016) introduced the Network for Evaluating and Researching University Participation Interventions (NERUPI) praxis based framework which can be used for designing and evaluating widening access interventions. Trialed at Bath University, the NERUPI framework makes use of "(1) theoretical perspectives and related academic research; (2) external monitoring requirements; and (3) evaluation processes to assess the effectiveness of institutional or collaborative interventions" (Hayton & Bengry-Howell, 2016, pp. 42).

The NERUPI Framework is underpinned by the theoretical concepts of capitals, field and habitus from Bourdieusian theory (e.g. Bourdieu and Wacquant, 1992). Capital is of three types; economic, cultural and social and with respect to education Bourdieau (1985) argues that social and cultural capital are critical to attainment and progression. It is cultural capital which is the primary determinant of differences in terms of academic achievement. In the NERUPI framework, social and cultural capital encompass educational skills and academic, intellectual and subject knowledge capital. The concept of capital is related to those of habitus and field. Habitus represents the dispositions individuals develop as a result of their specific familial environments (Harker, 1990) whilst field refers to a setting where individuals and their social statuses are located. An individual's particular location within a field is determined by the norms of the field, the individual's habitus and their capital (Bourdieu, 1985).

In the present context of WA, the NERUPI framework considers interventions in a field of engagement where the habitus of the learner, their school and the university intersect (Hayton & Bengry-Howell, 2016). The framework identifies a number of issues that learners classified as WA learners face (these are related to different forms of capital and habitus). Firstly they might well have aspirations to attend HE but, compared to non WA learners, might not, as of yet, have the capacity to realise these aspirations (Reay et al., 2005; Bok, 2010). A lack of individuals within their social networks who have knowledge and experience of HE to share with them (Ball and Vincent, 1998) means that they are not in possession of all the information when making decisions about their future and in particular have little knowledge or understanding of HE (Appadurai, 2004). A further two issues for WA learners are the extent to which they have the capabilities to navigate through HE when they get there and the extent to which they have the prerequisite skills for effective academic practice. The field of HE for them is likely to be unfamiliar and may present unique social and cultural challenges. Additionally they may be less skilled in abilities that underpin effective study, attainment and progression. The NERUPI framework has five aims, mapped against these (Hayton & Bengry-Howell, 2016, pp.46-48):

- Develop learners’ knowledge and awareness of the benefits of higher education and graduate employment

- Develop learners’ capacity to navigate higher education and graduate employment sectors and make informed choices.

- Develop learners’ confidence and resilience to negotiate the challenge of university life and graduate progression.

- Develop learners’ study skills and capacity for academic attainment and successful graduate progression.

- Develop learners’ understanding by contextualising subject knowledge.

The framework classifies interventions along 2 factors:

- The year groups at which they are aimed (levels 0 through 5 - Level 0 refers to anything that happens up to and including year 6; Level 1 refers to years 8 and 9, Level 2 refers to years 10 and 11, Level 3  is post-16, Level 4 is what they term ‘transition’ and Level 5 refers to activities that take place with learners in HE)

- The level of intensity of intervention (low, medium or high intensity)

Low-intensity interventions refer primarily to aspiration building activities, such as campus visits. Medium-intensity interventions are aspirational as well, but also include activities which help build the knowledge and understanding of how to progress to HE and what it might involve, for example GCSE options days or subject taster days. High-intensity interventions typically involve multiple interactions over time which seek to improve attainment or develop relevant skills such as mentoring programmes, summer schools or tutor schemes. Activities at these different levels and intensities are linked to sets of learning outcomes.

The framework sets out aims and objectives for interventions at each level. An overview of the framework, its five aims and the different capitals and curriculums these are mapped against can be seen below in Figure 2.

Figure 2 The NEURPI framework’s aims

Source: Hayton, A., Mackintosh, M., & Warwick, E. (2017) Theory, Practice & Impact in Widening Participation: A praxis based framework. Access to Higher Education and Learner Success Summit 2017

## Networks

A key element of NNCO’s and NCOP is the emphasis on collaboration between institutes and the formation of networks. Networks can be thought of as a “continuum between relatively weak or voluntary forms of partnership to stronger forms that are based on formalised partnerships.” (Stevenson, McCaig & Madriaga, 2017, pp. 14). This definition is derived from the work of Dhillon (2013) who argues that this continuum is comprised of four variables (Stevenson et al. 2017):

- Trust – the types and levels of trust between the different partners

- Network type – informal/formal, single/multi-level

- Norms and values – formal/informal, type of objective e.g. business and finance, support

- Motivations of participants – self interest to mutual interest

Networks can also be described in terms of their age, i.e. whether they are new, previously established or a combination of both, for example universities which have collaborated on previous projects but extend the network to include new collaboration with other institutes. The evaluation of the precursor to NCOP – the NNCO’s – found some evidence that those networks who had some pre-existing relationships/collaborations were able to develop efficacious collaborations more rapidly (Stevenson et al. 2017). For those NNCO’s who started from scratch as it were, the single point of contact (SPoC) was critical, playing what Stevenson et al term a brokerage role.

Stevenson et al’s (2017) evaluation describes a typical NNCO network with a form comprised of a lead institution, a management group, an operational group and post holders and single points of contact (for schools/colleges) (see Figure 4). The lead institution was responsible for putting individuals in the central team into post, liaising with and being accountable to HEFCE for the whole network and overall responsibility for finances. The management group had responsibility for the strategic priorities of the network and each institute in the network was presented within it. The operational group’s objectives typically entailed understanding the local context and identifying what outreach was needed as well as monitoring and evaluating performance, short term impact and financial activity. Post holders and single points of contact worked to map and gauge local outreach provision including gaps, duplications and individual school needs. They were also responsible for monitoring and evaluating activities and providing reports on this. Figure 4 below depicts lines of responsibility and reporting between the different components of the network.

With respect to the NNCOs, the evaluation concluded that whilst there was some evidence that pre-existing networks were initially able to develop more quickly than new networks, all networks eventually reached a point where they were operating effectively (Stevenson et al. 2017).

Figure 4 Typical network structure

Adapted from Stevenson, J., McCaig, C., & Madriaga, M. (2017) Evaluation of the National Networks for Collaborative Outreach (NNCOs).  Final Report to HEFCE by The Sheffield Institute of Education, Sheffield Hallam University

## Effective Collaboration

“Collaboration and partnership working in the context of widening participation and supporting learner success in higher education involve a range of structures within which institutions and organisations define shared interests and objectives and work together to design and deliver activities” (Wiggans, 2012, pp.3).

Development of collaborative networks can take place in different ways. Morris, Golden, Ireland & Judkins (2005) argue this is either done using a devolved or a specialist team approach. The former devolves delivery of the programme to the partner institutes but puts a co-ordinator in place to support them in this. The latter gives over delivery to a partnership appointed team of specialists. In the AimHigher evaluations EKOS (2007) pinpoint two approaches; centralised (the programme is delivered through a central team) and decentralised (individual institutes each receive responsibility and funding), but, note that larger collaborative networks used both approaches.

Issues arising in the development of collaborative WA agreements have been outlined by Booth (2007) who argues that partners need to “avoid overlap and duplication, address (the) lack of trust and concern for territory, minimise undermining influences and factors, keep increasingly anxious people and organisations on side and identify the most effective leverage factors” (pp.5). After the initial phase of start-up, collaborations can come to work in a number of ways - Booth (2007) identified four approaches to partnership working; Federalism, Co-opetition, Sharing platforms, Networked organisations (see Table 3).

Table 3 Approaches to collaborating

| Approach | Description |
| --- | --- |
| Federalism | There are both centralised and devolved functions and authority is allocated in accordance with the agreed division of functions. Power, roles and responsibilities are divided and the power that matters should reside as close to the action as possible. Power at the local level is not subject to alteration. Trust is critical. |
| Co-opetition | Institutionalised autonomy is maintained within a structure that combines the strengths of partners in a plan to pursue goals that meet both institutional and shared objectives. Partners make different contributions based on their strengths, such as information management, marketing or guidance and recruitment, to build an overall project through a team approach. Each partner is motivated to contribute to the whole because they believe they will benefit from the sum of the parts. They deliver more and higher quality outputs by using the complementary resources and knowledge that they bring to the collective approach. |
| Sharing platforms | The product is more important than the partnership and partners combine some elements of their own activities to build a bigger picture while maintaining the distinctiveness of individual providers. Partners work very closely together, have Steering Group members in common, share vital components and deliver different messages to distinctive sections of the community. |
| Networked organisations | Individual organisations come together to share ideas, discuss approaches and sometimes, but not always, act together. These networks may have the potential to link together a diverse range of partners using a few key governing principles. |

Sources: Wiggans, J. (2012). Collaboration and partnership working in a competitive environment. A literature synthesis of the Widening Access, Learner Retention and Success National Programmes Archive. York: Higher Education Academy

Research on the previous collaborations of Lifelong Learning Networks and AimHigher (Wiggans, 2012, pp. 3) concludes that working in collaborative networks can result in the following benefits:

1. Staff and organisational learning (schools, colleges and universities) regarding disadvantaged learners and the barriers for progression to HE

2. Development of valuable working links between different universities, colleges and schools and the development of relationships between individuals

3. A space which is independent from individual institutions for people to work towards the partnership objectives. It is freer from institutional constraints and permits sharing of ideas, knowledge and resources to work innovatively.

4. Provision of impartial information about education and career options post 16 and post 18

5. Capacity to use third party providers to deliver outreach which is more cost-effective.

Wiggans further notes that the factors which appeared to underpin these positive outcomes revolved around having the right employees, a sound partnership infrastructure with regular communication and coordinated processes which facilitate the engagement of learners with progression. It was important that central project and partner institution teams were comprised from committed, enthusiastic individuals (referred to as blended professionals) with high-level knowledge and expertise and that they were able to operate across boundaries to develop relationships and support collaborative working. It was also important that there was clear communication regarding allocation of funding, knowledge sharing and decision making. Findings have indicated a number of problems with collaborative working. External influences such as policy shifts and internal strategic priorities can take the emphasis off WA and institutes can fail to recognise the commitment, time and effort required to work in a collaborative network. In either case engagement in the network may not be sustained in the long term. Additionally there may be tensions between competing institutes and finally the structural approach of the collaboration has to be right in balancing devolving responsibility for delivery to institutes and achieving accountability for the use and impact of funding (Wiggans, 2012).

One issue relating to government funded collaborative networks is that the funding is only available for a limited period of time. The two implications of this are that 1. The networks may not have enough time to forge relationships with schools and design, deliver and evaluate activities/impact and 2.The sustainability of outreach work after funding has stopped. Findings from AimHigher and the LLN evaluations suggested that sustainability might be achieved in part by entrenching key WA activities within university access programmes, by consortia of universities developing their own funding pots and through organisational and employee attitudinal and knowledge shifts (Wiggans, 2012).

Reed, King & Whiteford (2015) argue that effective collaborative networks are facilitated through meticulous communication:

- regarding clarity of expectancies, goals, processes, timeframes and outcomes

- between and within partners to avoid misunderstanding of strategy and misalignment of individual agendas with institutional strategy

It is also important, state Reed et al (2015), that partnerships anticipate other risks such as prioritising one partners needs over another. They point out that this sort of behaviour can lead to what has been termed a 'vendor' relationship; here the vendor partner does not engage in the partnership as a long term collaboration but instead views it as a short term answer to some immediate need.

CFE conducted an interim evaluation of the NCOP consortia (published in March, 2018) and noted that the consortia, including that of DANCOP, had facilitated increased collaboration between diverse partners which in turn led to a more varied offer to learners with enhanced expertise. In particular the inclusion of FE colleges in the consortia meant that learners had access to information about alternative routes into HE. Consortia appeared to work most effectively when:

- the structures and processes in place were fit for purpose

- the consortia had a precisely articulated mission which was distinguished from previous collaborative partnerships

- staff were employed (but not necessarily located) centrally as this ensured consistency and focus

- staff embedded in other organisations maintained a clear NCOP identity for the deployment of impartial advice

- there was a degree of central control

- the communication between lead and partner institutions, and between strategic and operational teams, was effective and conveyed aims, objectives, rationales, processes and systems.

The key issues faced by consortia were the time it takes to establish new partnerships (particularly with FE colleges) and to form relationships with schools. Developing teams to oversee NCOPs and deliver activities took time because of the processes involved in recruiting staff.

# Methodology

## Evaluation Framework

The evaluation aims to be both formative and summative, using an expanded Kirkpatrick model of evaluation (see Figure 5) as a framework.

Figure 5 Expanded Kirkpatrick model of evaluation

The evaluation strategy was developed from the (simplified) logic model for the DANCOP project shown in Table 4 (full logic model can be seen in the Appendix). As Table 4 shows, the anticipated outcomes of the DANCOP programme have been mapped against the different outcome levels of the Kirkpatrick model; short term outcomes from DANCOP involve the reactions and learning of staff and learners, medium term outcomes reflect the behaviour of the staff and learners and long term outcomes are results based (e.g. GCSE attainment, applications to HE).  Based on the logic model a data requirements table was produced specifying the aims/objectives, variables to be assessed, methods to be used to measure variables, the participants and the timescale for each data collection phase (See Table 5).

Table 4 DANCOP Logic model with preconditions and assumptions

| INPUTS (ACTIVITIES) | OUTPUTS | OUTCOMES |  |  |
| --- | --- | --- | --- | --- |
|  |  | SHORT (uptake/reaction) | MEDIUM (learning) | LONG (behaviour) |
| Recruitment of new staff, formation of central team, hubs and project teams. | Building schools capacity to engage with outreach and other progression-related activity by funding HE progression coordinator posts within schools and officer level support roles. Includes development in each school of a sustained and progressive programme of outreach | 3000 plus interactions in first year and 6000 in second year By end of phase 1. 80%+ of high priority schools engaged with 50%+ medium priority schools engaged with 25%+ of low priority schools engaged with | Teachers: Increased knowledge of progression options, funding options | Teachers: Confidently talk about different progression routes and encourage all learners to explore FE and HE as viable options |
| Collection of data with learners before DANCOP activities began to understand the learner voice Formation of relationships with schools | Delivery of specialist targeted activity by third parties to raise aspirations and attainment and to re-engage learners. Dev of programme of options for schools and colleges that is individually tailored but collectively cohesive. Partners are likely to include IntoUniversity, Brightside, YMCA, Youth at Risk, Groundwork, Graduate Coaches, Brilliant Club, Sutton Trust, The access Project, Business in the Community, Enterprise for Education. Individual and small group coaching will feature heavily. | Teachers: Positive experiences of engaging with DANCOP Positive experiences of activities | Learners: Increased knowledge and awareness of progression options, funding, support and pathways into careers. Increased knowledge of how to study and revise Increased confidence Increased employability | Learners: Increased motivation to engage and succeed at school Increased intentions to progress into FE and HE |
| Building knowledge of local culture, attitudes and employment prospects | Promote diversity and innovation in outreach including extending outreach to remote gap areas, supporting capacity of FE partners to deliver outreach | Learners: Interactions with varied activities appropriate to own age and needs Positive experiences of activities |  |  |
| Audit of current provision (HE providers in the partnership) |  |  |  |  |
| Formation/development of collaborative partnerships |  |  |  |  |

Preconditions:

- Competing pressures in teachers’ workloads, leaving little time to organize participation in HE progression programmes

- Competing priorities for schools, under pressure to improve GCSE attainment

- Perceived lack of relevance of our current programmes in areas of low attainment and low aspirations

- Lack of understanding of HE provision in FECs

- Practicalities of travel. Many schools and colleges are located well over an hour from the nearest large university site with limited public transport

- Some key issues for learners are already emerging – low aspirations and/or low awareness of the link between education and rewarding employment; highly debt-adverse (removal of grants is significant); disengagement from education; low attainment

Assumptions:

Activities will overcome the challenges put in place by the above preconditions

- DANCOP hubs and central teams will undertake much of the organisation of participation in WA activities

- DANCOP will fund activities designed to support GCSE attainment

- DANCOP will build local knowledge and develop relationships with schools to enable them to provide tailored programmes relevant to their own specific needs

- DANCOP will provide activities which provide education about FE provision and different pathways and routes

- DANCOP will fund transport to activities

- DANCOP will develop activities which underpin aspiration, motivation and confidence building. They will offer access to mentoring programmes which support individuals with potential but have challenging backgrounds for example.

Table 5 Data Requirements

| FORMATIVE EVALUATION AIM 1. To produce a comprehensive mapping of the DANCOP structure and network in relation to its features, characteristics and the extent to which it has built upon NEMCON. Assess DANCOP’s progress against their stated targets |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | MEASURABLES | MEASUREMENT TOOLS | PARTICIPANTS | TIMELINE |
| 1.1 Produce a comprehensive mapping of DANCOP structure and network examining features and characteristics | DANCOP structure DANCOP features of collaborative network features and characteristics | DANCOP proposal Semi-structured interviews | Central team, Steering group, Hubs, partners | March 2018 March 2019 |
| 1.2 Measure progress against NEMCON | Progress versus NEMCON | Semi-structured interviews Monitoring and evaluation data and reports | Central team, Steering Group | March 2018 March 2019 |
| 1.3 Measure progress against targets | Progress Initial targets | Proposal Monitoring and evaluation reports Semi-structured interviews | Central team, Steering Group | March 2018 March 2019 |
| AIM 2. To understand how effectively the partnership is working |  |  |  |  |
| OBJECTIVE | MEASURABLES | MEASUREMENT TOOLS | PARTICIPANTS | TIMELINE |
| 2.1 How was the central team established? | Processes, procedures and timeline of team set up | Semi-structured interview | Steering committee and central team | March 2018 |
| 2.2 Did schools perceive their capacity to have been developed? How was the capacity developed? | Extent to which schools perceive their capacity to deliver HE progression has increased | Semi-structured interviews | School leaders and relevant teachers/staff | March 2019 |
| 2.3 What were the development plans? To what extent were the development plans effectively constructed and deployed? | Extent to which development plans in each targeted school were completed: - On time - To teacher/HE progression officer satisfaction Extent to which development plans were satisfactorily enacted/targets were met | Development plan documentation Structured interviews/questionnaires | School leaders and relevant teachers/staff | March 2019 |
| 2.4 What was the communication between the partners and the central team? Was this perceived to be satisfactory? | How did the various stakeholders communicate? Did they feel this worked? If not why not? | Semi-structured interviews | Central team, representatives from each partner institute | March 2018 and follow up March 2019 |
| 2.5 What targeted activity did the third party organisations provide and how effective was it? | Targeted activities by third parties and if it was effective | Monitoring and evaluation data collected by providers/central team Semi-structured interviews | Learners/teachers engaging in activities Learners, teachers, third party providers | Ongoing Ongoing |
| 2.6 In what ways did the outreach programme extend into remote areas and extend its diversity? Was this effective? | Diversity into remote schools | Monitoring and evaluation data collected by providers/central team Semi-structured interviews | Learners/teachers engaging in activities Learners, teachers, third party providers | Ongoing Ongoing |
| 2.7 What has been the interplay/partnership between the HE/FE providers and the third party activity providers? Have the complimented each other? Have the resources been distributed and used to their full potential? | How have partners, their own WA teams and third party providers collaborated? The effectiveness of this Resource dispersion and use | Semi-structured interviews | Central team, hubs, partner WA teams, third party providers | March 2018 March 2019 |
| 2.8 What innovative practices were used and how effective were they? | Innovative practice use | Semi-structured interviews | IPG, Central team, hubs, third party providers Relevant teachers | March 2018 March 2019 |
| 2.9 To what extent were deadlines met? | Deadlines | Semi-structured interviews Monitoring reports | Central team, Steering Group | March 2018 March 2019 |
| 2.10 What have been the main strengths of the partnership? | Strengths | Semi-structured interviews | Central team, Steering Group, Hubs, IPG | March 2018 March 2019 |
| 2.11 What have been the main challenges/issues | Challenges/issues | Semi-structured interviews | Central team, Steering Group, Hubs, IPG | March 2018 March 2019 |
| 2.12 What needs to be improved and could this be achieved? | Improvements | Semi-structured interviews | Central team, Steering Group, Hubs, IPG | March 2018 March 2019 |

| FORMATIVE EVALUATION AIM 3. Identify good practice and areas for improvement |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | MEASURABLES | MEASUREMENT TOOLS | PARTICIPANTS | TIMELINE |
| 3.1 What has worked? | Which activities impacted positively on learners? | Semi-structured interviews Monitoring and evaluation data Feedback | Central team and hubs, IPG Senior leaders/relevant teachers WA providers Learners | March 2018 March 2019 |
| 3.2 Why did it work? | What features of the activities account for their success? | Semi-structured interviews Monitoring and evaluation data Feedback | Central team and hubs, IPG Senior leaders/relevant teachers WA providers Learners | March 2018 March 2019 |
| 3.3 How could these be further developed and disseminated? | Could these be further developed and disseminated to other areas? | Semi-structured interviews Monitoring and evaluation data Feedback | Central team and hubs, IPG Senior leaders/relevant teachers WA providers Learners | March 2018 March 2019 |
| IMPACT EVALUATION AIM 4. To assess the success of the delivery of outreach in target wards |  |  |  |  |
| OBJECTIVE | MEASURABLES | MEASUREMENT TOOLS | PARTICIPANTS | TIMELINE |
| 4.1. Have learners developed - positive attitudes - aspirations - motivations - increased knowledge of career options and progression to HE? | Attitudes, aspirations, motivation, knowledge before and post project | Standardised online survey tailored to different ages Monitoring and evaluation data Semi-structured interviews | Learners Teachers | Ongoing Ongoing |
| 4.2 Evaluate the perceived value and benefits of DANCOP with respect to - Relevance - Interest - Delivery - Effectiveness in achieving their aims | Perceived benefits and value focussing on relevance, interest, delivery and efficacy | Semi-structured interviews Questionnaires | Senior leaders/teachers Central team, hub IPG, Steering Group Stakeholders WA providers Learners | Ongoing |
| 4.3 Has there been an increase in the number of learners with GCSE grades 4-9 to level 3 study with HE progression potential? | GCSE performance in each school from pre and post project years – consideration of GCSE measure of success ‘Attainment 8’? | School exam performance data | Schools/DfE | 2019 |

## Design

The most rigorous method for determining causality is the randomised control trial (RCT) design, developed for use in medical interventions, however the participants in this study, primarily young people at schools or colleges, could not randomly be assigned to interventions. A suitable substitute for the RCT in this situation is the quasi-experimental design - here there is non-random allocation of participants to groups (e.g. DANCOP learners taking part in activities and non-DANCOP learners who were not taking part). However as discussed earlier this approach suffers from similar methodological problems as the RCT. Where it has been possible to collect data from DANCOP and non-DANCOP learners this was incorporated into the design, specifically the study collected pre and post learner questionnaire data (see Appendix) from learners across several schools in Derbyshire and Nottinghamshire which included both DANCOP and non-DANCOP learners. For the evaluation of specific WA activities the study has so far typically only had access to survey information from the DANCOP learners taking part. It should be noted that whilst quasi-experimental data provides a comparison or ‘control’ group, interpretation of findings must still be cautious because there can be systematic differences between the groups.

## Timeline

The data presented here has been collected over time from the beginning of DANCOP in February 2017 until May 2019 and represents DANCOP’s progress up until then.

## Participants

The evaluation has collected data from a range of different participants – an overview of this can be seen in Table 6 below. Each group of participants are then discussed in more detail.

Table 6 Participant types and numbers to April 2018

| Participant type | N |
| --- | --- |
| Learners | 815 |
| Parents/carers/family | 2 |
| School staff members (includes DANCOP funded roles) | 30 |
| DANCOP team members (central team and hubs) | 16 |
| DANCOP committee members (IPG, Steering group) | 14 |
| Widening access activity deliverers | 2 |

#### Schools/Learners

As part of NCOP, HEFCE provided all consortia with a list of target wards from which they were able to work with learners from. These wards were identified from low levels of young progression to HE, and crucially have lower than expected progression to HE based on attainment. From the target ward list, the DANCOP team have calculated the percentage of learners from each ward that attend the schools and colleges within the D2N2 region (see Table 7).  In addition to collecting data from learners a number of staff working in schools whose roles are funded through DANCOP (N=4) were interviewed in a focus group and survey data was collected from staff in schools working with the different delivery teams (N=24).

Table 7 DANCOP schools and percentage of DANCOP learners in each

| School/College | % DANCOP learners |  | School/College | % DANCOP learners |
| --- | --- | --- | --- | --- |
| Quarrydale Academy | 92.91% |  | Nottingham Academy | 22.34% |
| Nottingham University Samworth Academy (NUSA) | 89.31% |  | The Becket School | 21.56% |
| Noel Baker School | 87.67% |  | Buxton and Leek College | 18.90% |
| Sutton Community Academy | 84.63% |  | St Thomas More Catholic School | 16.28% |
| Meden School - a Torch Academy | 84.49% |  | Eckington School | 15.65% |
| Ellis Guilford School | 83.94% |  | East Leake Academy | 14.51% |
| Bluecoat Beechdale Academy | 83.47% |  | Fernwood School | 14.14% |
| Da Vinci Community School | 78.63% |  | St Mary's Catholic High School | 13.00% |
| Merrill Academy | 77.09% |  | The Brunts Academy | 12.84% |
| Bulwell Academy | 74.92% |  | Alderman White School | 12.20% |
| The Bolsover School | 71.25% |  | Allestree Woodlands School | 11.61% |
| Shirebrook Academy | 63.74% |  | The Bemrose School | 11.32% |
| Holgate Academy | 62.81% |  | Kirkby College | 10.54% |
| Lees Brook Community School | 61.33% |  | Tibshelf Community School | 10.52% |
| The Farnborough Academy | 60.50% |  | Tuxford Academy | 9.00% |
| Ormiston Ilkeston Enterprise Academy | 60.00% |  | Arnold Hill Academy | 8.16% |
| The Oakwood Academy | 59.76% |  | Selston High School | 7.70% |
| The Dukeries Academy | 57.68% |  | Tupton Hall School | 7.23% |
| Swanwick Hall School | 56.41% |  | Derby Moor Community Sports College | 6.80% |
| David Nieper Academy | 55.24% |  | Chapel-en-le-Frith High School | 6.12% |
| Top Valley Academy | 54.41% |  | The Long Eaton School | 5.13% |
| Magnus Church of England Academy | 53.11% |  | The Manor Academy | 4.90% |
| Hall Park Academy | 51.29% |  | Granville Sports College | 4.86% |
| The Nottingham Emmanuel School | 50.42% |  | Rushcliffe School | 4.63% |
| Nottingham Girls' Academy | 50.22% |  | Carlton le Willows Academy | 4.52% |
| Aldercar Community Language College | 48.75% |  | Garibaldi College | 3.76% |
| Netherthorpe School | 46.91% |  | Chilwell School | 3.55% |
| City of Derby Academy | 46.28% |  | South Wolds Academy | 3.51% |
| Ashfield School | 44.32% |  | Hasland Hall Community School | 3.26% |
| Murray Park School | 43.61% |  | The Ripley Academy | 3.26% |
| Kirk Hallam Community Academy | 42.69% |  | John Flamsteed Community School | 3.17% |
| The Bramcote School | 41.24% |  | Colonel Frank Seely School | 2.93% |
| William Allitt School | 39.35% |  | Chellaston Academy | 2.74% |
| St Benedict – A Catholic Voluntary Academy | 38.04% |  | The Queen Elizabeth's Academy | 2.52% |
| The Trinity School | 37.69% |  | Hope Valley College | 2.20% |
| Heritage High School | 36.49% |  | Toot Hill School | 1.95% |
| Newark Academy | 36.24% |  | The Minster School | 1.54% |
| Saint John Houghton Catholic Voluntary Academy | 34.49% |  | West Bridgford School | 1.46% |
| Landau Forte College | 33.95% |  | Outwood Academy Portland | 1.44% |
| The Pingle School | 33.83% |  | Lady Manners School | 1.20% |
| The National CofE Academy | 33.75% |  | Whittington Green School | 1.08% |
| The Carlton Academy | 31.66% |  | Parkside Community School | 1.07% |
| Frederick Gent School | 31.28% |  | Brookfield Community School | 0.98% |
| Heanor Gate Science College | 29.44% |  | Outwood Academy Newbold | 0.81% |
| George Spencer Academy | 29.24% |  | South Nottinghamshire Academy | 0.76% |
| The Kimberley School | 28.99% |  | Littleover Community School | 0.73% |
| Bluecoat Academy (Wollaton) | 28.80% |  | Queen Elizabeth's Grammar School | 0.68% |
| Buxton Community School | 28.54% |  | John Port School Academy Trust | 0.62% |
| Wilsthorpe Community School | 28.32% |  | Belper School | 0.62% |
| Christ the King CVA | 27.88% |  | Ecclesbourne School | 0.57% |
| West Park School | 27.27% |  | New Mills School and Sixth Form | 0.55% |
| Friesland School | 27.24% |  | Outwood Academy Valley | 0.45% |
| The Samworth Church Academy | 26.83% |  | Retford Oaks Academy | 0.41% |
| Springwell Community College | 26.69% |  | Dronfield Henry Fanshawe School | 0.31% |
| The Joseph Whitaker School | 26.48% |  | Highfields School | 0.22% |
| Djanogly City Academy Nottingham | 24.03% |  | Anthony Gell School | 0.15% |
| All Saints Catholic Academy | 21.03% |  | The Elizabethan High Academy | 0.09% |
| The Redhill Academy | 20.94% |  |  |  |

#### DANCOP teams

Focus groups were run with the following groups/teams involved in DANCOP:

- The central DANCOP management team including the project manager, partnerships manager and operations manager

- Central DANCOP team members including project officers and the monitoring and evaluation officer and assistant

- The Derby hub team

- The Nottingham hub team

- The Mansfield hub team

- The Innovations and Partners Group (IPG)

- The Steering Group (SG)

#### Widening access Deliverers

Within DANCOP, individuals from the central team, hubs, partner institutes and third party providers were all responsible for the delivery of WA activity. The evaluation team has conducted interviews with the central team, hubs and three of the third party providers.

## Methods

The evaluation team has so far collected quantitative and qualitative data using a range of methods (see Table 8 below) regarding perceptions, experiences, knowledge, understanding, attitudes and intentions from as many learners as possible and from as many schools as possible.

Table 8 Number of participants to date by assessment tool

| Assessment tool | Number of participants | Number of schools/colleges involved |
| --- | --- | --- |
| Standardised survey assessing pre and post knowledge, attitudes and intentions regarding HE (Both DANCOP and non DANCOP learners) | Circa 400 paper and online responses | 6 |
| Activity evaluation surveys (primarily DANCOP learners) | 890 | 26 |
| School staff evaluation surveys | 24 | 24 |
| Focus group discussion pre and post long term activities (DANCOP learners) DANCOP teams DANCOP funded roles in schools | 70 35 4 | 2 4 |
| One to one interviews Third party providers | 3 |  |

#### Standardised CFE Survey (Pre/post NCOP engagement)

This was designed by CFE, the national level evaluators for NCOP, with evaluation teams for each consortia invited to input/provide feedback. Two versions were developed; one for learners in years 12 and 13 and one for younger learners (see the Appendix). These questionnaires collected some personal and demographic data (in part to allow matching of responses across time points). The pre DANCOP programme standardised survey (see the Appendix) data was collected early in the 2018/2019 academic year (September-October). In order to recruit learners for this survey, the evaluation team used school/staff contact details provided by the DANCOP team to email appropriate link staff asking for their cooperation. Schools were able to access the survey online through a link provided by CFE or, if they felt it was more appropriate for them, they were able to request paper copies supplied by iCeGS. Participation in the survey was incentivised through the chance to win an iPad.

A second questionnaire was issued in September 2018 and a third in May 2019 to assess shift on the assessed measures.

#### DANCOP activity evaluation surveys

DANCOP has a standardised feedback sheet for learners to complete whenever they engage in an activity (see the Appendices). The survey has a series of questions which each WA deliverer, whether working for a partner institute or a third party provider, must retain but also has a section where the WA deliverer can add their own questions from a bank of preapproved questions. Learners are asked to answer each question twice - once before the activity and once after. This provides insight into shifts in knowledge, attitudes and intentions over the course of the activity.

#### School staff evaluation surveys

A short evaluation survey was sent to participating schools to assess their perceptions of engaging with DANCOP and potential impacts on learners and the school (see Appendix).

#### Focus Group Discussions

Semi-structured interview schedules were developed (see the Appendix) for focus groups.

1. The evaluation team has to date run six focus groups with 70 learners taking part in several different activities.

2. Focus group discussions using semi-structured interview schedules were run with the DANCOP central team (management and non-management roles were interviewed separately), Derby hub team, Mansfield hub team and Nottingham hub team, the SG (5 members) and with the IPG. Interview schedules for these can be seen in the Appendix.

# Findings and Analysis

The results and analysis are presented by the aims of the evaluation outlined in section 3.

# 1. The structure of the network and the collaborative partnerships

## Who is involved?

In the original DANCOP proposal, the following institutes were named as partners:

- University of Derby

- University of Nottingham

- Nottingham Trent University

- Bishop Grosseteste University

- Derby College

- Nottingham College

- Buxton and Leek College

- Chesterfield College

- Stephenson College

- Vision West Nottinghamshire College

When initial interviews and focus groups were conducted with DANCOP team members in March 2018, and later when final interviews were run, all three universities in Derby and Nottingham were fully engaged with the collaboration. Bishop Grosseteste University had not engaged but this institute is not located within Derbyshire and Nottinghamshire so although they had expressed a desire to work with learners in the Newark ward this has not transpired. College engagement had been variable with Buxton & Leek and Stephenson showing less involvement – Table 9 shows the spread of institutes in terms of representation on the three different management groups (Innovations and Partners Group, steering group and Governance Board). Buxton & Leek are not represented at all and Stephenson only on the Innovations and Partners Group (IPG). FE colleges have found themselves in a tumultuous climate with some facing large scale redundancies. For some institutions this has resulted in significantly less engagement with the network and collaborative efforts as it is no longer a key focus. Furthermore there were difficulties in recruiting staff to projects when others were being made redundant and existing college staff tangentially working on the project either were being made redundant or did not know how long they would be there. Where colleges were more stable, and in particular where there was a key member of staff serving as a representative on one or more management groups, engagement was better. One more factor which had led to better engagement is the department in which the DANCOP project staff have been placed, for example in one college it was in the marketing team (less effective) whilst in others it is alongside existing widening access colleagues (more effective). Both structural and physical locations have impacted on how well people have worked together (this is discussed in more detail later).

Table 9 Institutions and their representatives on management groups.

| Institutions | IPG | Steering Group | Governance Board |
| --- | --- | --- | --- |
| Derby College | X | X | X |
| West Nottinghamshire College | X | X |  |
| Stephenson College | X |  |  |
| Nottingham College | X |  |  |
| Chesterfield College | X |  | X |
| University of Nottingham |  | X | X |
| Nottingham Trent University |  | X | X |
| University of Derby |  | X | X |

NB. The Governance Board also contains representatives from the D2N2 LEP, Derby City Council and Nottingham City Council.

## How is DANCOP structured and what are the roles?

The original plan for the DANCOP management groups and teams structure can be seen in Figure 6.

Figure 6 Proposed DANCOP structure

Innovations and Partners Group

(Chair: FEC HE Head)

Operations Group

(Chair: Project Manager)

Steering Group

(Chair: HEI WA/Outreach head)

Governance Board

(Chair: Lead HEI Pro-Vice Chancellor)

The roles and objectives of each group in Figure 6, as detailed in the original proposal, are outlined below:

“A Steering Group will shape the direction of the project, identifying key issues and priorities, agreeing targets and deciding the overall balance of expenditure, as well as the allocation of funds. This Group will work closely with the Project Manager to develop detailed plans, ensuring adherence to HEFCE guidance. It will be responsible for ensuring that the project fulfils HEFCE reporting requirements. The Steering Group will comprise a small group of key representatives, including a representative of each partner university, one to two representatives of the Further Education Colleges and a representative for schools. These representatives will be suitably experienced outreach experts at either Head or Manager level within their organisations. The Project Manager will report to the Steering Group and will attend its meetings (along with other employees of the project as required) to report on progress. The group is intentionally small to facilitate quick decision making and a relatively frequent meeting schedule (every month). Other partners or organisations will attend as required by meeting agendas. The Steering Group will report into the Governance Board through its Chair.

An Innovations and Partners Group will be charged with allocating and monitoring funds for smaller-scale activity, tailored to the needs of specific areas and reflecting educational pathways available in individual Further Education Colleges. All FECs in the consortium will be represented on this group, other partners and school representatives will be able to bring submissions for smaller-scale activity to the group as needed. This group will be Chaired by an FEC lead at Head level. This group will provide reports to the Steering Group.

An Operations Group will also be established. This will be Chaired by the Project Manager and will be attended by the central project team. This Group will cover day-to-day operational matters, and will make decisions on minor operational issues within agreed plans to ensure smooth and efficient working practice. The Operations Group will produce reports for the Steering Group and contribute to reports for the Governance Board. The Group will meet monthly.

A Governance Board will be Chaired by a PVC from the University of Derby (the lead institution) and include a senior representative from key partners and stakeholders (LA, LEP, third sector and school representatives). The Project Manager and Chair of the Steering Group will attend to present reports. The Board will monitor the implementation of plans and progress against targets; and review expenditure. The Board will meet once or twice a year.”

The actual DANCOP structure, including hubs, in March 2018 is detailed below in Figure 7 and this structure remained in place at follow up in March 2019.

The Steering Group (SG) in practice is much as it was outlined in the proposal, having retained its small size (five members with the project manager as a co-opted member without voting rights) and meeting once a month. However membership had changed over time with people leaving representative institutes and being replaced. Its primary role has been to guide the aims, objectives and general approach of the project manager in the central DANCOP team to ensure that the programmes and projects making up DANCOP are relevant. The SG also approve expenditure on projects. The group receive a monthly report from the project manager on schools/colleges and providers engaged with and the learners who have engaged with activities – they ensure that the work being done fitted within the guidance and funding given by the Office for Students (OFS). The SG report to the Governance Board, providing financial and activity reports, who serve as an executive sign off and might alert the steering group to opportunities not being fully taken advantage of.

The Governance Board (GB) was comprised of representatives of the key institutions as well as representatives from the D2N2 Local Enterprise Partnership (LEP), Derby City Council and Nottingham City Council. The project manager also attends GB meetings as does the chair of the SG. The GB do not typically become involved with day to day communications, however, because GB members represent partner institutions they will, as individuals, be working directly with the project manager around specific requirements, projects or activities. For example the D2N2 LEP representative as worked directly with the project manager to drive two projects forward.

Figure 7 Actual DANCOP Structure

Governance Board

Chair: Lead HEI Provost

Steering Group

Chair: Director or Head from partner institution

Innovations and Partners Group

Chair: Partner FEC Director or Head

Colleges DANCOP funded posts

DANCOP Central Team

Project Manager, Operations Manager, Partnerships Manager, Monitoring and Evaluation Officer, Monitoring and Evaluation Assistant, Higher and Degree Apprenticeships Officer, Communications Officer, Creative Industries Officer, Lead Project Officer, Project Officer, Project Assistant, Project Administrator, Finance Co-ordinator

Derby Hub

Lead Project Officer,

Project Officer x3,

Administrator

Mansfield Hub

Lead Project Officer,

Project Officer x2, Events Coordinator, Administrator (Vacancy)

Nottingham Hub

Lead Project Officer,

Project Officers x 3,

Administrator

SCHOOLS IN NOTTINGHAMSHIRE WITH DANCOP LEARNERS

SCHOOLS IN CHESTERFIELD/MANSFIELD AREAS WITH DANCOP LEARNERS

SCHOOLS IN DERBY / DERBYSHIRE WITH DANCOP LEARNERS

The IPG is chaired by an appropriate Director or Head in a lead FE College. The structure and roles represented in the IPG have remained the same over time but the representatives from the different institutes have changed. It was noted by the IPG during their second focus group that the “nuances within it have changed with personnel” with different perspectives and backgrounds being brought to the fore. At the first focus group the IPG served to identify innovative projects but practically had become a forum for college partners to discuss and develop activities and ideas they had for future activity in individual institutions or specialist areas. By the second focus group the IPG had developed a role which sat at a distance from the SG and which considered the impact of activities. It has been developing knowledge of what will work and what won’t work. With the reduction in funding size from 2017 to present the IPG use their knowledge of what works to develop the effective projects that are already in place. The IPG noted that for DANCOP the FE’s had a more substantial influence than in other NCOPs which had permitted the IPG to become more operational in nature. Their shift represents a shift from phase 1 which was concerned with embedding in-reach, to phase 2 which is concerned with reviewing and refining the in-reach and being an important source of information, feedback and intelligence from the FEI’s to the rest of the NCOP which otherwise could be too HEI focussed.

In the original proposal, the structure included an operations group – this is effectively the central DANCOP team and so the term ‘operations group’ is not used in the parlance of the various DANCOP members. The central DANCOP team is in charge of day to day operational matters, and conducts decision making regarding minor operational issues within agreed plans to ensure smooth and efficient working practice. The project manager prepares reports for the SG on targets, activities and expenditure and contributes to reports for the Governance Board. The central DANCOP team was the initial team to be established and hence originally it conducted much of the awareness raising and relationship development with schools. This has shifted now as relationships and direct liaison with individual schools has become more the domain of the three separate hubs.

The central DANCOP team comprises four unique roles; the project manager, the monitoring and evaluation officer, the partnership lead and the Degree and Higher Apprenticeships officer. The project manager overseas all the central team members as well as liaising with the SG, the IPG and the GB. The monitoring and evaluation officer’s role is to track engagement with schools, the activities delivered, the number of DANCOP learners reached and collate and evaluate learner, teacher and parent feedback on activities delivered. This requires the officer to also work with the external evaluation team (iCeGS) and the East Midlands Widening access Research and Evaluation Partnership (EMWPREP). EMWPREP is an organisation which institutes can join; members can pool resources to for a range of services which facilitate a systematic approach to the monitoring and evaluation of the effectiveness of their programme of outreach activities. Services provided by EMWPREP include:

- Monitoring and evaluation of institutions’ outreach programme

- Evaluation of discrete outreach activities

- Targeting learners for outreach activity

- Analysing partner institutions’ learner data

- Monitoring and Evaluation Database co-ordination

- Designing and implementing bespoke research and data methodologies as per partnership requirements

- Maintaining a bespoke national postcode database to provide key socio-economic and demographic information on various groups

- Undertaking literature reviews

- Delivering presentations to disseminate research findings.

The partnerships manager is relatively new in post (April 2018) as the central team found that forming, developing and maintaining relationships with third party providers and other partners was a full time role and not something that could be undertaken by the project manager. The partnerships manager has line management responsibilities for the monitoring and evaluation officer and the communications officer. Additionally the partnerships manager oversees the operational development and delivery of programmes and services delivered by third parties and IPG college based DANCOP teams. This involves the monitoring of spending and progress against targets and implementing action plans to ensure KPI's are achieved. Finally the partnerships manager also has responsibility for procurement and contract creation for third parties and deputises for the DANCOP project manager.

The higher and degree apprenticeships officer role was created because the SG and Governance Board stated early on that they felt there was a need for someone to focus specifically on higher and degree apprenticeships. The role involves providing information, education, advice and guidance on higher and degree apprenticeships to schools.

The hubs were a later addition to the DANCOP structure primarily because of the time it took to recruit and full these posts. Each hub has approximately four staff including a lead project officer and at least one (but typically two) project officer. These roles were employed through the HEI or FEI in which they were located physically. Their primary function is to form, develop and maintain relationships with schools within their separate geographical remits. They serve as a form of single point of contact for schools. Hubs work with schools to encourage them to engage with the activities from individual institutes (e.g. University of Derby forensic science day), central DANCOP (Higher and Degree Apprenticeship talks) or third party providers (e.g. IntoUniversity FOCUS workshop series). Hubs can also work with schools to develop individually tailored events designed specifically to meet the schools specialist requirements. Schools have differing numbers of DANCOP learners so the hubs might prioritise working with schools with higher numbers of DANCOP learners. The most significant difference between first and second interview in the role of the hubs has been the decrease in use of third party providers to the hub teams doing delivery of activities. This was a significant increase in work load for the hubs and led to additional project officers being appointed.

DANCOP College funded roles were rolled out over the course of the first year and these officers worked to deliver in-reach and target schools for out reach. These roles were funded by DANCOP but employment was through the college. On occasion these roles have worked in collaboration with third parties.

## Features and Outcomes of DANCOP

### Structure

The structure of DANCOP remains largely unchanged from the proposal but is more nuanced than the typical NNCO structure developed by Stevenson et al (2017) as it delineates the SG from the GB, it does not have a formal 'lead institution' group (rather lead institution representatives appear on both the SG and the GB, as do representatives from all HEI's), and single points of contact have been replaced by hubs. Hubs are delineated from other providers, schools and colleges. One recommendation from Stevenson et al regarding the NNCO's was that innovative practice should be captured and shared - hence the IPG which is a feature of DANCOP.

The DANCOP network can be classified as a new network since there was no cross-over from its precursor NEMCON. It is also a formal network with multiple levels. Since all the partners are represented on the management groups and have hubs, and in some cases specific widening participation (WP) officers, there appears to be equity and trust across partners. However, it was noted that the university which hosts the central DANCOP team had different strategic objectives regarding widening access compared to the other two HEI’s. In the case of the former, focus was, and may remain on, widening access. In another HEI the focus had shifted towards retention. Whilst this was not problematic at the point of data collection in March 2019 it was clear that it was perceived to be one with respect to sustainability after the funding stopped. Nonetheless, by March 2019 there remained shared values and mutual interest with respect to motivation to be involved in DANCOP, both these features support effective networks.

The collaboration has adopted a specialist team approach (Morris et al, 2005) whereby delivery is given over to a team of specialists (or in this case a central team and three hubs) appointed by the partnership. In terms of centralised v decentralised the collaboration shows elements of both; the programme has a central team which delivers some elements but there is also some decentralisation as separate teams have been appointed and given their own responsibilities. In many ways this worked well within DANCOP with each hub being comprised from ‘blended professionals’ who all brought commitment to supporting learners, experience and knowledge. Over time however the hubs had formed their own identities to some extent, e.g.

“we’re known as the hub that just gets on with it”  Hub team member

Furthermore, the central project team and host HEI hub had developed different specialisms (the host HEI hub had its group of schools whereas the central project team focused on specialist and larger scale projects) so as to differentiate their offers - decentralisation was being developed. This did mean that for some (but not all) schools, there was a clear point of contact because each hub had responsibility for a particular group of schools. Some schools – primarily those with high percentages of DANCOP learners who had well established relationships with DANCOP – were therefore able to work more closely with their hubs.

A disadvantage of increased decentralisation is that teams sitting on the periphery of the structure can feel isolated and removed from decision making and this was noted by the hubs:

“….you sometimes feel out of the loop of decisions and things… something has happened centrally and then the repercussions ripple out to you but you don’t fully understand why or how or what” Hub team member

### Central v decentralised employment

The interim evaluation of NCOP by CFE noted that partnerships worked better when all employees were employed centrally (but located differentially) because firstly it ensured focus and secondly it ensured consistency. In DANCOP there was no evidence that being employed through different institutes had a negative effect on focus. DANCOP team ethos was well developed across all the teams and there was a clear, shared mission. However, there were several inconsistencies in employment practices and organisational culture, processes and performance which resulted in several issues relating to recruitment, job satisfaction, intention to quit and retention.

In the first instance the IPG college representatives noted they had faced significant problems and delays in recruiting project officers to colleges because of the fixed-term nature of the role and the lower salary (compared to project officer roles based in HEI’s). They also noted that the ambiguity surrounding funding and the length of the role meant the college officers were considering applying for other roles which meant the difficult cycle of recruiting would have to begin again.

The perceived inequity across DANCOP project officers was not unique to the college based roles. Because the three hubs were employed by two different HEI’s and an FEI, there was also inconsistency in salary, holiday entitlement and time off in lieu practices. These had become apparent to the different team members so although the hub and central project team members remained committed to delivering high quality outreach, there were clear indicators of dissatisfaction, for example some project officers refusing to commit to residential trips because they would not receive equivalent time off in lieu (TOIL). This impacted on other hub teams too:

“because of the negative impact it has on them, it affects the rest of the team”

“…generally speaking our terms and conditions are probably some of the nicest ones and we all like working here and feel that we are fairly treated….you feel almost guilty that you’ve got a nicer deal” Hub team members

There were indicators of increased intention to quit and in some instances some members had left. These issues were significantly enhanced by the lack of certainty around funding and length of contracts – some project team members felt they had no option but to seek alternative employment because they did not know if their role would be available in three months but they needed the financial security.

“I think people, whether they want to stay or not, have to, you’ve got to put your own livelihood first” Hub team member

Furthermore the intention to quit was raised across several DANCOP members which meant that there was competition for other roles being advertised which had led to a difficult atmosphere.

“… the other thing is that everyone is applying for the similar jobs, there’s like a lot of jobs coming up and you know that there’ll be more than one person in the organisation going for it, because everyone is in the same boat.” Hub team member

Hub teams worked in different institutes and these different institutes each had their own organisational cultures and processes. One hub team noted that working with the host HEI legal and finance teams was exceptionally difficult and frustrating and that the finance processes in their own HEI were significantly more fit for purpose.

“I think we are quite lucky... I always say we’re very lucky to work for this institution I think in comparison we’ve got really positive things, but I think there is a difference between all of the hubs with like the TOIL, and the different perks and things that you get, which sometimes when it works your way, you just kind of keep your head under the radar.”  Hub team member

### Collaboration

In terms of Booth's (2007) four approaches to collaborative working, elements of several of the four approaches can be seen. Firstly there is evidence that there is some Co-opetition as institutionalised autonomy is maintained within the structure but there is a shared plan which allows the institutes to meet both their own and shared objectives. Accordingly, they are able to deliver more and higher quality outputs by using the pooled resources and knowledge. However as with Booth's 'sharing platform' approach, DANCOP has partners working closely together, and with SG members in common, to share vital components but also deliver different messages to distinctive sections of the community. For example, the college’s in-reach and outreach has a different message to those sent out by HEI's.

Collaborative working theoretically provides a number of benefits to the partners (Wiggans, 2012). Some of her hypothesised benefits have emerged within DANCOP. There is, within the IPG, an independent space out with institutions for individuals to moot ideas, discuss and evaluate them which is freer from the constraints of their home institutes and permits sharing of ideas, knowledge and to some extent resources to work innovatively. It also provides a pipeline for intelligence from FEI’s and allows them to have some influence. DANCOP had the benefit of having capacity to use third party providers which allowed for provision which is more closely aligned with the individual needs of schools. For example, in some schools within DANCOP the learners were fulfilling their potential but lacked awareness and knowledge of university as a next step. In other schools the main issue was that there were learners with potential but their behaviour and backgrounds acted as a barrier. These different needs required different interventions; the former could be met by a university WA team or through IntoUniversity, but the latter required something more specialised that an in house team was unlikely to be capable of. In the present case this need had been meet by a third party provider called Think For The Future.

# 2. DANCOP’s progress against Targets

DANCOP’s milestones/targets at the outset were:

- Evidence engagement in all wards by the end of the academic year 2017/18.

- Engage with 3000 learners from target cohorts in the first academic year of the programme and 7000 in the second.

- Engage with 80% of the highest priority schools in phase 1

- Engage with 50% of the medium priority schools in phase 1

- Engage with 25% of the medium priority schools in phase 1

In the first year (2016/2017) DANCOP worked with 241 unique learners. In the second year (2017/2018) they worked with 6344 unique learners. They have now worked with 14363 different learners (from a possible 27710) which represents more than half of DANCOP learners (52%). Table 10 displays the wards within the DANCOP area, the number of DANCOP learners in each ward and the number/percentage of learners who have been reached in each ward. The wards showing the best engagement are Shirebrook North West (100%), Scarcliffe (90%), Shirebrook Langwith (82%), Boughton 77%) and Sutton in Ashfield North (75%). The lowest engagement was with Balderton West (11%), Awsworth (17%), Holmewood & Heath (18%) and Killisick (23%). Thirty five of the 63 wards have had 50% or more of their DANCOP learners engaged.

Table 10 Wards and learners reached by DANCOP to August 2019

| DANCOP Wards | Number of Learners in Ward | Number of Unique Learners DANCOP Have Worked With | Percentage of Ward Engagement |
| --- | --- | --- | --- |
| Alfreton | 415 | 250 | 60% |
| Alvaston | 785 | 385 | 49% |
| Aspley | 1450 | 640 | 44% |
| Awsworth | 115 | 20 | 17% |
| Balderton West | 245 | 28 | 11% |
| Basford | 900 | 330 | 37% |
| Bestwood | 970 | 499 | 51% |
| Bilborough | 1115 | 648 | 58% |
| Birklands | 330 | 227 | 69% |
| Blidworth | 275 | 140 | 51% |
| Bolsover North West | 200 | 117 | 59% |
| Bolsover South | 230 | 126 | 55% |
| Bolsover West | 180 | 113 | 63% |
| Boughton | 280 | 215 | 77% |
| Boulton | 840 | 327 | 39% |
| Bridge | 480 | 202 | 42% |
| Bridge | 300 | 93 | 31% |
| Bulwell | 990 | 326 | 33% |
| Chaddesden | 800 | 511 | 64% |
| Church Gresley | 390 | 196 | 50% |
| Clifton South | 735 | 371 | 50% |
| Cotmanhay | 250 | 116 | 46% |
| Derwent | 870 | 613 | 70% |
| Devon | 335 | 114 | 34% |
| Eakring | 345 | 155 | 45% |
| Eastwood South | 425 | 248 | 58% |
| Elmton-with-Creswell | 320 | 157 | 49% |
| Heanor and Loscoe | 295 | 184 | 62% |
| Holmewood and Heath | 180 | 32 | 18% |
| Hucknall East | 440 | 225 | 51% |
| Hucknall West | 610 | 318 | 52% |
| Ilkeston Central | 200 | 103 | 52% |
| Ilkeston North | 245 | 148 | 60% |
| Ironville and Riddings | 280 | 102 | 36% |
| Killisick | 205 | 47 | 23% |
| Kirk Hallam | 360 | 120 | 33% |
| Kirkby in Ashfield West | 470 | 269 | 57% |
| Langley Mill and Aldercar | 315 | 189 | 60% |
| Limestone Peak | 115 | 56 | 49% |
| Lowgates and Woodthorpe | 280 | 136 | 49% |
| Mackworth | 630 | 341 | 54% |
| Meden | 385 | 275 | 71% |
| Middlecroft and Poolsbrook | 340 | 169 | 50% |
| Newhall and Stanton | 435 | 173 | 40% |
| Nottingham Road | 275 | 105 | 38% |
| Old Park | 200 | 121 | 61% |
| Ollerton | 385 | 258 | 67% |
| Pinxton | 260 | 115 | 44% |
| Sandiacre North | 300 | 137 | 46% |
| Scarcliffe | 200 | 179 | 90% |
| Shirebrook Langwith | 125 | 103 | 82% |
| Shirebrook North West | 155 | 158 | 100% |
| Shirebrook South East | 115 | 80 | 70% |
| Sinfin | 1070 | 628 | 59% |
| Somercotes | 385 | 128 | 33% |
| St Ann's | 735 | 416 | 57% |
| Stapleford North | 220 | 104 | 47% |
| Stapleford South West | 320 | 133 | 42% |
| Stone Bench | 330 | 100 | 30% |
| Sutton in Ashfield Central | 690 | 487 | 71% |
| Sutton in Ashfield East | 745 | 537 | 72% |
| Sutton in Ashfield North | 565 | 422 | 75% |
| Valley | 280 | 98 | 35% |
| Total DANCOP Learner Population | 27710 | 14363 | 52% |

## The engagement of schools into the network/collaborative partnerships

### How many have engaged?

At data collection in March 2018, Quarrydale Academy had the highest percentage of DANCOP learners and was also the school from which most learners have engaged with DANCOP activities (377 learners). However the other schools which had high engagement with DANCOP (Park Vale Academy, Springwell, Trinity, Nottingham Emmanuel, Murray Park, Bulwell, Eckington and Oakwood) were not necessarily the schools with the highest percentage of DANCOP learners.

By April 2019, DANCOP had delivered a total of 6716 activities with 109 different schools and colleges (from a possible 130), which had resulted in 122,841 learner engagements, 5294 parental engagements and 5446 teacher engagements. In the 2018/2019 academic year DANCOP have so far worked with 14,041 unique DANCOP learners on progressive and sustained delivery.

By April 2019, DANCOP had engaged with a much wider range of schools and colleges (109 compared to 26 in March 2018), as displayed Table 11. All but 24 schools had more than 100 learner engagements and 41 schools and colleges showing over 1000 learner engagements each. Fifty schools/colleges had been able to engage parents in activities and 98 schools/colleges had teachers who had engaged (see Table 10). Tibshelf Community School recorded the largest number of parent engagements (420), followed by Landau Forte College (396). Derby College (291), Nottingham College (287) and Derby Manufacturing UTC (231) recorded the greatest number of teacher engagements. Please note that Table 11 does not include engagements captured through community events or from events which were attended by multiple schools/colleges such as work experience at Bombardier.

Table 11 Percentage of DANCOP learners in each school with number of activities delivered and number of engagements

| School/college | % DANCOP learners | Number of activities | Learner engagements | Parent engagements | Teacher engagements |
| --- | --- | --- | --- | --- | --- |
| Quarrydale Academy | 92.91% | 196 | 6343 | 0 | 93 |
| Nottingham University Samworth Academy | 89.31% | 140 | 2061 | 0 | 151 |
| Sutton Community Academy | 84.63% | 124 | 2494 | 37 | 133 |
| Meden School | 84.49% | 54 | 1490 | 0 | 87 |
| Ellis Guilford School | 83.94% | 94 | 1823 | 0 | 20 |
| Bluecoat Beechdale Academy | 83.47% | 96 | 1391 | 5 | 79 |
| Da Vinci Academy | 78.63% | 342 | 5765 | 152 | 197 |
| Merrill Academy | 77.09% | 112 | 1142 | 8 | 49 |
| The Bulwell Academy | 74.92% | 93 | 822 | 34 | 17 |
| The Bolsover School | 71.25% | 31 | 1623 | 22 | 76 |
| Shirebrook Academy | 63.74% | 193 | 5590 | 326 | 154 |
| Holgate Academy | 62.81% | 38 | 1425 | 12 | 39 |
| Lees Brook Community School | 61.33% | 66 | 1749 | 10 | 39 |
| Farnborough Academy | 60.50% | 74 | 1778 | 0 | 90 |
| Ormiston Ilkeston Enterprise Academy | 60.00% | 95 | 2084 | 24 | 87 |
| The Oakwood Academy | 59.76% | 70 | 839 | 0 | 11 |
| The Dukeries Academy | 57.68% | 84 | 2108 | 300 | 73 |
| Park Vale Academy | 57.00% | 34 | 774 | 0 | 9 |
| Swanwick Hall School | 56.41% | 17 | 476 | 83 | 19 |
| David Nieper Academy | 55.24% | 104 | 1494 | 27 | 58 |
| Tupton Hall School | 54.41% | 7 | 134 | 0 | 0 |
| Magnus Church of England Academy | 53.11% | 46 | 1056 | 10 | 90 |
| Hall Park Academy | 51.29% | 48 | 782 | 34 | 41 |
| The Nottingham Emmanuel School | 50.42% | 45 | 1049 | 0 | 36 |
| Nottingham Girls' Academy | 50.22% | 80 | 626 | 0 | 32 |
| Aldercar High School | 48.75% | 41 | 577 | 15 | 47 |
| Netherthorpe School | 46.91% | 74 | 1245 | 47 | 16 |
| City of Derby Academy | 46.28% | 75 | 1279 | 2 | 7 |
| Ashfield Comprehensive School | 44.32% | 283 | 5067 | 335 | 170 |
| Hucknall Sixth Form Centre | 44.16% | 13 | 987 | 0 | 15 |
| Murray Park Community School | 43.61% | 130 | 3156 | 43 | 54 |
| Kirk Hallam Community Academy | 42.69% | 45 | 1271 | 268 | 70 |
| The Bramcote School | 41.24% | 100 | 955 | 0 | 7 |
| William Allitt School | 39.35% | 16 | 567 | 26 | 13 |
| Saint Benedict, A Catholic Voluntary Academy | 38.04% | 132 | 2137 | 1 | 144 |
| The Trinity Catholic School A Voluntary Academy | 37.69% | 48 | 973 | 0 | 14 |
| Derby Manufacturing UTC | 37.00% | 426 | 1766 | 89 | 231 |
| Heritage High School | 36.49% | 20 | 1056 | 27 | 45 |
| Noel-Baker Academy | 36.24% | 157 | 2702 | 59 | 43 |
| The Newark Academy | 36.24% | 4 | 82 | 20 | 7 |
| Nottingham College | 33.98% | 249 | 2829 | 31 | 287 |
| Landau Forte College | 33.95% | 82 | 1326 | 396 | 98 |
| The Pingle Academy | 33.83% | 95 | 3175 | 109 | 90 |
| The National CofE Academy | 33.75% | 2 | 126 | 0 | 3 |
| West Nottinghamshire College | 33.56% | 630 | 7751 | 109 | 213 |
| Derby College | 32.94% | 305 | 4014 | 142 | 291 |
| Frederick Gent School | 31.28% | 23 | 814 | 105 | 32 |
| Royal School for the Deaf Derby | 29.63% | 2 | 9 | 2 | 5 |
| Heanor Gate Science College | 29.44% | 65 | 1321 | 0 | 24 |
| George Spencer Academy and Technology College | 29.24% | 42 | 444 | 77 | 17 |
| The Kimberley School | 28.99% | 14 | 77 | 0 | 1 |
| Buxton & Leek College | 28.54% | 6 | 70 | 0 | 0 |
| Buxton Community School | 28.54% | 144 | 1360 | 55 | 72 |
| Wilsthorpe Community School | 28.32% | 24 | 412 | 0 | 11 |
| Christ The King Voluntary Academy | 27.88% | 5 | 27 | 0 | 0 |
| West Park School | 27.27% | 40 | 622 | 0 | 9 |
| Friesland School | 27.24% | 15 | 418 | 0 | 10 |
| Samworth Church Academy | 26.83% | 13 | 772 | 213 | 32 |
| Springwell Community College | 26.69% | 85 | 1706 | 96 | 120 |
| The Joseph Whitaker School | 26.48% | 120 | 851 | 68 | 32 |
| Bilborough College | 26.38% | 20 | 674 | 0 | 14 |
| Nottingham University Academy of Science and Technology | 25.10% | 32 | 1005 | 0 | 25 |
| Djanogly City Academy | 24.03% | 12 | 45 | 0 | 0 |
| Carlton Academy | 23.00% | 24 | 462 | 0 | 10 |
| Nottingham Academy | 22.34% | 73 | 2270 | 205 | 17 |
| Bluecoat Aspley Academy | 21.96% | 68 | 606 | 0 | 53 |
| Chesterfield College | 21.73% | 77 | 1223 | 0 | 94 |
| The Becket School | 21.56% | 46 | 1704 | 95 | 79 |
| All Saints Catholic Voluntary Academy | 21.03% | 19 | 325 | 0 | 1 |
| Redhill Academy | 20.94% | 21 | 180 | 0 | 5 |
| Bluecoat Wollaton Academy | 18.90% | 1 | 16 | 0 | 1 |
| Stephenson College | 18.70% | 11 | 24 | 0 | 10 |
| St Thomas More Catholic School Buxton | 16.28% | 1 | 60 | 0 | 1 |
| Eckington School | 15.65% | 26 | 271 | 0 | 6 |
| East Leake Academy | 14.51% | 17 | 671 | 15 | 22 |
| Fernwood School | 14.14% | 2 | 45 | 0 | 2 |
| St Mary's Catholic High School, A Catholic Voluntary Academy | 13.00% | 6 | 69 | 0 | 0 |
| The Brunts Academy | 12.84% | 37 | 793 | 0 | 12 |
| Alderman White SChool | 12.20% | 17 | 124 | 0 | 1 |
| Allestree Woodlands | 11.61% | 13 | 180 | 9 | 5 |
| The Bemrose School | 11.32% | 7 | 156 | 0 | 9 |
| Kirkby College | 10.54% | 7 | 102 | 0 | 5 |
| Tibshelf Community School | 10.52% | 7 | 588 | 420 | 11 |
| Tuxford Academy | 9.00% | 15 | 1156 | 42 | 23 |
| Arnold Hill Academy | 8.16% | 27 | 1107 | 3 | 28 |
| Selston High School | 7.70% | 8 | 742 | 150 | 49 |
| Nottingham Free School | 7.07% | 4 | 17 | 0 | 0 |
| Derby Moor Academy | 6.80% | 8 | 64 | 0 | 2 |
| Chapel-en-le-Frith High School | 6.12% | 6 | 34 | 10 | 3 |
| The Long Eaton School | 5.13% | 15 | 111 | 6 | 8 |
| The Manor Academy | 4.90% | 7 | 288 | 0 | 16 |
| Granville Academy | 4.86% | 5 | 179 | 60 | 3 |
| Rushcliffe School | 4.63% | 9 | 209 | 0 | 10 |
| Carlton Le Willows Academy | 4.52% | 7 | 294 | 50 | 3 |
| Garibaldi College | 3.76% | 11 | 161 | 0 | 10 |
| Chilwell School | 3.55% | 4 | 6 | 0 | 0 |
| The South Wolds Academy & Sixth Form | 3.51% | 7 | 0 | 0 | 7 |
| The Ripley Academy | 3.26% | 3 | 50 | 0 | 2 |
| Chellaston Academy | 2.74% | 12 | 98 | 0 | 7 |
| Hope Valley College | 2.20% | 1 | 3 | 0 | 0 |
| Toot Hill School | 1.95% | 1 | 13 | 13 | 5 |
| Minster School | 1.54% | 8 | 0 | 0 | 8 |
| Whittington Green School | 1.08% | 5 | 20 | 0 | 0 |
| Outwood Academy Newbold | 0.81% | 4 | 100 | 4 | 3 |
| Littleover Community School | 0.73% | 8 | 376 | 0 | 1 |
| Queen Elizabeth Academy | 0.68% | 3 | 228 | 0 | 6 |
| Retford Oaks Academy | 0.41% | 3 | 5 | 0 | 0 |
| Anthony Gell School | 0.15% | 5 | 43 | 0 | 9 |

DANCOP aimed to work with:

- 80% of high priority schools (a group of 26 schools and colleges whose learners are comprised from 50% or more DANCOP learners)

- 50% of medium priority schools (a group of 44 schools and colleges whose learners are comprised from 20-49% of DANCOP learners)

- 25% of low priority schools (a group of 16 schools and colleges whose learners are comprised of 10-19% DANCOP learners)

In addition there are a group of lowest priority schools and colleges who have less than 10% DANCOP learners against which no targets were set. Table 12 shows the proportion of these each of these groups of schools/colleges which engaged with DANCOP, the proportion who engaged in DANCOP activity with parents and the proportion who engaged in DANCOP activity with teachers against the target range. As Table 12 shows DANCOP surpassed all their targets here working with 100% of schools in each group.

Table 12 Percentages of schools engaged with mapped against priority status

|  | Proportion engaging in DANCOP activity with learners | Proportion engaging in DANCOP activity with parents | Proportion engaging in DANCOP activity with teachers (CPD and teacher engagement with activities delivered to learners) | Target range |
| --- | --- | --- | --- | --- |
| High priority band (26 schools/colleges) | 100% | 62% | 100% | 80% |
| Medium priority band (44 schools/colleges) | 100% | 59% | 95% | 50% |
| Low priority band (16 schools/colleges) | 100% | 38% | 88% | 25% |
| Lowest priority band (44 schools/colleges) | 48% | 14% | 39% | N/A |

## Activities delivered

This section details the activities delivered, by whom and to which learners up to the end of the academic year in 2018. First we look at the different kinds of activities delivered as classified by DANCOP (see Table 12). The most commonly delivered activity type was mentoring with 2272 different sessions (out of 6716) delivered. Mentoring activities include a range of different sub activities which include behavioural mentoring, 1 to 1 mentoring, The Scholars Programme, 1 to 1 tuition, mock interviews, education mentoring, career interviews, Brightside online mentoring, HE exploration, Maths tutoring and some activities (those delivered by Causeway Education) also included parental contact.

Information, advice and guidance sessions were the next most commonly delivered activity (2205). This category of activity includes UCAS support, study skills, critical thinking development, revision support, interviews, the learn to work Higher and Degree Apprenticeshipsprogramme, resilience programmes, Unifrog sessions, networking, work experience guidance, NCS Why Go? workshops, one to one guidance interviews, transferable skill development, conferences for young professionals and apprentices, CV workshops, exam preparation, finance talks and The Access project.

Master classes were delivered 1564 times. This category of activity included workshops by The Brilliant Club, literacy interventions, CV workshops, revision sessions and tutorials on all aspects of the curriculum, mental health sessions maths interventions delivered 1 to 1 and in groups, resilience and confidence classes, STEM ambassador sessions, English in media interventions, critical thinking sessions, Fable robots sessions, qualifications and progression pathways, Lego mindstorm robots, PET-XI training, Into University sessions, GCSE interventions, Science in the real world and the STEM bus.

Nearly 300 teacher CPD sessions were delivered. This category of activities included sessions and downloadable resources on advancing teachers understanding of access (for example post – 16 study options, how to apply to university, how to write effective personal statements, how universities use contextual information, using league tables, working with learners, helping learners to choose universities and courses, academic reference writing, admissions tests).

There were 117 parent/carer engagements which took place at parents and options evenings across a number of schools, parental contact in mentoring programmes, parent talks for 6th form learners and sessions on supporting studying at home.

The remaining activities included:

- campus visits (to both colleges and a range of universities including Oxbridge and Russell group and via the Grow the Rose programme)

- light touch sessions (typically delivered in assemblies on subjects such as opportunities and options)

- residentials (a widening access summer school, a Navy residential and the World Challenge trip to Morrocco)

- workshops by NCS (NCFITC budgeting and finance, lotus developing confidence and mindfulness, participation and self-esteem)

- community engagement (volunteering in care homes, work experience at Bombardier, trip to Yorkshire Sculpture Park, Premier League Enterprise Challenge, Roma Community Care Education System session).

There was a significant increase in the number of teams delivering activities from the interim evaluation where only 5 different teams had been involved (listed in decreasing numbers of learners engagements):

- IntoUniversity

- Central team/widening access

- WNC outreach

- Derby hub

- Mansfield hub

By the end of the 2018/2019 academic year data collection over 80 teams or different partnerships of teams had worked together to deliver activities. Table 13 shows activities broken down by delivery type and the percentage of the total number of deliveries they had. Table 14 lists each delivery team and combination of teams who worked together to deliver events, alongside the number of deliveries each made. Table 15 shows the teams which had the greatest number of deliveries.

Table 13 Activity types

| Activity type | Number of deliveries | Percent |
| --- | --- | --- |
| Campus visit | 218 | 2.45% |
| Community engagement | 25 | 0.28% |
| Information, advice and guidance | 2843 | 31.90% |
| Light-touch | 83 | 0.93% |
| Master class | 2289 | 25.69% |
| Mentoring | 2914 | 32.70% |
| Parent/carer engagement | 181 | 2.03% |
| Residentials | 56 | 0.63% |
| Teacher CPD | 302 | 3.39% |
| Grand Total | 8911 | 100.00% |
| Campus visit | 218 | 2.45% |

Table 14 Delivery teams/partnerships and the number of activities they delivered

| Delivery Team/organisation | Number of deliveries | Percent |
| --- | --- | --- |
| - Advancing Access | 75 | 1.1 |
| - Advancing Access & Central Team | 2 | .0 |
| - Brightside | 98 | 1.5 |
| - Brightside & Derby College In-reach | 2 | .0 |
| - Brilliant Club | 32 | .5 |
| - Careerstorch | 62 | .9 |
| - Causeway Education | 219 | 3.3 |
| - Central Higher and Degree Apprenticeships | 4 | .1 |
| - Central Higher and Degree Apprenticeships& Mansfield Hub | 2 | .0 |
| - Central Higher and Degree Apprenticeships, Derby Hub, Mansfield Hub & Central Team | 1 | .0 |
| - Central Higher and Degree Apprenticeships, Mansfield Hub & Chesterfield College | 1 | .0 |
| - Central Higher and Degree Apprenticeships, Mansfield Hub & Derby Hub | 1 | .0 |
| - Central Team | 41 | .6 |
| - Central Team - STEM bus | 35 | .5 |
| - Central Team & Derby Hub | 1 | .0 |
| - Central Team & IntoUniversity | 1 | .0 |
| - Central Team & Nottingham Hub | 1 | .0 |
| - Central Team & Widening Access | 7 | .1 |
| - Central Team, Nottingham College & Learn By Design | 1 | .0 |
| - Central Team, Nottingham College STEM Centre, Strategy, Derby Hub & Creative Hub | 1 | .0 |
| - Central Team, West Nottinghamshire College Outreach, Nottingham College STEM Centre & Chesterfield College | 1 | .0 |
| - Chesterfield College In-reach | 50 | .7 |
| - Chesterfield College Outreach | 20 | .3 |
| - Creative Hub | 3 | .0 |
| - Derby College FE Study Support Coaches | 56 | .8 |
| - Derby College FE Study Support Coaches, Nottingham College & Nottingham College STEM Centre | 1 | .0 |
| - Derby College In-reach | 81 | 1.2 |
| - Derby College Outreach | 6 | .1 |
| - Derby Hub | 195 | 2.9 |
| - Derby Hub & Central Higher and Degree Apprenticeships | 1 | .0 |
| - Derby Hub & Central Team | 1 | .0 |
| - Derby Hub & Derby College In-reach | 1 | .0 |
| - Derby Hub SSO | 163 | 2.4 |
| - Derby Hub SSO & University of Derby Widening Access | 1 | .0 |
| - Derby Hub, Derby Hub School Support Officer, University of Derby Widening Access & Central Team | 1 | .0 |
| - Derby Hub, Strategy & Mansfield Hub | 2 | .0 |
| - Grow the Rose | 4 | .1 |
| - Grow the Rose & Derby Hub | 1 | .0 |
| - Ideas4Careers | 62 | .9 |
| - IntoUniversity | 147 | 2.2 |
| - Learn by Design | 39 | .6 |
| - Mansfield Hub | 148 | 2.2 |
| - Mansfield Hub & Central team | 12 | .01 |
| - Mansfield Hub & Derby hub | 1 | .0 |
| - Mansfield Hub & West Nottinghamshire College Outreach | 2 | .0 |
| - Mansfield Hub School Support Officer | 83 | 1.2 |
| - Mansfield Hub, Derby Hub & Nottingham Hub | 1 | .0 |
| - Mansfield Hub, Nottingham Hub & Central team | 1 | .0 |
| - Mansfield Hub, Nottingham Hub, Derby Hub & Central team | 3 | .0 |
| - Mansfield Hub, West Nottinghamshire College In-Reach, West Nottinghamshire College Outreach, Derby College In-reach, Advancing Access & Nottingham College | 1 | .0 |
| - Mansfield Hub, West Nottinghamshire College Outreach & Central Team | 1 | .0 |
| - Nottingham College | 102 | 1.5 |
| - Nottingham College & Nottingham College STEM Centre | 10 | .1 |
| - Nottingham College STEM Centre | 20 | .3 |
| - Nottingham Hub | 69 | 1.0 |
| - Nottingham Hub & Central Higher and Degree Apprenticeships | 1 | .0 |
| - Nottingham Hub School Support Officer | 38 | .6 |
| - Nottingham Hub School Support Officer & Stretch Development | 3 | .0 |
| - Nottingham Trent University | 21 | .3 |
| - Performance In Education | 9 | .1 |
| - Real Clear & Edward Maxwell Ltd | 40 | .6 |
| - Siddiqui Education | 15 | .2 |
| - Stephenson College | 3 | .0 |
| - Stretch Development | 8 | .1 |
| - Stretch Development & West Nottinghamshire College In-reach | 3 | .0 |
| - Talk The Talk | 21 | .3 |
| - The Access Project | 202 | 3.0 |
| - The Brilliant Club | 58 | .9 |
| - Think for the Future | 194 | 2.9 |
| - Thinking Space | 11 | .2 |
| - Unifrog | 8 | .1 |
| - West Nottinghamshire College In-Reach | 89 | 1.3 |
| - West Nottinghamshire College Outreach | 123 | 1.8 |
| - West Nottinghamshire College Outreach & Chesterfield College Outreach | 1 | .0 |
| - West Nottinghamshire College study skills coaches | 108 | 1.6 |
| - University of Derby Widening Access | 63 | .9 |
| - University of Derby Widening Access & Derby Hub | 2 | .0 |
| - University of Derby Widening Access & Mansfield Hub | 2 | .0 |
| - Yipiyap | 109 | 1.6 |
| Total | 6718 | 100.0 |

Table 15 delivery teams

| Delivery team | No of deliveries |
| --- | --- |
| Derby Hub/Derby Hub School Support Officer | 358 |
| Mansfield Hub/Mansfield Hub School Support Officer | 231 |
| Causeway Education | 219 |
| The Access Project | 202 |
| Think for the Future | 194 |
| IntoUniversity | 147 |
| West Nottinghamshire College Outreach | 123 |
| Yipiyap | 109 |
| West Nottinghamshire College study skills coaches | 108 |
| Nottingham Hub/Nottingham Hub School Support Officer | 107 |
| Nottingham College | 102 |
| Brightside | 98 |
| West Nottinghamshire College In-Reach | 89 |
| Derby College In-reach | 81 |
| Advancing Access | 75 |
| University of Derby Widening Access | 63 |
| Careerstorch | 62 |
| Ideas4Careers | 62 |
| The Brilliant Club | 58 |
| Derby College FE Study Support Coaches | 56 |

# 3. Impact of DANCOP on learners

This section of the findings considers data from a range of different sources collected using a number of different methods as shown in Table 16. The findings are presented thus:

- Learner pre/post activity surveys which indicate possible changes in knowledge, intentions and attitudes in the short term

- Case study of Think for the Future mentoring

- DANCOP and non DANCOP learners surveys which indicate longer term changes in knowledge, intentions and attitudes and include comparison against a ‘control’ group

- Parental feedback from surveys

- Teachers surveys

- Staff in DANCOP funded roles

- Summary of impact from different participants

- Conclusion – what does the data tell us in regard to the objectives of the evaluation?

Table 16 Assessing impact: participants and methods

|  | Method | Assessing | When |
| --- | --- | --- | --- |
| Learners undertaking DANCOP funded activities | Survey | Knowledge/attitude change in the short term | Pre and post activity |
| DANCOP and non DANCOP learners | Survey | Knowledge of HE and aspiration change in the medium term | Early during DANCOP and May 2019 |
| Teachers completing surveys | Survey | Perceptions of activities Perceptions of learners behaviour change in the medium term | March – May 2019 |
| Staff in DANCOP funded roles taking part in focus groups | Focus Group | Perceptions of activities Perceptions of learners behaviour change in the medium term | March –May 2019 |

## A. Learner feedback on activities

Learners were asked to complete feedback surveys provided by DANCOP when they took part in an activity (at the start of phase 1 of DANCOP all participants for every activity completed them but this was reduced part way through phase 1 to include only specific activities); these surveys have one part that is completed before the activity and one that is completed after. There are some feedback questions which are standardised but providers are also able to add further questions specific to elements of their own activities. The following analyses consider primarily the standardised questions.

The DANCOP feedback sheets ask learners to rate the overall activity. The number of learners who rated each activity as either poor, fair, good or excellent is shown below in Table 17 (this table excludes small number of activities which had very low participation rates). Typically learners rated activities as 'excellent' or ‘good’, with far fewer rating events as 'fair' and only one as 'poor'.  Twelve activities were rated as excellent by 50% or more of respondents: Brightside online mentoring, IntoUniversity revision and studying mentoring, Ideas4Careers, IntoUniversity Future pathways mentoring, the Forensic Anthropology PS, UCAS parent & learner talk, the HE experience day, the Health and Social Care days, Boys into HE, the IntoUniversity family day and the Oxbridge Programme. More than half of all different activities showed them being as rated as ‘good’ by 50% or more of respondents. Fifty five of the different activities received ratings of ‘fair’ but this was always by less than 36% of respondents. Seventeen activities received a rating of ‘poor’ but never by more than 5.8% of respondents.

Table 17 Activity ratings and percentage of respondents (empty cells represent 0%)

|  | Number of participants | Excellent | Good | Fair | Poor | No response |
| --- | --- | --- | --- | --- | --- | --- |
| Boys into HE | 18 | 50.0% | 11.1% |  |  | 38.9% |
| Brightside on line mentoring training | 14 | 85.7% | 14.3% |  |  |  |
| Building Confidence | 22 | 22.7% | 54.5% | 22.7% |  |  |
| Buxton Away day | 449 | 14.7% | 59.9% | 19.6% | 2.2% | 3.6% |
| Construct Your Future Follow up | 21 | 19.0% | 66.7% | 9.5% |  | 4.8% |
| Criminal justice taster day | 35 | 37.1% | 42.9% | 11.4% | 5.7% | 2.9% |
| David Hodgson Talk | 20 | 25.0% | 55.0% | 15.0% |  | 5.0% |
| Derby Book Festival Emma Jane Kirby talk | 44 | 38.6% | 50.0% | 9.1% |  | 2.3% |
| Discover University | 22 | 36.4% | 36.4% |  |  | 27.3% |
| Employability skills workshop | 21 | 9.5% | 81.0% | 9.5% |  |  |
| Employability workshop | 181 | 22.9% | 64.6% | 9.7% |  | 2.8% |
| Engineering revision session | 13 | 30.8% | 53.8% | 15.4% |  |  |
| Enterprise session | 93 | 5.4% | 66.7% | 20.4% | 3.2% | 4.3% |
| EPQ Reference writing | 20 | 15.0% | 65.0% | 20.0% |  |  |
| Finance and budgeting | 75 | 14.7% | 57.3% | 22.7% | 4.0% | 1.3% |
| Forensic Anthropology PS | 22 | 63.6% | 27.3% |  |  | 9.1% |
| Higher And Degree Apprenticeship and debating session | 14 | 14.3% | 78.6% | 7.1% |  |  |
| Higher And Degree Apprenticeship and unifrog | 66 | 25.8% | 56.1% | 15.2% | 1.5% | 1.5% |
| HE experience day | 18 | 61.1% | 33.3% | 5.6% |  |  |
| HE Higher and degree apprenticeships | 14 | 28.6% | 57.1% | 7.1% |  | 7.1% |
| HE session | 24 | 29.2% | 54.2% | 16.7% |  |  |
| Health and social care day | 50 | 52.6% | 47.4% |  |  |  |
| Ideas4Careers | 125 | 76.0% | 23.2% |  |  | 0.8% |
| Information day | 18 | 11.1% | 72.2% | 16.7% |  |  |
| Into University Future Pathways Mentoring | 12 | 66.7% | 33.3% |  |  |  |
| IntoUniversity Business in FOCUS | 156 | 44.9% | 41.0% | 10.3% | 3.8% |  |
| IntoUniversity education pathways | 116 | 43.1% | 48.3% | 1.7% |  | 6.9% |
| IntoUniversity employability skills | 106 | 30.2% | 66.0% |  |  | 3.8% |
| IntoUniversity FOCUS on choices | 222 | 36.0% | 55.0% | 7.2% |  | 1.8% |
| IntoUniversity FOCUS on future | 496 | 45.6% | 46.0% | 6.5% |  | 2.0% |
| IntoUniversity FOCUS on success | 464 | 43.1% | 38.4% | 5.6% |  | 12.9% |
| IntoUniversity Intro to UCAS and personal statements | 48 | 20.8% | 50.0% | 12.5% |  | 16.7% |
| IntoUniversity Post 16 Options | 40 | 30.0% | 60.0% | 5.0% |  | 5.0% |
| IntoUniversity Revision and studying mentoring | 14 | 85.7% | 14.3% |  |  |  |
| IntoUniversity Revision skills and techniques | 120 | 43.3% | 41.7% | 6.7% |  | 8.3% |
| IntoUniversity transferable skills | 110 | 20.0% | 58.2% | 10.9% | 1.8% | 9.1% |
| IntoUniversity University life | 84 | 40.5% | 33.3% |  |  | 26.2% |
| IntoUniversity Family day | 14 | 50.0% | 50.0% |  |  |  |
| Introduction to HE | 46 | 13.0% | 78.3% | 4.3% |  | 4.3% |
| Learning styles session | 13 | 7.7% | 84.6% | 7.7% |  |  |
| Making the most of the UCAS convention | 17 | 17.6% | 82.4% |  |  |  |
| NCFITC Budgeting | 130 | 7.7% | 63.8% | 23.8% | 1.5% | 3.1% |
| Oxbridge Programme | 8 | 50.0% | 50.0% |  |  |  |
| Parent's evening | 36 | 11.1% | 83.3% |  |  | 5.6% |
| Paris trip | 35 | 31.4% | 60.0% | 5.7% |  | 2.9% |
| Performance in education | 783 | 13.4% | 32.4% | 12.5% | 4.2% | 37.4% |
| Progression pathways | 200 | 24.0% | 63.0% | 6.0% |  | 7.0% |
| Revision session | 187 | 16.0% | 56.7% | 24.1% | 1.6% | 1.6% |
| Revision skills | 457 | 14.0% | 64.3% | 16.6% | 2.4% | 2.6% |
| Revision support | 9 | 44.4% | 44.4% | 11.1% |  |  |
| Revision techniques | 70 | 35.7% | 54.3% | 4.3% |  | 5.7% |
| Revision workshop | 18 | 38.9% | 55.6% |  |  | 5.6% |
| Skills day subject taster | 81 | 8.6% | 58.0% | 22.2% | 2.5% | 8.6% |
| Learner finance | 270 | 39.3% | 50.0% | 5.6% | 1.5% | 3.7% |
| Learner finance talk | 119 | 0.8% | 59.7% | 36.1% | 2.5% | 0.8% |
| Study abroad | 21 | 47.6% | 42.9% | 9.5% |  |  |
| Study skills | 155 | 21.3% | 65.2% | 12.9% |  | 0.6% |
| Taster HE experience day for young people services | 11 | 45.5% | 54.5% |  |  |  |
| The Access Project Programme | 55 |  |  |  |  | 100.0% |
| Time Management and resilience workshop | 56 | 3.6% | 75.0% | 21.4% |  |  |
| Time management and setting goals | 12 | 25.0% | 50.0% | 25.0% |  |  |
| Transferable skills workshop | 259 | 18.5% | 57.9% | 17.0% | 2.7% | 3.9% |
| UCAS Parent + Learner Talk | 8 | 62.5% | 37.5% |  |  |  |
| UCAS session | 49 | 22.4% | 67.3% | 8.2% |  | 2.0% |
| Understanding the UCAS process | 34 | 47.1% | 47.1% | 5.9% |  |  |
| Unifrog | 64 | 20.3% | 57.8% | 18.8% |  | 3.1% |
| University experience day | 127 | 48.8% | 39.4% | 1.6% |  | 10.2% |
| Vision University Centre visit | 20 | 10.0% | 80.0% | 10.0% |  |  |
| What can I do with History GCSE Plus ND | 21 | 28.6% | 61.9% | 4.8% |  | 4.8% |
| What do graduates do? | 23 | 13.0% | 65.2% | 13.0% | 4.3% | 4.3% |
| Why go to university? | 145 | 20% | 66% | 11% | 1.4% | 8.9% |

## Short term Changes in learners knowledge, intentions and attitudes

These analyses are based on feedback sheets which DANCOP learners complete pre and post activity. They do not have a control group to serve as a comparison and caution must therefore be used in concluding that any changes seen in measures taken are a direct result of taking part in the activity. Nonetheless they represent perceptions of the learners with respect to what they believed they knew, thought and intended before and after. These analyses are presented as follows:

1. Summated feedback for all activities, learners and schools

2. Feedback on each provider (activity feedback is summated)

3. Feedback on specific activities (data from different classes or schools is summated)

### 1. Summated feedback for all activities

Average item responses from learners, regardless of provider or activity, for the before/after questions on the DANCOP feedback sheets is shown below in Table 18. Note that the scale was 1 through to 5 with 1 indicating strong disagreement and 5 indicating strong agreement. N is the number of learners who provided data for those items and SD is the standard deviation (this is a measure of how varied the responses were around the mean - a lower SD indicates that the responses were close to the mean).

Table 18 Mean responses to before/after questions from all learners and all activities and paired sample t-test results.

|  |  | Mean | N | SD | t | df | sig. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.53 | 6463 | 1.33 | -38.32 | 6462 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.94 | 6463 | 1.22 |  |  |  |
| 2 | I know where to get information about university BEFORE | 2.95 | 1855 | 1.19 | -36.571 | 1854 | .000 |
|  | I know where to get information about university AFTER | 3.93 | 1855 | 1.03 |  |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.30 | 5605 | 1.16 | -50.275 | 5604 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 3.96 | 5605 | 1.02 |  |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.65 | 4547 | 1.15 | -46.225 | 4546 | .000 |
|  | I know what a university / higher education is AFTER | 4.31 | 4547 | .87 |  |  |  |
| 5 | I feel motivated to work hard in school/college BEFORE | 3.62 | 258 | .90 | -12.526 | 257 | .000 |
|  | I feel motivated to work hard in school/college AFTER | 4.20 | 258 | .81 |  |  |  |
| 6 | I can go into higher education when I leave school if I want to BEFORE | 3.73 | 399 | 1.02 | -13.278 | 398 | .000 |
|  | I can go into higher education when I leave school if I want to AFTER | 4.28 | 399 | .82 |  |  |  |
| 7 | I have a good level of knowledge about university BEFORE | 2.81 | 239 | .93 | -20.202 | 412 | .000 |
|  | I have a good level of knowledge about university AFTER | 4.15 | 239 | .76 |  |  |  |
| 8 | Each university offers different courses BEFORE | 3.88 | 251 | .95 | -13.076 | 250 | .000 |
|  | Each university offers different courses AFTER | 4.66 | 251 | .67 |  |  |  |
| 9 | I am confident that I would fit in at university BEFORE | 2.90 | 62 | 1.19 | -6.785 | 61 | .000 |
|  | I am confident that I would fit in at university AFTER | 3.55 | 62 | 1.14 |  |  |  |
| 10 | I know enough about higher education to make a decision about whether or not to go at this stage BEFORE | 3.23 | 413 | 1.04 | -20.202 | 412 | .000 |
|  | I know enough about higher education to make a decision about whether or not to go at this stage AFTER | 4.15 | 413 | .88 |  |  |  |
| 11 | I feel confident about revising BEFORE | 3.27 | 155 | 1.10 | -7.892 | .154 | .000 |
|  | I feel confident about revising AFTER | 3.79 | 155 | 1.03 |  |  |  |
| 12 | I know some techniques to help me revise/remember BEFORE | 3.35 | 155 | 1.07 | -9.334 | 154 | .000 |
|  | I know some techniques to help me revise/remember AFTER | 3.99 | 155 | .96 |  |  |  |
| 13 | I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college BEFORE | 4.31 | 109 | 1.06 | -2.383 | 108 | .019 |
|  | I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college AFTER | 4.44 | 109 | .96 |  |  |  |

For each before/after question there was a statistically significant increase (confirmed through paired sample t-tests) in mean rating from before to after, as shown in Table 18 (where the significance value is less than .05 the test has returned a statistically significant result, indicating a change). This suggests that after taking part in DANCOP activities participants indicated significant increases on/in:

- thinking about applying to university in the future

- knowing where to get information about university

- knowing enough about future options to help make decisions about what to do after school/college

- knowing what a university / higher education is

- feeling motivated to work hard in school/college

- feeling able to go into higher education after school

- having a good level of knowledge about university

- knowing each university offers different courses

- feeling confident about fitting in at university

- knowing enough about higher education to make a decision about whether or not to go at this stage

- feeling confident about revising

- knowing some techniques to help with revision

- having a preference for going to HE over going straight into work after school or college

### 2. Feedback on providers

These analyses summate responses across activities and schools/colleges to look at shifts on before/after questions by provider. Provider’s feedback sheets were tailored such that they asked questions relevant to the specific activity or activities being run. Thus not all questions can be compared for all providers. Additionally, where participant numbers are low (for example less than 30), inferential tests have not been run, the following providers were tested:

- Central team/University of Derby Widening Access

- Derby Hub

- Mansfield Hub

- Nottingham Hub

- University of Derby Widening Access

- Derby College

- West Nottinghamshire College

- IntoUniversity

- Performance in Education

- The Access project

#### Central team/University of Derby Widening access

Learners who took activities run by the Central/Widening Access team reported a significant increase in their intention to apply to university, knowledge concerning their options, knowledge of university and confidence in fitting in (see Table 19 for mean ratings before and after and the results of the paired sample t-tests).

Table 19 Mean responses and paired sample t-tests on before/after questions for Central/Widening access activities

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.29 | 49 | 1.33 | -5.48 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.92 | 49 | 1.03 |  |  |
| 2 | I know where to get information about university BEFORE | 2.75 | 16 | 1.23 | -3.78 | .002 |
|  | I know where to get information about university AFTER | 4.13 | 16 | .95 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.10 | 49 | 1.17 | -4.63 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 3.57 | 49 | 1.00 |  |  |
| 4 | I know what a university / higher education is BEFORE | 2.94 | 33 | 1.19 | -8.58 | .000 |
|  | I know what a university / higher education is AFTER | 4.33 | 33 | .59 |  |  |

##### Derby Hub

As with the other providers there is an increase in mean responses from before to after the activity. These increases in intention to apply to HE, knowing enough about options to make decisions and knowing about university were all statistically significant (see Table 20). The increase in knowing where to get information was not statistically significant, however increases in feeling confident about revising and knowing some revision techniques were both statistically significant.

Table 20 Mean responses to before/after questions for Derby hub activities

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.31 | 609 | 1.35 | -10.52 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.66 | 609 | 1.29 |  |  |
| 2 | I know where to get information about university BEFORE | 3.88 | 34 | .94 | -2.02 | .051 |
|  | I know where to get information about university AFTER | 4.26 | 34 | .82 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.26 | 604 | 1.18 | -14.60 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 3.79 | 604 | 1.09 |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.63 | 570 | 1.10 | -15.25 | .000 |
|  | I know what a university / higher education is AFTER | 4.20 | 570 | .88 |  |  |
| 5 | I feel confident about revising BEFORE | 3.27 | 154 | 1.11 | -7.90 | .000 |
|  | I feel confident about revising AFTER | 3.80 | 154 | 1.03 |  |  |
| 6 | I know some techniques to help me revise/remember BEFORE | 3.35 | 154 | 1.08 | -9.35 | .000 |
|  | I know some techniques to help me revise/remember AFTER | 3.99 | 154 | .96 |  |  |

#### Mansfield Hub

As with the other providers there is an increase in mean responses from before to after the activities run by Mansfield Hub. These increases in intention to apply, knowing enough about options to make decisions, knowing about university, the nature of the education and courses were all statistically significant (see Table 21).

Table 21 Mean responses to before/after questions for Mansfield Hub activities

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.35 | 1408 | 1.41 | -15.19 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.66 | 1408 | 1.34 |  |  |
| 2 | I know where to get information about university BEFORE | 2.98 | 822 | 1.20 | 8.42 | .000 |
|  | I know where to get information about university AFTER | 3.63 | 822 | 1.14 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.41 | 1402 | 1.19 | -19.59 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 3.84 | 1402 | 1.09 |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.94 | 585 | 1.11 | -11.66 | .000 |
|  | I know what a university / higher education is AFTER | 4.30 | 585 | .87 |  |  |
| 5 | Each university offers different courses BEFORE | 4.38 | 55 | .80 | -4.35 | .000 |
|  | Each university offers different courses AFTER | 4.75 | 55 | .48 |  |  |

#### Nottingham Hub

As with the other providers there is an increase in mean responses from before to after the activities run by Nottingham Hub. These increases in intention to apply, knowing enough about options to make decisions, knowing about university, the nature of the education and courses were all statistically significant (see Table 22).

Table 22 Mean responses to before/after questions for Nottingham Hub activities

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.63 | 224 | 1.26 | -9.53 | .000 |
|  | I am thinking about applying to university in the future AFTER | 4.29 | 224 | 1.02 |  |  |
| 2 | I know where to get information about university BEFORE | 2.56 | 117 | 1.01 | -15.97 | .000 |
|  | I know where to get information about university AFTER | 4.33 | 117 | .83 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.13 | 222 | 1.09 | -15.21 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 4.15 | 222 | .88 |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.40 | 224 | 1.07 | -15.50 | .000 |
|  | I know what a university / higher education is AFTER | 4.40 | 224 | .72 |  |  |

#### University of Derby Widening Access

The Widening Access team from the University of Derby delivered some activities without the central team and these are analysed separately below (see Table 23 for mean, N, SD and results of paired sample t-tests).

Table 23 Mean responses to before/after questions for UoD Widening Access activities

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.40 | 435 | 1.34 | -10.66 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.90 | 435 | 1.19 |  |  |
| 2 | I know where to get information about university BEFORE | 2.89 | 152 | 1.11 | -15.14 | .000 |
|  | I know where to get information about university AFTER | 4.14 | 152 | .78 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.21 | 411 | 1.12 | -17.85 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 4.02 | 411 | .94 |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.29 | 14 | 1.06 | -5.57 | .000 |
|  | I know what a university / higher education is AFTER | 4.50 | 14 | .65 |  |  |
| 5 | I feel motivated to work hard in school/college BEFORE | 3.66 | 232 | .90 | -11.50 | .000 |
|  | I feel motivated to work hard in school/college AFTER | 4.22 | 232 | .78 |  |  |
| 6 | I can go into higher education when I leave school if I want to BEFORE | 3.81 | 338 | .99 | -11.99 | .000 |
|  | I can go into higher education when I leave school if I want to AFTER | 4.31 | 338 | .80 |  |  |
| 7 | I have a good level of knowledge about university BEFORE | 2.79 | 214 | .87 | -20.83 | .000 |
|  | I have a good level of knowledge about university AFTER | 4.14 | 214 | .74 |  |  |
| 8 | I am confident that I would fit in at university BEFORE | 2.90 | 61 | 1.20 | -6.63 | .000 |
|  | I am confident that I would fit in at university AFTER | 3.54 | 61 | 1.14 |  |  |

#### Derby College

The activities delivered by Derby College resulted in significant increases for mean ratings of thinking about applying to university, knowing enough about options to make a decision and knowing what a university education is. Mean scores, SD and paired sample t-test results are shown in Table 24.

Table 24 Paired sample t-test results for Derby College deliveries

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.66 | 540 | 1.45 | -9.17 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.95 | 540 | 1.31 |  |  |
| 2 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.64 | 535 | 1.15 | -13.15 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 4.11 | 535 | .95 |  |  |
| 3 | I know what a university / higher education is BEFORE | 4.13 | 532 | 1.177 | 11.78 | .000 |
|  | I know what a university / higher education is AFTER | 4.59 | 532 | .737 |  |  |

#### West Nottinghamshire College

Mean before/after question responses are shown below in Table 25 along with the outcomes of the paired sample t-tests. The t-tests indicate that there were significant increases in mean ratings of thinking about going to university, knowing where to get information from, knowing enough about options to make a decision, knowing what a university education is and believing they can go to university if they want to. There was also statistically significant increase in feeling they would rather go to university after school/college than go straight into work although the statistical significance was less than for the other measures.

Table 25 Mean responses to before/after questions for WNC Outreach activities

|  |  | Mean | N | SD | t | P |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.23 | 563 | 1.411 | -12.17 | .000 |
|  | I am thinking about applying to university in the future AFTER | 3.72 | 563 | 1.264 |  |  |
| 2 | I know where to get information about university BEFORE | 2.40 | 58 | 1.169 | -10.39 | .000 |
|  | I know where to get information about university AFTER | 4.22 | 58 | .817 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.23 | 567 | 1.262 | -14.19 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 3.88 | 567 | 1.075 |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.44 | 510 | 1.266 | -15.16 | .000 |
|  | I know what a university / higher education is AFTER | 4.15 | 510 | .958 |  |  |
| 5 | I can go into higher education when I leave school if I want to BEFORE | 2.88 | 32 | .976 | -5.27 | .000 |
|  | I can go into higher education when I leave school if I want to AFTER | 3.97 | 32 | .999 |  |  |
| 6 | I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college BEFORE | 4.06 | 54 | 1.220 | -2.39 | .020 |
|  | I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college AFTER | 4.26 | 54 | 1.067 |  |  |

#### IntoUniversity

Learners reported significant increases in knowledge about university and courses, intention to apply to university, where to get information from and whether they knew enough to make a decision after taking the IntoUniversity workshops (see Table 26 for t-test results and mean ratings before and after).

Table 26 Mean responses and paired sample t-test results for before/after questions for IntoUniversity

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.75 | 1837 | 1.21 | -23.78 | .000 |
|  | I am thinking about applying to university in the future AFTER | 4.19 | 1837 | 1.05 |  |  |
| 2 | I know where to get information about university BEFORE | 2.94 | 571 | 1.18 | -25.28 | .000 |
|  | I know where to get information about university AFTER | 4.13 | 571 | .87 |  |  |
| 3 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.18 | 1074 | 1.05 | -30.28 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 4.08 | 1074 | .89 |  |  |
| 4 | I know what a university / higher education is BEFORE | 3.60 | 1348 | 1.12 | -29.78 | .000 |
|  | I know what a university / higher education is AFTER | 4.33 | 1348 | .83 |  |  |
| 5 | Each university offers different courses BEFORE | 3.74 | 196 | .95 | -12.71 | .000 |
|  | Each university offers different courses AFTER | 4.63 | 196 | .72 |  |  |
| 6 | I know enough about higher education to make a decision about whether or not to go at this stage BEFORE | 3.15 | 357 | 1.02 | -20.22 | .000 |
|  | I know enough about higher education to make a decision about whether or not to go at this stage AFTER | 4.13 | 357 | .86 |  |  |

#### Performance in Education

Mean before/after question responses are shown below in Table 27 along with the outcomes of the paired sample t-tests. The t-tests indicate that there were significant increases in mean ratings of thinking about going to university, knowing enough about options to make a decision and knowing what a university education is.

Table 27 Paired sample t-test results for Performance in education deliveries

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 3.61 | 718 | 1.15 | -12.28 | .000 |
|  | I am thinking about applying to university in the future AFTER | 4.08 | 718 | 1.08 |  |  |
| 2 | I know enough about my future options to help me make a decision about what to do after school/college BEFORE | 3.27 | 711 | 1.11 | -16.98 | .000 |
|  | I know enough about my future options to help me make a decision about what to do after school/college AFTER | 4.01 | 711 | 1.02 |  |  |
| 3 | I know what a university / higher education is BEFORE | 3.45 | 721 | 1.07 | -18.81 | .000 |
|  | I know what a university / higher education is AFTER | 4.26 | 721 | .99 |  |  |

#### The Access project

The mean ratings and results of the paired sample t-tests are shown below in Table 28. These reveal that mean ratings of knowing where to get information from and knowing enough about university at this stage increased significantly after the activity. However, thinking about applying and feeling they would rather go to university than straight into work did not increase.

Table 28 Paired sample t-test results for The Access Project deliveries

|  |  | Mean | N | SD | t | p |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | I am thinking about applying to university in the future BEFORE | 4.62 | 55 | .93 | -.596 | .553 |
|  | I am thinking about applying to university in the future AFTER | 4.67 | 55 | .88 |  |  |
| 2 | I know where to get information about university BEFORE | 3.70 | 53 | 1.15 | -3.69 | .001 |
|  | I know where to get information about university AFTER | 4.11 | 53 | 1.06 |  |  |
| 3 | I know enough about higher education to make a decision about whether or not to go at this stage BEFORE | 3.74 | 54 | 1.10 | -4.31 | .000 |
|  | I know enough about higher education to make a decision about whether or not to go at this stage AFTER | 4.26 | 54 | 1.08 |  |  |
| 4 | I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college BEFORE | 4.56 | 54 | .83 | -.83 | .410 |
|  | I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college AFTER | 4.61 | 54 | .83 |  |  |

### 3. Feedback on specific activities

These analyses examine the before and after responses for specific activities (which may have been run several times with learners from a number of different schools). There were over 70 different activities delivered but not all were attended by enough learners/learners for inferential statistical analyses to be meaningful. Therefore the following analyses concentrate on those activities which had been delivered to groups of 40 or more:

•	Buxton away day

•	DBF Emma Jane Kirby talk

•	Employability workshop

•	Enterprise session

•	Finance & budgeting

•	Higher and Degree Apprenticeships  & Unifrog

•	Ideas4Careers

•	Business in FOCUS

•	Education Pathways

•	Employability skills

•	FOCUS on choices

•	FOCUS on success

•	Introduction to UCAS and personal statements

•	FOCUS on future

•	Revision skills/techniques

•	Transferable skills

•	University Life

•	Introduction to HE

•	NCFITC Budgeting

•	Performance in education

•	Progression pathways

•	Revision session

•	Revision skills

•	Revision techniques

•	Skills day subject taster

•	Learner finance

•	Study skills

•	The Access Project

•	Transferable skills workshop

•	UCAS session

•	Unifrog

•	University experience day

•	Why go to university

An additional point is that not all measures were assessed for every activity, rather feedback was collected on those measures which were deemed relevant to the specific activity. Full descriptive data (mean ratings for before and after, standard deviations and standard error of the mean) and t-test results and precise significance levels for all possible comparisons are presented in the appendix. Here we present those activities and measures with N > 40 and indicate whether the difference in rating before and after the activity was statistically significant (as tested using a paired sample t-test). Table 28 lists all activities where the number of participants was greater than 39. The asterisks indicate there was a significant increase in mean rating from before to after completing the activity. NS indicates there was no significant increase. Where the cells are blank this indicates that the measure was either not taken or there were not enough responses to conduct inferential statistics.

Results indicate that where measures were recorded participants typically showed increased mean ratings post activity. Only four measures from two different activities returned non-significant results:

- The Derby Book Festival Emma Jane Kirby Talk:

  - Thinking about applying to university

  - Knowing where to get information about university

- The Access Project:

  - Thinking about applying to university

  - I would rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college

It is important to remember that without a control group for comparison we cannot conclude that these changes are directly due to the activities themselves, however it is fair to say that participants typically indicated they felt they had more knowledge as a result of taking part.

Table 29 Significant and non significant changes in measures after undertaking DANCOP activities

| Activity | Thinking about applying to university in the future | Know where to get information about university from |  | Know enough about future options to make a decision |  |  | Know what a university education is | Feel motivated to work hard |  |  | I can go into HE if I want to | Good level of knowledge about university |  |  | Each uni offers different courses |  | Confident that I would fit in |  | Know enough to decide now | Confident about revising |  | Know some revision techniques |  | Rather go to HE than straight into work |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Buxton away day | * | * |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DBF Emma Jane Kirby talk | NS | NS |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employability workshop | * |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enterprise session |  |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finance & budgeting | * |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Higher and Degree Apprenticeships& unifrog | * |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ideas4Careers | * | * |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity Business in FOCUS | * | * |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity Education Pathways | * |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity Employability skills | * |  |  |  |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity FOCUS on choices | * |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Thinking about applying to university in the future |  | Know where to get information about university from |  | Know enough about future options to make a decision | Know what a university education is |  |  | Feel motivated to work hard | I can go into HE if I want to |  |  | Good level of knowledge about university | Each uni offers different courses |  | Confident that I would fit in |  | Know enough to decide now |  | Confident about revising | Know some revision techniques |  | Rather go to HE than straight into work |  |
| IntoUniversity FOCUS on success | * |  | * |  | * | * |  |  |  |  |  |  |  | * |  |  |  | * |  |  |  |  |  |  |
| IntoUniversity Introduction to UCAS and personal statements | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity FOCUS on future | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  | * |  |  |  |  |  |  |  |  |
| IntoUniversity Revision skills/techniques | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity Transferable skills | * |  |  |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IntoUniversity University Life | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  | * |  |  |  |  |  |  |  |  |
| Introduction to HE | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NCFITC Budgeting | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Performance in education | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Progression pathways | * |  |  |  | * |  |  |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revision session | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  | * | * |  |  |  |
|  | Thinking about applying to university in the future |  | Know where to get information about university from |  | Know enough about future options to make a decision | Know what a university education is |  |  | Feel motivated to work hard | I can go into HE if I want to |  |  | Good level of knowledge about university | Each uni offers different courses |  | Confident that I would fit in |  | Know enough to decide now |  | Confident about revising | Know some revision techniques |  | Rather go to HE than straight into work |  |
| Revision skills | * |  | * |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revision techniques | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  | * |  |  |  |  |  |  |  |  |
| Skills day subject taster | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Learner finance | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Study skills | * |  | * |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Access Project | NS |  | * |  | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NS |  |
| Transferable skills workshop | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | * |  |
| UCAS session | * |  |  |  | * | * |  |  |  |  |  |  |  | * |  |  |  |  |  |  |  |  |  |  |
| Unifrog | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| University experience day | * |  | * |  | * |  |  |  |  | * |  |  | * |  |  |  |  |  |  |  |  |  |  |  |
| Why go to university | * |  |  |  | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

### Summary of Learner short term changes

Learners were typically positive and showed an increase in mean responses before and after the activities. In many cases the sample size was large enough for inferential statistics to be conducted and these indicated the increases were statistically significant. It is fair to conclude that in the short term, taking part in the DANCOP activities detailed above was related to learners feeling they had increased:

- Knowledge of future options to help them make a decision about what to do after school/college

- Thinking about going to university

- Knowledge of what a university education is

- Knowledge of where to get information about university

- Knowledge about university in general and their different courses

- Confidence in their ability to go to university

- Confidence in their ability to fit in at university

- Knowledge of revision techniques

- Confidence in ability to revise

Without control group comparisons however we cannot conclude that the activities are the direct cause of these changes nor that the changes will result in medium term changes in behaviour or longer term outcomes.

## B. Think for the Future case study

#### What?

The organisation

Think for the Future aims to "empower young people to thrive, rather than to simply survive". Ten thousand students are excluded from school every year which has a cost to the state and to schools - Think for the Future offer programmes to schools and communities to deal with students who have clear educational potential but don't fulfil it because of behavioural or pastoral problems.

The programme

The Think for the Future mentoring programme is aimed specifically at students who:

- Are at risk of being permanently excluded from school

- Have high levels of poor behaviour including classroom removals and isolation's

- Have low school attendance

- Have significant safeguarding incidents that are affecting educational potential

### Why?

The mentoring programme aims to develop the student’s emotional intelligence, their attitudes towards themselves and their work, behaviour, social conduct and aspirations. It is through development of these things that mentors hope to reduce challenging behaviour and school exclusions and "inspire positive change" so that the students can fulfil their potential at school.

.

### How?

We set out the logic model for the programme below.

The mentoring programme involves a carefully selected mentor working with groups of students over a number of weeks (typically 38) in 30-60 minute slots. Mentors are outgoing individuals with backgrounds that closely resemble the students; typically they have faced hardships, difficulties and challenges but have overcome them to reach their own goals and aspirations. Mentors are chosen strategically for schools and with the students they will use their own past experiences and learning to develop a positive, trusting relationship with the students. They are then in a position to challenge the students' attitudes and behaviours, enabling them to think about alternatives ways of thinking, feeling and behaving.

The mentoring programme covers three main subject areas with the students:

1. Self-esteem and relationships, e.g. raising self-esteem and resilience, controlling emotions, respecting others, healthy relationships and effective communication.

2. Behaviour and anger management e.g. controlling outbursts, releasing emotions appropriately, self-reflection, concentration, consequences of actions

3. Life skills and careers e.g. goal setting, positive social media use, empathy, tackling social barriers, aspirations, leadership/team work, values, cultures and beliefs.

### Who?

Twenty year 9 students from a Nottinghamshire school were taking part in the mentoring this evaluation has observed. The students were split into two separate groups for mentoring, receiving half an hour once a week for twelve weeks. At the outset we talked to the students about their motivation, what they knew about college and university and what their aspirations were. These were quite varied (see below) with some showing grounded aspirations such as social work or law and others perhaps less so, talking about being a footballer, a model or working in an F1 pitcrew. Motivation was not talked about positively; typically it was in reference to things they were motivated to avoid such as lessons or other people. Responses also indicated apprehension about the future. When they talked about their options they did however show awareness of college, apprenticeships and university but at the same time when asked about A levels they had little to say other than that that was too far away for them to think about yet.

Overall:

- They demonstrated some knowledge of what was on offer after school

- For some of them there were ideas about what careers they would be interested in

- Motivation to get to these careers was not readily expressed

### Outcomes?

We map observed outcomes to an adapted Kirkpatrick model of evaluation (see below). A range of data has been used to explore take-up, reaction, learning, behaviour and results: student feedback from a focus group; teacher feedback from interviews, attendance data and attainment data.

#### Take-up

All students who were put forward attended the sessions regularly. Learners attended on average 75% of sessions and all but three learners attended at least half of the sessions. One learner attended all the sessions and ten learners attended 85% of the sessions.

#### Reaction

Both groups of students took part in focus groups in February 2018 (early in the first half of the programme). We asked them to give us three words that described how they had experienced the programme so far; the same words were used by both groups:

Fun	Interesting	Good

Positive		Helpful		Chilled

Brings joy to my Mondays!

INTERESTING

A second focus group was run at the end of the programme. Again we asked students to reflect on how they had experienced the programme. At twelve weeks they still only had positive feedback using many of the same words as before: fun, educational, interesting, helpful, good.

IT’S MADE US FEEL HAPPY

#### Learning

Students were able to articulate a number of things they had learned from taking part in the programme. Many of these were connected to self-learning and emotional intelligence development, in particular many comments made reference to having more self-confidence, believing in themselves more and being self-reliant/responsible, e.g.:

| If you believe it you can do it | The only person who can stop you from doing what you want to do is yourself. | It’s important to make mistakes so you can learn from them |
| --- | --- | --- |
| Sometimes you want to do the wrong thing but it’s better to do what you NEED to do | Think before you act. | I need to be confident and positive |
| Don’t get in with the wrong people, try to get friends that won’t get you into trouble. | Never let anyone bring you down | Don’t let your past define you |

Several comments related to their future options and careers with clear indications that awareness of opportunities and the range of options open to them had increased. Further there was a realisation that they could have aspirations regardless of what their home life or background was but that they needed to attend to those now and not just ‘see what happens.’

| Education means a LOT | You need education | It doesn’t matter what background you’re from |
| --- | --- | --- |
| Sometimes you have to ignore what people say because it’s YOUR future that matters and nobody elses. | We’ve got more opportunities than I thought we did. For different subjects there are quite a lot of different jobs you can do. Or you could be an entrepreneur! | There is a lot more to do at college than I knew. I always thought it was just like school but there’s a lot more to do with jobs so it can help with choices after that. |
| I didn’t really think about what I wanted to before but now I realise that I need to think about what I want to do. I can’t just leave it until the last minute and do whatever comes my way. | I’d rather do something that actually entertains me… sometimes I feel like helping other people out… it makes you feel better. And not just getting a normal job - that’s everyday life. I want a job that has meaning. | It makes you think about all the paths you can take. |
| I want to get my head down more now because I know what the future holds. If you can focus then there’s quite a lot you could be doing but if you don’t get the grades you could end up doing anything or something that could lead you into something bad. Or being unemployed. | It helps you through the future AND through your past, it can help with mental health | It helps you out a lot in everyday situations |

#### Behaviour

Students were able to identify a number of behavioural changes. Most commonly this was about feeling more confident, having faith in themselves and believing in themselves more. For several of the male students a key change was feeling less angry, being able to manage their emotions and adopt more positive responses in challenging situations:

Confidence.

It has given me more confidence.

I have more confidence in myself.

I have more faith in myself.

I believe in myself a lot more now. I think about what I am going to do before I do it.

I used to get angry all the time and now I don’t. It has helped me out family wise because I used to get angry at my mum. She would get angry with my dad and I wouldn’t know which side to pick. It really stressed me out. But now I know that if you try and be a bit calmer and just get on with your own life then it makes it a bit easier.

Something happened today and this lad started to try and fight me. He started to swing for me… he did hit me… and I didn’t fight back because I knew that would be the wrong decision. It would have got me into trouble. So I just pushed him away.

.

Several students talked about changes to how they engaged with school, there was clear evidence that participation in the programme had led to clearer, more focussed thinking and attitudes towards school and this resulted in improved attendance in school and classes:

School has changed. My behaviour is better.

I come to school more often.

I go to more lessons now.

I keep saying to myself “just get your head down”. It pops into my head now.

The majority of students expressed a strong desire that the programme be continued for them in the next year with one participant stating that he did “…not know what I will do when this finishes”. Responses suggested that much of this is directly due to the mentor. The students talked about how they could respect and identify with her because she had the same background as they did. The mentor’s own particular path to success was peppered with challenges and difficulties that she was able to share with them and show them how she had overcome them. The students consequently were able to trust the mentor and felt the space she created was safe, positive and allowed them to be themselves. She was able to provide a reliable and trustworthy source of help for the students and one student was inspired to enter a career where she could help people much like the mentor did.

She makes me feel better, there’s trust around her, I feel safe around her.

She always has an answer to your problems, she knows what you’re going

through because she’s gone through it. She’s always there to help you.

### Conclusions

Learners who took part in the Think for the Future behavioural group mentoring reported that the programme had indeed created a safe, trusting place for them to talk. They showed clear indications of respect, trust and genuine affection for their mentor. Several of the learners indicated they were more able to manage their emotions and gave examples of when this had happened. The majority of learners indicated they understood themselves better and importantly were able to understand other’s behaviour more effectively. They were also able to indicate that they had learned about the importance of giving thought to their futures and that their options were wider than they might have thought previously. Feedback from the school regarding exclusions, behaviour, attainment and attendance has not yet been obtained.

## C. DANCOP v non DANCOP learners Over time

In year 1 of phase 1 of DANCOP iCeGS ran a survey developed by the NCOP evaluation team CFE. The survey explored key elements linked to barriers to FE and HE in learners. The same survey was distributed to the same learners in year 2 of phase 1 (April/May 2019) in order to assess change in the medium term and compare DANCOP to non DANCOP learners. This section discusses the findings of these surveys, reporting on the aggregated data collected from all the schools and matched learners who took part in phase 1 and phase 2.

Data was collected from learners in seven different schools, each in a different target ward. Four schools were in Derby, two in North Derbyshire and one in South Derbyshire. Data was collected from 728 matched learners in total, ranging in age from year 9 through to year 12. Learners who lived in DANCOP localities and those who did not but attended participating schools took part in the survey.

Individual learners are categorised as DANCOP learners or not based on their home postcodes; the survey data includes responses from both DANCOP (n = 440) and non-DANCOP (learners n = 296). The schools who participated varied in the percentage of their learners categorised as DANCOP learners, ranging from under 5% to over 78%.  Table 30 denotes the percentage of DANCOP and non-DANCOP learners attending each participating school and the number of DANCOP and non-DANCOP learners from each school who participated in the survey. The majority of non-DANCOP learners who took part in the survey were from a school with a very low percentage of DANCOP learners however the remainder of non-DANCOP learners came primarily from the school with the greatest percentage of DANCOP learners. The comparison between DANCOP and non-DANCOP learners is not necessarily one of affluent versus deprived areas.

Table 30 School's % of DANCOP learners and numbers of DANCOP and non-DANCOP learners who participated in the survey

| School | % of DANCOP learners in school | Number of DANCOP learner survey responses | Number of non DANCOP learner survey responses | Total |
| --- | --- | --- | --- | --- |
| A | 4.8 | 15 | 209 | 224 |
| B | 11.6 | 7 | 0 | 7 |
| C | 78.6 | 103 | 66 | 169 |
| D | 61.3 | 290 | 18 | 308 |
| E | 55.5 | 12 | 3 | 15 |
| F | 11.3 | 1 | 0 | 1 |
| G | 4 | 0 | 4 | 4 |

The report first considers the demographics of the learners who took part. It then moves on to examine learner’s intentions and aspirations for the future. Next it considers key influencers, self-perceptions and knowledge of HE.

### Learner characteristics and demographics

The survey collected data on gender, ethnicity, year of study (in year 1 of phase 1) whether the learner considered themselves to have a disability and whether learners would be first generation to attend HE – see Table 31.

Table 31 Learner characteristics

| Learner Characteristic | % |
| --- | --- |
| Female | 50% |
| Male | 50% |
| White - British | 84.3% |
| White - Irish | 1.0% |
| White - Scottish | 0.5% |
| Other White background | 2.2% |
| Black or Black British - Caribbean | 0.2% |
| Black or Black British - African | 0.5% |
| Other Black background | 0.7% |
| Mixed White and Black Caribbean | 1.2% |
| Mixed White and Black - African | 0.5% |
| Asian or Asian British - Pakistani | 0.2% |
| Other Asian background | 0.7% |
| Mixed White and Asian | 0.5% |
| Chinese | 0.2% |
| Gypsy traveller | 0.2% |
| Other mixed background | 0.2% |
| Prefer not to say | 4.1% |
| Year 9 | 34.8% |
| Year 10 | 33.8% |
| Year 11 | 14.3% |
| Year 12 | 1.0% |
| Disability | 9% |
| No disability | 78% |
| Prefer not to say | 13% |
| First generation | 27% |
| Not first generation | 35% |
| Don’t know | 38% |

Of note is that there were few responses from year 12 learners and in fact the majority of learners were from years 9 and 10. Learners typically classified themselves as White-British and nearly 40% of learners did not know if they would be the first in their family to attend HE – this is possibly a reflection on the younger age of the participants.

### Aspirations

This section explores:

- learner’s aspirations for when they finished their current studies in year 1 of phase 1 and whether these changed over time at year 2 of phase 1.

- their intentions towards attending HE post-18 or at a later date in year 1 of phase 1 and whether these changed over time at year 2 of phase 1

For brevity the analyses focus on the comparison of phase 1/phase 2 data against DANCOP learner status and do not consider gender, year group, ethnicity or generation status.

#### After their current studies

Learners were asked to indicate from a range of options what they wanted to do after their current studies at year 1 and year 2. Responses can be seen in Table 32.

In phase 1 aspirations were varied and differed slightly between DANCOP and non DANCOP learners. The most popular choice for both learner types was to study at an FE college (DANCOP learner n = 102, non DANCOP learner n = 93). For both learner types the second most common preference was to begin an apprenticeship (DANCOP n = 56, non DANCOP n = 61). Getting a full time or a part time job was a more common preference for DANCOP learners than for non DANCOP learners who instead showed preferences for studying at a university (both local and away from home). It was more common for DANCOP learners to not know what they wanted to do when they finished their current studies than non DANCOP learners.

Table 32 Preferred options at year 1 and year 2

| Preferred option | DANCOP learner | Non DANCOP learner | Total |
| --- | --- | --- | --- |
| Other year 1 | 22 | 4 | 26 |
| Other year 2 | 19 | 4 | 23 |
| Get a full-time job year 1 | 48 | 15 | 63 |
| Get a full-time job year 2 |  |  |  |
| Get a part-time job year 1 | 32 | 18 | 50 |
| Get a part-time job year 2 |  |  |  |
| Stay at or stay in further education college year 1 | 102 | 93 | 195 |
| Stay at or stay in further education college year 2 | 99 | 83 | 182 |
| Study higher education at a further education college/provider year 1 | 24 | 1 | 25 |
| Study higher education at a further education college/provider year 2 | 37 | 14 | 51 |
| Study at a local university year 1 | 21 | 27 | 48 |
| Study at a local university year 2 | 66 | 21 | 87 |
| Study at a university away from home year 1 | 38 | 25 | 63 |
| Study at a university away from home year 2 | 64 | 18 | 82 |
| Begin an apprenticeship year 1 | 56 | 61 | 117 |
| Begin an apprenticeship year 2 | 55 | 64 | 119 |
| Begin a higher/degree apprenticeship year 1 | 4 | 0 | 4 |
| Begin a higher/degree apprenticeship year 2 | 11 | 5 | 16 |
| Some other type of training year 1 | 6 | 8 | 14 |
| Some other type of training year 2 | 6 | 8 | 14 |
| Don't know year 1 | 76 | 43 | 119 |
| Don’t know year 2 | 16 | 45 | 61 |

In phase 2 the most common preference was still further education in an FE college (DANCOP learners n = 99; non DANCOP learners n = 83) and beginning an apprenticeship remained a common preference for both learner types. However, there was a marked increase in the number of DANCOP learners preferring attending a local university (n=66) or university way from home (n=64). This increase is not seen with non DANCOP learners.

#### Applying to HE

Learners were asked to indicate how likely they were to apply to HE using the following response scale:

- Definitely won’t apply

- Very unlikely to apply

- Fairly unlikely to apply

- Fairly likely to apply

- Very likely to apply

- Definitely will apply

- Don’t know

The percentage of responses for each point on the scale are shown in Table 33 which allows for comparison of DANCOP and non DANCOP learners at both phases.

Table 33 DANCOP  versus non DANCOP learners intentions to apply to HE at age 18/19 for year 1 and 2

| Is learner a DANCOP learner |  | Year 1 % | Year 2 % | Increase (+) Or decrease (-) |
| --- | --- | --- | --- | --- |
| DANCOP learners | Definitely won't apply | 4.6 | 3.0 | - |
|  | Very unlikely | 6.2 | 4.5 | - |
|  | Fairly unlikely | 9.6 | 8.8 | - |
|  | Fairly likely | 26.4 | 29.9 | + |
|  | Very likely | 20.4 | 24.2 | + |
|  | Definitely will apply | 12.0 | 12.0 | - |
|  | Don't know | 20.9 | 17.8 | - |
|  | Total | 100.0 | 100.0 |  |
| Non DANCOP learners | Definitely won't apply | 5.5 | 5.0 | - |
|  | Very unlikely | 6.1 | 4.6 | - |
|  | Fairly unlikely | 16.0 | 14.0 | - |
|  | Fairly likely | 21.2 | 23.0 | + |
|  | Very likely | 19.1 | 22.0 | + |
|  | Definitely will apply | 11.9 | 11.7 | - |
|  | Don't know | 20.1 | 19.7 | - |
|  | Total | 100.0 | 100.0 |  |

In phase 1 approximately 20% of both learner types did not know if they would apply or not. This decreased in phase 2 for both groups of learners although the decrease was greater for DANCOP learners. For both DANCOP and non DANCOP learners there was a decrease between phase 1 and phase 2 in:

- Those who would definitely not apply

- Those who were very unlikely to apply

- Those who were fairly unlikely to apply

And an increase between phase 1 and phase 2 in:

- Fairly likely to apply

- Very likely to apply

### Key Influences

Learners were asked to indicate which of family, friends, teachers, career advisors or ‘other’ was the strongest influence on their decision making about what to do next. The strongest influence on decision making was the family for both groups of learners and in both years of phase 1 with over 66% of learners reporting this (see Table 34). DANCOP learners showed a small decrease in the number reporting family as the greatest influence from phase 1 to phase 2 with careers advisors and ‘other’ becoming more popular. Non DANCOP learners remained reasonably static over time.

Table 34 Greatest influences on decision making for DANCOP and non DANCOP learners in year 1 and 2

|  | Greatest Influence | PHASE 1 % | PHASE 2 % | Increase (+) Or decrease (-) |
| --- | --- | --- | --- | --- |
| DANCOP learner | Family | 75.6 | 68 | - |
|  | Friends | 7.0 | 6.8 | - |
|  | Teachers | 4.2 | 4.1 | - |
|  | Careers advisors | 2.6 | 4.1 | + |
|  | Other | 10.6 | 17 | + |
| Non DANCOP learner | Family | 66.4 | 66.2 | - |
|  | Friends | 5.1 | 5.1 |  |
|  | Teachers | 5.8 | 5.7 | - |
|  | Careers advisors | 3.1 | 3.0 | - |
|  | Other | 19.7 | 19.9 | + |

### Confidence, motivation and academic fit

This section explores the psychological and sociological concepts which literature suggests underpins learner’s choices regarding HE; their confidence regarding their academic ability, their self-efficacy and the extent to which they perceive themselves as a fit for academic life.

Learners responded to:

- I am motivated to do well in my studies

- I could get the grades I need for further study

- I could gain a place on a good course if I wanted to

- HE is for people like me

- I would fit in well with others in HE

- I have the academic ability to succeed at HE

- I could cope with the level of study required at HE

Learners used a five point Likert scale (1 strongly disagree to 5 strongly agree) with a sixth option ‘I don’t know’. The data set was cleaned with ‘don’t know responses’ being recoded as a 0. Mean ratings were calculated for each of the measures above for year 1 and year 2 and for DANCOP and non DANCOP learners. Mean ratings for each group and for both years are shown in Table 35 and indicate increases for both DANCOP and non DANCOP learners from year 1 to year 2.

Table 35 Mean ratings for DANCOP v non DANCOP learners in year 1 and 2

|  | DANCOP learners N=356 |  | Non DANCOP learners N=292 |  |
| --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 1 | Year 2 |
| I am motivated to do well in studies | 4.04 | 4.62 | 3.99 | 4.07 |
| I could get the grades I need for further study | 3.55 | 3.96 | 3.49 | 3.55 |
| I could gain a place on a good course if I wanted to | 3.27 | 4.09 | 3.35 | 3.78 |
| HE is for people like me | 2.62 | 3.10 | 2.71 | 2.98 |
| I would fit in well with others in HE | 2.67 | 2.73 | 2.80 | 2.92 |
| I have the academic ability to succeed at HE | 2.91 | 3.13 | 2.92 | 2.86 |
| I could cope with the level of study required at HE | 2.82 | 3.01 | 2.83 | 2.92 |

A series of mixed ANOVA’s was run to determine whether there were differences between DANCOP and non DANCOP learners and whether there were differences between Year 1 and Year 2. Results are in Table 36 which displays the F result, the significance level and the partial eta squared which is an assessment of the size of the effect (where the effect size reaches .01 this is considered small, where it reaches .06 this is considered moderate and where it reaches .1 this is considered a large effect size). Significant findings are highlighted in blue.

Table 36 Mixed ANOVA results showing main and interaction effects for learner status and year with estimated effect sizes using partial eta squared.

| Measure | Effect | F | Sig. | Effect size (pes) |
| --- | --- | --- | --- | --- |
| I am motivated to do well in studies | Effect of Year | 95.40 | .000 | .129 (large) |
|  | Effect of DANCOP learner status | 20.354 | .000 | .031 (small) |
|  | Interaction effect | 86.86 | .000 | .119 (large) |
| I could get the grades I need for further study | Effect of Year | 47.83 | .000 | .069 (moderate) |
|  | Effect of DANCOP learner status | 5.46 | .020 | .008 |
|  | Interaction effect | 36.452 | .000 | .039 (small) |
| I could gain a place on a good course if I wanted to | Effect of Year | 154.77 | .000 | .194 (large) |
|  | Effect of DANCOP learner status | .962 | .327 | .001 |
|  | Interaction effect | 12.43 | .000 | .023 (small) |
| HE is for people like me | Effect of Year | 84.44 | .000 | .106 (moderate) |
|  | Effect of DANCOP learner status | .026 | .872 | .000 |
|  | Interaction effect | 6.67 | .010 | .009 |
| I would fit in well with others in HE | Effect of Year | 25.18 | .000 | .034 (small) |
|  | Effect of DANCOP learner status | 1.75 | .186 | .002 |
|  | Interaction effect | 1.549 | .214 | .002 |
| I have the academic ability to succeed at HE | Effect of Year | 4.13 | .042 | .006 |
|  | Effect of DANCOP learner status | 1.29 | .255 | .002 |
|  | Interaction effect | 12.12 | .0014 | .017 (small) |
| I could cope with the level of study required at HE | Effect of Year | 10.48 | .001 | .015 (small) |
|  | Effect of DANCOP learner status | .083 | .774 | .000 |
|  | Interaction effect | .970 | .325 | .001 |

- Mean ‘I am motivated to do well in my studies” was found to differ significantly between DANCOP and non DANCOP learners with DANCOP learners reporting higher mean scores. The mean scores also increased significantly over time. The increase in mean scores over time was not the same for DANCOP and non DANCOP learners however, there was a significant, large, interaction effect whereby DANCOP learners reported a significantly greater increase in mean score over time than non DANCOP learners.

- Mean “I could get the grades I need for further study” was found to differ significantly between DANCOP and non DANCOP learners with DANCOP learners reporting higher mean scores.  Mean scores were also found to increase over time for all learners however the increase in mean scores over time was not the same for DANCOP and non DANCOP learners however. There was a significant interaction effect such that DANCOP learners reported a significantly greater increase in mean score over time than non DANCOP learners.

- Mean “I could gain a place on a good course if I wanted to” was found to increase over time but the increase in mean scores over time was not the same for DANCOP and non DANCOP learners. There was a significant interaction effect whereby DANCOP learners reported a significantly greater increase in mean score over time than non DANCOP learners.

- Mean “HE is for people like me” was found to increase over time for all learners but the increase in mean scores over time was not the same for DANCOP and non DANCOP learners. There was a significant interaction effect whereby DANCOP learners reported a significantly greater increase in mean score over time than non DANCOP learners.

- Mean “I would fit in well with others at HE” was found to increase over time for all learners.

- Mean “I have the academic ability to succeed at HE” was found to increase over time for all learners but the increase in mean scores over time was not the same for DANCOP and non DANCOP learners. There was a significant interaction effect whereby DANCOP learners reported a significantly greater increase in mean score over time than non DANCOP learners.

- Mean “I could cope with the level of study required at HE” was found to increase over time for all learners but the increase in mean scores over time was not the same for DANCOP and non DANCOP learners. There was a significant interaction effect whereby DANCOP learners reported a significantly greater increase in mean score over time than non DANCOP learners.

In summary there was a trend for measures of confidence, motivation and fit to increase over time for all learners however DANCOP learners typically showed a greater increase over time than non DANCOP learners. The two exceptions to this were fitting in well with others at HE and coping the level of study required where the increase over time was equivalent for DANCOP and non DANCOP learners.

### Knowledge of higher education

This section explores learner’s knowledge of a range of aspects of HE: the courses that are available, routes into HE, how to apply, qualifications needed, student life, financial support, accommodation, support and how courses link to careers. It also explores the impact they thought HE could have on their lives, specifically whether they believe it will broaden their horizons, challenge them intellectually, develop valuable life skills, improve their social life, increase their earning potential and help them get a better job.

#### Knowledge of aspects of HE

Knowledge of aspects of HE was assessed using a three point response scale: Nothing; A little; A lot. Table 37 shows responses from DANCOP and non DANCOP learners at Year 1 and Year 2 for each aspect of knowledge. Chi square analyses were run to compare the responses from DANCOP learners with those from non DANCOP learners at Year 1 and then again at Year 2 on each aspect of knowledge.

###### At Year 1:

- All learners were more likely to know nothing about how to apply to HE through UCAS than to know a little or a lot (p = .042)

- All learners were more likely to know a little about the grades and qualifications they heeded to get into the course they wanted than to know nothing or a lot (p = .029)

- Non DANCOP learners were more likely to know a little about student life than DANCOP learners (p = .001)

- DANCOP learners were more likely than non DANCOP learners to know a lot about how HE courses link to careers than non DANCOP learners (p= .019)

###### At Year 2:

- DANCOP learners were more likely than non DANCOP learners to know a lot about the courses that are available in HE (p=.000)

- DANCOP learners were more likely than non DANCOP learners to know a lot about the different routes into HE (p=.000)

- DANCOP learners were more likely than non DANCOP learners to know a lot about how to apply through UCAS to HE (p = .000)

- DANCOP learners were more likely than non DANCOP learners to know a lot about where to find information about applying to HE (p = .015)

- DANCOP learners were more likely than non DANCOP learners to know a lot about the qualifications and grades needed to get into the course they wanted to (p=.001)

- DANCOP learners were more likely than non DANCOP learners to know about the costs of study at HE (p = .014)

Table 37 Knowledge of aspects of HE in DANCOP and non DANCOP learners at year 1 and year 2

|  | Year 1 |  |  |  |  |  |  | Year 2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | DANCOP (n=350) |  |  | Non DANCOP (n=288) |  |  |  | DANCOP (n=350) |  |  | Non DANCOP (n=288) |  |  |
|  | Nothing | A little | A lot | Nothing | A little | A lot |  | Nothing | A little | A lot | Nothing | A little | A lot |
| Courses available in HE | 74 | 227 | 49 | 60 | 202 | 25 |  | 64 | 114 | 172 | 53 | 184 | 50 |
| Routes into HE | 89 | 223 | 37 | 84 | 173 | 31 |  | 61 | 121 | 167 | 75 | 152 | 61 |
| Applying through UCAS | 258 | 81 | 10 | 232 | 54 | 2 |  | 105 | 26 | 219 | 152 | 26 | 110 |
| Where to find information about applying | 111 | 192 | 46 | 80 | 175 | 32 |  | 87 | 107 | 155 | 73 | 116 | 98 |
| Qualifications and grades needed | 98 | 191 | 77 | 52 | 198 | 38 |  | 99 | 128 | 123 | 60 | 149 | 78 |
| Student life | 82 | 191 | 77 | 52 | 198 | 38 |  | 83 | 155 | 111 | 52 | 164 | 72 |
| Courses and careers | 67 | 205 | 78 | 60 | 188 | 39 |  | 67 | 147 | 134 | 62 | 117 | 108 |
| Costs of studying | 107 | 175 | 67 | 87 | 154 | 47 |  | 108 | 1630 | 110 | 88 | 135 | 64 |
| Financial support | 162 | 145 | 43 | 126 | 138 | 24 |  | 155 | 134 | 60 | 124 | 133 | 31 |
| Accommodation | 115 | 182 | 52 | 85 | 154 | 49 |  | 115 | 182 | 52 | 85 | 154 | 49 |
| Support available | 135 | 173 | 42 | 105 | 153 | 30 |  | 135 | 173 | 42 | 105 | 153 | 30 |

#### Knowledge of impacts of attending HE

Learners rated their agreement with a number of statements about the potential impacts of attending HE:

- HE will broaden my horizons

- HE will challenge me intellectually

- HE will give me valuable skills

- HE will improve my social life

- HE will enable me to earn more

- HE will enable me to get a better job

Learners used a six point scale to respond where:

- 1 = strongly disagree

- 2 = disagree

- 3 = neither agree nor disagree

- 4 = Agree

- 5 = Strongly agree

- 6 = Don’t know

The data was cleaned and don’t know scores recoded to 0. Scores were then treated as numeric variables. Mean scores for each impact, by learner status and for each phase, are shown below in Table 38.

Table 38 Mean impact ratings for DANCOP and non DANCOP learners at year 1 and 2

|  | DANCOP learners |  |  | Non DANCOP learners |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Mean | N | SD | Mean | N | SD |
| HE will broaden my horizons Year 1 | 2.81 | 429 | 1.82 | 3.05 | 277 | 1.60 |
| HE will broaden my horizons Year 2 | 3.22 | 429 | 1.73 | 3.25 | 277 | 1.59 |
| HE will challenge me intellectually Year 1 | 3.30 | 428 | 1.70 | 3.30 | 277 | 1.56 |
| HE will challenge me intellectually Year 1 | 3.52 | 428 | 1.53 | 3.35 | 277 | 1.52 |
| HE will give me valuable life skills Year 1 | 3.36 | 429 | 1.71 | 3.42 | 277 | 1.43 |
| HE will give me valuable life skills Year 2 | 3.58 | 429 | 1.51 | 3.48 | 277 | 1.39 |
| HE will improve my social life Year 1 | 3.15 | 428 | 1.67 | 3.23 | 276 | 1.48 |
| HE will improve my social life Year 2 | 3.23 | 428 | 1.48 | 3.37 | 276 | 1.32 |
| HE will enable me to earn more Year 1 | 3.27 | 428 | 1.71 | 3.41 | 274 | 1.55 |
| HE will enable me to earn more Year 2 | 3.50 | 428 | 1.54 | 3.46 | 274 | 1.51 |
| HE will enable me to get a better job Year 1 | 3.50 | 429 | 1.69 | 3.62 | 277 | 1.45 |
| HE will enable me to get a better job Year 2 | 3.73 | 429 | 1.47 | 3.67 | 277 | 1.40 |

Table 38 shows that typically, means for each impact increased for both sets of learners between Year 1 and Year 2. A series of Mixed ANOVA’s were run to test whether the differences between Year 1 and Year 2 were statistically different from each other and whether DANCOP and non DANCOP learners show similar trends over time or not. Results are shown below in Table 39. Statistically significant findings are highlighted in blue and the results include partial eta squared which is a measure of the size of the effect. For each of the impacts there was a significant effect of Year meaning that mean ratings increased significantly over time for all learners. However, the increase in time for each impact was not the same for DANCOP learners as non DANCOP learners as indicated by the significant interaction effects. For HE will broaden my horizons, HE will challenge me intellectually, HE will give me valuable life skills, HE will enable me to earn more and HE will enable me to get a better job DANCOP learners reported significantly greater increases over time than non DANCOP learners. For HE will improve my social life it was non DANCOP learners that showed a greater increase over time compared with DANCOP learners.

Table 39 Mixed ANOVA results for potential impacts of HE by DANCOP learner status and Year

| Measure |  | F | Sig | Effect size (PES) |
| --- | --- | --- | --- | --- |
| HE will broaden my horizons | Effect of Year | 46.63 | .000 | .062 (moderate) |
|  | Effect of DANCOP learner status | 1.25 | .263 | .002 |
|  | Interaction effect | 3.39 | .027 | .007 |
| HE will challenge me intellectually | Effect of Year | 19.15 | .000 | .027 |
|  | Effect of DANCOP learner status | .443 | .506 | .001 |
|  | Interaction effect | 7.50 | .006 | .011 (small) |
| HE will give me valuable life skills | Effect of Year | 19.14 | .000 | .026 (small) |
|  | Effect of DANCOP learner status | .032 | .857 | .000 |
|  | Interaction effect | 7.63 | .006 | .011 (small) |
| HE will improve my social life | Effect of Year | 24.23 | .000 | .033 (small) |
|  | Effect of DANCOP learner status | 1.08 | .297 | .002 |
|  | Interaction effect | 6.59 | .010 | .009 |
| HE will enable me to earn more | Effect of Year | 13.64 | .000 | .019 (small) |
|  | Effect of DANCOP learner status | .059 | .808 | .000 |
|  | Interaction effect | 11.29 | .001 | .016 (small) |
| HE will enable me to get a better job | Effect of Year | 19.92 | .000 | .028 (small) |
|  | Effect of DANCOP learner status | .058 | .809 | .000 |
|  | Interaction effect | 8.10 | .005 | .011 (small) |

In summary there was a trend for all learners to report higher mean scores for potential impacts of HE in Year 2, however, DANCOP learners typically showed a greater increase over time than non DANCOP learners. The exceptions to this was ‘HE will improve my social life’ which increased for non DANCOP learners.

## D. Parental Feedback

Parents (n=95) completed surveys after attending one of the following activities:

- Springwell parents evening

- West Vision Nottinghamshire parents evening

- Oakwood and Park Vale Academies Family day

- UCAS Parents/student talk

They rated the activities they attended as excellent or good (see Table 40). With only 1 respondent indicating that an activity was fair (West Vision Nottinghamshire parents evening).

Table 40 Parental ratings of activities

| Activity |  | Excellent | Good | Fair |
| --- | --- | --- | --- | --- |
|  | Springwell parents evening | 0 | 1 | 0 |
|  | Family day | 9 | 2 | 0 |
|  | UCAS Parents/student talk | 5 | 5 | 0 |
|  | Vision West Nottinghamshire parents evening | 13 | 3 | 1 |

Table 41 Mean responses for parent respondents

| Variables | Mean | N | SD |
| --- | --- | --- | --- |
| I know about university (before) | 4.05 | 18 | 1.05 |
| I know about university (after) | 4.66 | 18 | .59 |
| I want my child to go to university (before) | 4.25 | 39 | .93 |
| I want my child to go to university (after) | 4.71 | 39 | .60 |
| I know enough to support my child if they want to apply to university (before) | 3.18 | 38 | 1.15 |
| I know enough to support my child if they want to apply to university (after) | 4.44 | 38 | .82 |

Paired sample t-tests suggested that parents:

- Knew significantly more after attending significantly more about university after having attended the event (this questions was only asked of those who attended the West Vision Nottinghamshire parents evening) t = -2.650, df = 27,  p = .017

- Were more likely to want their child to go to university after attending an activity (this question was asked of parents at all activities) t = -3.061, df = 38, p = .004

- Felt able to support their children if they wanted to apply to university after having attended an event (this question was asked of parents at all activities) t = -6.882, df = 37, p = .000.

The effect was strongest for feeling more able to provide support.

Hubs talked about their observations of parents during sessions which have included them and felt this had typically been well received.

“But the schools want us to be there and when we have done sessions where we've actually talked to parents, they've gone down fairly well with parents and they’ve asked a lot of questions….” Hub team member

## E. Teacher and other staff Feedback

Teacher/staff feedback was collected in two ways; firstly from the teams delivering specific activities and secondly via a survey sent to all schools who had engaged with DANCOP.

### Activity teacher feedback

One hundred and one teacher feedback surveys were completed which provided feedback on a number of different activities. Table 40 displays the delivery teams, activities which feedback was provided for and the number of teachers who provided feedback.

Table 42 Delivery teams, activities and number of respondents

| Delivery team(s) |  | Activity title | Number of teacher responses |
| --- | --- | --- | --- |
|  | Central/UoD Widening Access | Parents evening | 2 |
|  | Chesterfield college | Higher & Degree Apprenticeships | 2 |
|  | Derby Hub | David Hodgson Talk UCAS parent & student talk On site visit | 3 2 1 |
|  | IntoUniversity | Business in FOCUS FOCUS on choice FOCUS on future FOCUS on success | 17 3 2 7 |
|  | Mansfield Hub | Revision skills session | 5 |
|  | Stephenson College | Explore manufacturing Go4SET | 1 1 |
|  | West Nottinghamshire College outreach | Alternative work experience days Drop down day at VWNC HE experience day Health & social care day Skills day subject taster Transferable skills workshop | 6 5 2 3 6 10 |
|  | Other | Boys into HE | 2 |

When asked to rate the activities they had observed with their learners, 69% of responses were ‘excellent’, 30% were ‘good’ and only 1% was ‘fair’. No responses indicated the activity was poor. Ratings by activity are shown below in Table 41. With the exception of the Services Taster day staff were more likely to rate the event as excellent than good or fair.

Table 43 Teacher ratings of activities

| Activity |  | Excellent | Good | Fair | Total |
| --- | --- | --- | --- | --- | --- |
|  | Alternative work experience day | 5 | 1 | 0 | 6 |
|  | Boys into HE | 1 | 1 | 0 | 2 |
|  | Business in FOCUS | 14 | 1 | 0 | 17 |
|  | Buxton Community School | 4 | 3 | 1 | 6 |
|  | David Hodgson Talk | 2 | 1 | 0 | 3 |
|  | Drop down day at VWNC | 1 | 1 | 0 | 5 |
|  | Employability workshop | 6 | 4 | 0 | 7 |
|  | Explore manufacturing | 1 | 1 | 0 | 1 |
|  | FOCUS on choices workshop | 3 | 0 | 0 | 3 |
|  | FOCUS on future | 2 | 0 | 0 | 2 |
|  | FOCUS on success workshop | 7 | 0 | 0 | 7 |
|  | Go4SET Assessment and Celebration | 0 | 0 | 0 | 1 |
|  | HE experience day | 2 | 1 | 0 | 2 |
|  | HE higher & degree apprenticeships | 1 | 0 | 0 | 2 |
|  | Health & Social Care day | 2 | 1 | 0 | 3 |
|  | Introduction HE choices | 1 | 0 | 0 | 1 |
|  | On site visit | 1 | 0 | 0 | 1 |
|  | Parent's evening | 1 | 0 | 0 | 2 |
|  | Revision skills session | 0 | 1 | 0 | 5 |
|  | Services Taster HE experience day | 0 | 5 | 0 | 1 |
|  | Skills day - subject taster | 3 | 1 | 0 | 6 |
|  | Transferable skills workshop | 7 | 3 | 0 | 10 |
|  | UCAS parent and student talk | 1 | 3 | 0 | 1 |
| Total |  | 65 | 28 | 1 | 95 |

Responses to questions regarding ‘what worked’ elements were answered by comparatively few respondents (n= 23). These responses indicated that sessions which were ‘pacy’, included tasks and indeed a range of tasks tended to keep learners more engaged. Other comments reflected on the utility of the in depth knowledge that was provided which helped to develop awareness.

### ICEGS Survey

###### WHO RESPONDED?

Ten respondents identified Derby as their local DANCOP hub, 6 respondents identified Nottingham as their local DANCOP hub and 6 respondents identified Mansfield as their local DANCOP hub. Respondents had a range of job titles including:

- Raising aspirations co-ordinator

- Assistant head teacher

- Careers mentor

- Career lead

- CEIAG co-ordinator

- Faculty leader

- Careers advisor

- Aspirational mentor

- DANCOP school mentor

The percentage of DANCOP learners at each institute ranged from 15% to 95% with an average of 56%.

###### DANCOP SESSIONS

Respondents were asked to indicate how many sessions their school had delivered with DANCOP. Figure 8 breaks this down in more detail. From the eleven DANCOP sessions identified, UCAS, career and Higher and Degree Apprenticeship sessions were delivered least frequently while university information and employability sessions were delivered most frequently. Every respondent was aware of a university information session being delivered at least once in their institute.

Figure 8 DANCOP Sessions

###### YEAR GROUP

The total number of DANCOP activities that were delivered varied for each year group. Eleven of 17 respondents said that at least 3 DANCOP sessions were delivered to Year 9 learners. Five of 17 respondents said that Year 9 learners had between 1 and 2 DANCOP sessions in total and 1 respondent said that 0 DANCOP sessions were delivered to Year 9 learners.

Thirteen of 17 respondents said that at least 3 DANCOP sessions were delivered to Year 10 learners. Four of 17 respondents said that Year 10 learners had between 1 and 2 DANCOP sessions in total.

Figure 9 Year groups

###### DANCOP SESSIONS: EFFECTIVENESS AND RELEVANCE

Participants were asked to rate the effectiveness of each DANCOP session on a scale:

- Not effective

- Somewhat effective

- Very effective

- Not applicable

Figure 10 breaks their responses down in detail.

Figure 10 Effectiveness of DANCOP sessions

None of the 10 sessions were identified as not being effective. The sessions that were identified the most as being very effective include employability (15 of 19 respondents), university information (15 of 19 respondents), personal effectiveness (11 of 19 respondents) and STEM (10 of 19 respondents) sessions.

Participants were next asked to rate the relevance of each DANCOP session on a scale of:

- Not at all relevant

- Somewhat relevant

- Very relevant

- Not applicable

Figure 11 shows that 9 of the 10 sessions were rated by respondents as being at the least somewhat relevant while the PE session was identified by one respondent as not being relevant at all.

The sessions that were identified the most as being very relevant include employability (17 of 19 respondents), university information (18 of 19 respondents), and personal effectiveness (16 of 19 respondents) sessions.

Figure 11 Relevance of DANCOP sessions

###### ATTITUDES

Participants were next asked the extent to which their learner’s attitudes towards work, FE and HE had changed as a result of participating in DANCOP funded activities. Figure 12 shows that thirteen out of 18 respondents said they felt learners are more likely to work hard at school to achieve good grades. 14 of 18 respondents felt learners are more likely to progress onto FE and 16 of 18 respondents also felt learners would be more like to progress onto HE.

Figure 12 Changes in attitudes

###### BEHAVIOUR, ATTENDANCE AND KNOWLEDGE

Participants were next asked to what extent do they think their learner’s behaviour, attendance, and knowledge of career options have changed as a result of participating in DANCOP funded activities. Figure 13 breaks their responses down in detail.

Figure 13 Changes in behaviour, attendance and knowledge

All 19 respondents said they felt learners’ knowledge of different career options had improved. 14 of 18 respondents felt learners’ attendance and behaviour stayed the same while 4 learners felt they had improved. No respondents felt that learners’ knowledge, behaviour or attendance got worse.

## F. Feedback from Staff in DANCOP funded roles

Hubs were asked about how they felt their activities had been received and their possible impact. They noted that typically feedback was positive – from learners, teachers and parents. They noted that often learners would engage more with them as opposed to a teacher:

“I've had so much questions about university, by the end, I said right this is your chance to ask me anything, and we do, so I think having an extra person who is not their teacher or their head teacher, to talk through what university is, be honest about the funding, about, you know, where you should live etc, I think schools really like that.  We often get "oh it's better coming from you than it is from me."

## Summary of impacts

The evaluation poses a number of questions regarding specific impacts on learners. This section brings together the findings discussed above to answer these questions.

Have the learners developed positive attitudes, aspirations and motivations?

Learner feedback indicated positive shifts in feeling motivated to work hard in school/college increased thinking about applying to university in the future. Compared to non DANCOP learners they also reported greater increases in motivation to do well in their studies, that HE was for people like them and that they would fit in well with others at HE. Focus group feedback from learners demonstrated clear, positive, changes in attitudes and behaviour.

Learners feedback showed significant increases in thinking about apply to HE and compared to learners became more likely to feel they were fairly likely to apply at Year 2 compared to Year 1, although this was the finding for all learners, not just DANCOP learners. Teachers who completed the survey suggested that there had been increases in the number of learners who were now more likely to consider FE and HE.

Have learners increased knowledge of career options, pathways and progressing to HE?

Learner feedback indicated significant increases in knowing where to get information about university and knowing enough about future options to help make decisions about what to do after school/college. Compared to non DANCOP learners, at Year 2 DANCOP learners were more likely to know a lot about the courses that are available in HE, the different routes into HE, how to apply through UCAS to HE, where to find information about applying to HE and the qualifications and grades needed to get into the course they wanted to. There is limited data to explore whether learners had greater awareness of career options - school staff who completed the iCeGS survey suggested that their learners were more aware of career options.

Have learners increased knowledge and awareness of funding and support in progression routes/destinations?

DANCOP learners were more likely than non DANCOP learners to know about the costs of study at HE by Year 2 but there was no evidence that they knew more about support.

Have learners increased knowledge of how to study and revise?

Feedback from learners who took part in DANCOP revision activities reported significant increases in feeling confident about revising and knowing some techniques to help them revise. Both DANCOP and non DANCOP learners reported feeling more confident in their ability cope with the level of study required at HE by Year 2.

Have learners increased confidence?

Learners who took part in activities reported significant increases in knowing enough about their options to make a decision regarding their future, feeling able to go into HE, feeling confident about fitting in and feeling confident about revising. Compared to non DANCOP learners they also reported increases in believing they could get the grades they need for further study, that they could gain a place on a good course if they wanted to, that they have the academic ability to succeed at HE and that they could cope with the level of study required at HE.

Assess perceived value and benefit

Teachers and other school staff who completed the iCeGS study suggested that they had typically perceived the activities to be relevant and effective in meeting the aims of the session. Teacher feedback stated that activities were perceived to be excellent or good. School staff suggested in the survey that typically their learners were now more likely to be considering HE or FE. However, they did not feel there had been any change in attendance or behaviour in the classroom. From a parental perspective, attending a parents evening, a family day or a UCAS talk appears to have significantly increased the parent’s knowledge of what university is, how much they would like their child to go to university and their ability to support their child should they wish to apply.

# Enablers, challenges and innovations

## What worked and why?

### Blended professionals

A key factor in the success DANCOP has had with surpassing its targets has been the existence of so called ‘blended professionals’ in the delivery teams. Wiggans (2012) noted the need for the right employees; it is important that central project and partner institution teams are comprised from committed, enthusiastic individuals (referred to as blended professionals) with high-level knowledge and expertise and that they were able to operate across boundaries to develop relationships and support collaborative working. There was significant evidence that all the hubs and the central teams were comprised of these individuals.

“recruiting good people from lots of relevant backgrounds with lots of good experiences” Central team manager

The blended professionals themselves very much felt that their perseverance and dedication was a key contributing factor and that they were able to meet targets despite the processes and procedures in place:

“I think the reason DANCOP has been successful is because of the staff that work on it. I think that the staff on the ground have all come in and worked really hard and been really passionate… the people have come into these roles because they're really passionate about young people, they're passionate about education.  Lots of people have left the education system in various different roles knowing that, actually, our education system at the minute isn't working, and young people need something else, they need more support, they need more guidance.  And, you know, schools need that support as well, so I think that's what's made the real sort of difference.” Hub team member

“…across all the hubs, and now the numbers that we're seeing and the relationships with schools and that they're coming to us for activity and booking stuff in, is incredibly positive.  And I don't want to take that away from anyone, but I do think that has happened because of the passion of the people, on the ground.  I think, obviously, with steering group and senior management, there's been some levels of support and some input into that, but also I think there's been at least an equal amount of hindrance to what we've achieved because of the processes and procedures from above.” Hub team member

### Individual development

Hubs reported that the ability of individual team members to develop their own projects, such as mental health first aid instructor and level 6 careers guidance qualification, has meant that they have been able to develop their own skills and knowledge. It has also meant that DANCOP have been able to depend less on third party deliverers over time and make use of their own hubs and central team to deliver a wider range of activities.

### Inclusion

Rotating monthly meetings around the different hub sites which helps to ensure all hubs feel included.

### Hubs, colleges and third parties

One element that has worked, from the perspective of both HEI’s and FEI’s, is having hubs that can deliver a broad range of activities but having capacity to fund third party deliverers who are experts in particular areas, for example Brightside, Causeway, Learn By Design, Performance in Education, STEM specialists, IntoUniversity, Stretch Education and Brilliant Club.

One member of the IPG suggested that their capacity to make use of third party deliverers had been especially helpful

“it's been really nice to see all of the college teams take up a lot of activity with our third-party providers as well…. through my role I can contract third parties to deliver activities that are bespoke that our internal teams wouldn't then be able to do...  And one of the sort of best collaborations, have been where the internal college teams have embraced the third party where you can actually work on that together” IPG member

### Developing a clear offering

As a result of reflection and guidance from OFS, DANCOP have developed a framework of activities which have been mapped against different outcomes and the Gatsby Benchmarks. This has been helpful for schools as it means they understand more clearly the rational for DANCOP, what can be provided and what the associated outcomes should be. Further guidance from OFS means that DANCOP are continuing to develop their offering so that there is a clear set of learning objectives and learner journeys for learners to progress through. This is designed to develop provision and encourage longer term engagement from schools in sustained activities with learners. Deliverers of activities were clear that sustained engagement with learners led to relationships, trust and stronger engagement from the learners.

### Steering group

The steering group was comparatively small (approximately five members) which permitted agility (although it was noted that with a small group size there isn’t room for individuals to be off long term sick and several changes in chairs of the steering group had been challenging). However, the steering group was also comprised from individuals with years of experience and knowledge. This was particularly important for the project manager who did not have this level of experience in widening access.

“But, what steering group bring that I haven’t got is years of experience and participating in developing activities knowing what works, knowing what your pitfalls are going to be, knowing all of the politics and history, etc. That’s the experience they bring and I think it’s invaluable because everyone in the DANCOP team is new ….[they do not have] years and years of experience and participation in this exact format so that’s what they’re for,  I think, is really useful and I will say, no, that doesn’t work, or we’ve been here before. That’s what I get from it that’s really useful.” Manager

### The IPG

The Innovations and Partner Group (IPG) was unique to DANCOP and has been effective in bringing FEI’s into the collaborative partnership and giving them a strong voice as well as capacity to develop new activities. A further positive effect is the development of HEI’s understanding of how FEI’s work and FEI’s have a better understanding of HEI’s.

“It has been effective to watch the interaction between kind of HEIs and FEIs come together to kind of make this work because we do work in kind of different ways, we have different cultures and resources.  So, I think that that has been good for the HEIs, because they've kind of started to understand some of the aspects of FE and colleges and schools, and it's been good for us because we kind of see the kind of bigger picture in terms of destinations and higher education is a whole WP kind of objective.” IPG member

Additionally, the membership of the IPG has allowed them to develop their own bank of knowledge and understanding of ‘what works’, in part through experimenting with new ideas. This has been beneficial for the colleges in a much wider sense because it has developed awareness of issues and solutions to them.

“it's always good to have fresh ideas, actually, this room has the experience of what does work, what doesn't work, we've tried that before, let's not do that, let's try this, we think this is what we need”. IPG member

“that ability to go and try something, because we've got funding for it, actually has driven other parts of the colleges … because to a certain extent it has exposed areas where non DANCOP learners potentially would need support and help as well.  So, I think that's been a kind of big learning thing for us, and I think that would only come about through the kind of structure of the IPG and the steering group and the mix of disciplines and institutions.” IPG member

One final benefit of the IPG is that it has allowed colleges who were later in fully engaging to side step some of the issues encountered by what they have referred to as ‘early adopters’.

“…because we've come to this much later, possibly, than the other two colleges, it's taken us longer to get started, and therefore I can recognise some of the phases that are being described and the benefits of this sort of group, is it allows me to short circuit the learning of other people, so we've benefited immeasurably from the early adopters.” IPG member

### Experimentation

Having the resources to experiment with new activities and test out new approaches has been very well received and has supported the development of knowledge as well as providing what an IPG member referred to as ‘ripple effects’.

“So it's allowed us to probably try things that perhaps within our own resources, we might not have tried.” IPG member

“Yes, I think that's a key benefit to this is the fact that you can try these things, and so having that extra resource allows us to try something and the benefits then kind of filter out, or ripple out from that particular thing” IPG member

For example, one ‘ripple effect’ specified was the support it has provided for existing students within the colleges

“it has allowed us to intervene and harness curriculum resources in a way we probably couldn't have done, without it”

“it's added significant value to both our engagement activity but also our support for students internally, in college”

### DANCOP funded roles

A number of schools were able to use funding to create a role within the school that facilitated learner progression. There was discretion over the exact nature and responsibilities associated with these roles. In some the role was administrative, in others it was both administrative and organizational and in others it was aligned with a careers role. Focus group interviews with the individuals in these roles suggested that funding a role was exceptionally helpful for a number of reasons. Firstly, existing staff in schools do not always have the capacity to communicate effectively with DANCOP. Secondly, they do not have the capacity to complete the administrative elements of working with DANCOP. Thirdly schools do not always have a member of staff with a positive attitude, an understanding of the benefits of outreach and how such activities can support a good career guidance programme. Funding a member of staff whose role subsumes some if not all of these allows schools to engage much more effectively with DANCOP and supports attitude and culture shift more widely in those schools.

### Summary of ‘What works’

The key aspects which were felt to be effective were the recruitment of ‘blended professionals’ (Wiggans, 2012) who were knowledgeable, flexible, enthusiastic and passionate about working with young people. In addition, having a steering group which comprised people with many years of experience and knowledge was also seen to be beneficial.

The IPG was perceived to be particularly effective for college partners because it provided a route for inclusion, a space for experimentation and a mechanism for developing resources and practices that benefitted colleges both with respect to DANCOP learners and more widely.

The capacity to develop hubs and have delivery teams which could deliver a breadth of activities was beneficial, however, the capacity to bring in specialist third party providers was essential and benefitted all partners within the collaborative network.

DANCOP funded roles in schools provided much needed capacity and improved communication and relationships.

## Challenges

### Starting from new

DANCOP, although theoretically a continuation and development of NEMCON, was a new development. It did not retain any of the NEMCON staff or features which meant that all the roles of the collaborative partnership (central team, hubs etc.) needed to be recruited and established - this took a long time because of the processes inherent in FE’s and HE’s (for example HR, legal, finance), the short term nature and ambiguity of contract length, uncompetitive salaries in FEI’s and because of contextual factors in play at the time such as redundancies in some of the FEI’s. This meant that DANCOP had significant targets to hit but with very few members of staff in place. For one hub this was still an issue in phase 2, although despite these difficulties DANCOP had in fact surpassed its targets by a significant extent.

### OFS

#### spending requirements and funding periods

OFS requirements regarding spending over time periods meant that DANCOP had only a small number of staff in post but had significant spending requirements and targets to reach. Consequently, there was a small, new, collaborative partnership with funding to be spent but that had few, if any, relationships with the schools. Furthermore, schools did not know about DANCOP, its aims and objectives, or what it could offer. It is well known that establishing relationships with schools is difficult, in part because of the great number of other organisations also trying to do this and partly because of the heavy workload of staff in schools. It requires persistence and therefore takes time.

DANCOP’s work in those first months centred round trying to establish relationships with schools. This involved establishing a single point of contact, trying to raise their awareness of DANCOP’s role and offer and crucially trying to gain an understanding from schools of what they needed with respect to widening access. Per OFS requirements, DANCOP needed to spend their allocated funding. In order to achieve this schools were able to request, (and for the most part received), funding for a wide range of different activities, third party offerings and practical costs such as transport. This was beneficial in some ways because it allowed DANCOP to understand the needs and barriers schools have and face. However, when DANCOP then moved to offering a framework of provision it meant that schools who had previously been told that DANCOP wanted to know what they needed, were then told that they could only access those activities within the DANCOP framework. This was a barrier for some hub/school relationships - the move from school driven requirements to DANCOP driven frameworks, which wasn’t coupled with extra funding to support the greater number of schools who were now engaged, meant that there was disappointment and frustration on behalf of both schools and hub team members who had spent time nurturing these relationships. It is important to note that over time a standardised framework of provision, which was mapped against the Gatsby Benchmarks, has been enabling and is an important progression.

#### Funding clarity

The first issue that arises with respect to funding is the lack of clarity from the OFS. This has been a significant barrier in the development of DANCOP as a high performance team and in the delivery of activities. In the first instance, the ambiguity of whether funding would be made available for DANCOP to be extended, of how much funding would be made available and when it would be made available has had two critical, deleterious impacts. Firstly, it has led to uncertainty and job insecurity amongst hub, college and central team members; these are psychological states that are commonly associated with reduced motivation, dissatisfaction, increased intention to quit and reduced intention, and there were clear indicators of these in DANCOP team members. All of these impacts undermine a team’s ability to perform at its highest level.

“But the impact of that on staffing, as I’m sure you’ll be aware, is huge not just for me managing those but the impact on the team more generally and nobody can do anything about it” Central team manager

Secondly it has impacted significantly on what DANCOP have been able to approve in funding to schools. At the outset there were fewer schools engaged, there were significant amounts of funding which needed to be spent and a wider range of requests were considered. As DANCOP moved into the second phase of delivery where funding was more ambiguous and less available, a smaller range of requests have been possible. For example, transport to activities could be funded in phase 1 but has not always been available in phase 2. Since transport to activities and events is a key barrier for schools in engaging in trips and visits, this has a significant impact on their ability to visit HEI’s, FEI’s and other exhibitions and events. Some schools did raise the ambiguity of funding as an issue and expressed frustration, but the impact was more keenly felt by the hub team members.

#### OFS, Postcodes and Geography

Generally, it has been problematic for some schools to engage because they may not have had enough DANCOP learners. Specifically, however, one hub has experienced an unanticipated problem whereby they had learners attending schools within DANCOP’s remit but who had a postcode from a different NCOP. This has meant that DANCOP were not able to fund them but likewise the other NCOP could not because they attend a school in DANCOP’s remit.

### Working with schools

#### Communication and relationships with schools

Communicating with schools and developing relationships is difficult for any organisation seeking to provide schools with a service. It can be difficult to know who to reach out to initially as each school has unique structures, roles and responsibilities. This can be problematic further into the relationship as well. The roles of the individual who DANCOP liaise with vary significantly and this has meant that some opportunities which DANCOP offer to schools are missed because the individual within the school is too busy to read the emails (e.g. SLT) or does not have the power to make that decision:

“… has no budgetary power, no SLT, or anything like that, but might be really keen, it might be, we've got a few assistant heads, members of SLT, and they've got, sort of got the opposite problem that, if they get something and they see it and they make a decision, it's like that, but they might not have the time to read your emails, and everything like that.  So, the people that we deal with vary significantly, and their sort of power within the school varies quite a lot, which has made things harder, and I think some people just, you get back to them, you say "what about this?" and they're like "I sent it out to SLT, I've sent it to all the heads of year, I've had nothing back" and it's like, well what can you do?”

Maintaining relationships can then be challenging because communication continues to be problematic. Whilst some staff in schools will be able to respond to emails, it is not uncommon for others to not respond all or some of the time. This can lead to missed opportunities:

“Our main school didn't take that up [Morocco World Challenge trip] and then when you said “we can't do that because we've been camping or going to Morocco then” or whatever, and they were like "Oh why aren't our kids going on that?"  "We sent you so many emails, no one replied, no one was bothered about going."

“Yes, and that particular person was, "that's a shame, because that would have been a really good opportunity for our kids."  We thought, yes, we know.  But it's just so, that's the problem”

“So, it's quite hit and miss with what response you get and I suppose we never really know when is the perfect time to email a teacher or a staff member and there probably isn't one.”

Other difficulties that DANCOP faced included the competition between colleges and hubs – it has been confusing for some schools knowing what the difference is between colleges, DANCOP hubs, DANCOP funded roles in colleges and so on. Schools have on occasion not known who to contact for what. Furthermore, the time taken to approve funding has made maintenance of relationships difficult in some cases. Finally, the issue of GDPR has made it difficult to work with some schools. Nonetheless hub members did report that the majority of schools they worked with had positive relationships with them.

#### School and staff attitudes and attributes

One hub had noted that to some extent funding for schools was available in a ‘first come, first served’ manner. This had meant that those schools who were quick of the mark in being able to recognise the potential opportunities on offer through DANCOP and are really well organised had been able to request, and receive, more funding than those who were struggling, but in fact may need the support more:

“I don't think the system of doing it has been very fair because we've had schools that have got their act together… we've got one outstanding school who has been really good at getting in…. you can tell, when you work with them, the level of organisation, the spreadsheets that they'll send you, they're tracking everything and they know exactly, they've got their whole year planned out and they'll send you that at the beginning and they want to know, where you can fit in… And then you've got other schools that aren't but they almost need the support more because of the fact they've got no one dedicated to that and they're not accessing any support with other organisations, but they miss out because there's no one to submit funding requests.”

Some have also noted there are differences in attitudes between teaching and SLT staff which means that DANCOP and schools have missed out on opportunities:

“Yes, and they miss opportunities, so I know that one of my schools really wanted the STEM bus, and you tried really hard to work with the science teachers and get things, and the head of the year, no deputy head of school, was, "why didn't we get this?" it's well, "because your teachers didn't want it."  And she was really disappointed, wasn't she?”

The lack of capacity and an appropriate liaison within some schools might be relieved through funding a role within that school. There were a number of these roles developed across schools whose remit included administration, coordination, liaising with DANCOP and raising aspirations, depending on what the school needed. Focus group discussions with the individuals holding these roles suggested that communication between DANCOP and these schools was more effective and that schools were able to take more of the opportunities offed from DANCOP.

### DANCOP Structures and processes

#### The funding application process

The problems caused by the ambiguity of funding from OFS have been further exacerbated by the application processes in place within DANCOP. Schools or organisations applying for funding must complete the application form which is then submitted to the hub or team which the school is affiliated with. From the hub it is submitted to one of two managers who then pass it to the project manager who takes the application to the next steering group meeting. The application is considered at the steering group who may approve, ask for clarification or reject. If the application requires clarification it goes back down through the project manager, to the hub and then to the school. This process can take a significant amount of time by which point the school may have missed out on an activity. Not only have schools missed out on activities but their frustration with the process has meant that relationship building has been more difficult:

“Or it's passed deadlines, I've had schools who are like "we can go on this trip, or we can do this, by the end of the month, or two weeks' time" and they'll be emailing us "have you had a response yet?" and I have to go "really sorry, no, I'll chase it up" and there's not much you can do but it does ruin the relationship with schools quite a lot.  We've definitely had one school that I don't think want to work with us because things took so long.”                          Hub team member

In other situations schools have submitted fairly routine requests which have then been turned down:

“…so they might request something that is fairly standard, like "we would like transport to a university" and you're like "yes, that's pretty standard" so you sort of let them know, they want a yes or no answer, but you can't give them a yes or no answer, you sort of have to say, "in theory yes, like this sort of request is fine, I've raised a purchase order for it, but until you receive that, it's not confirmed."  But then occasionally they've booked the transport, gone on it, or booked whatever it is, gone on it and everything and then if something has happened with the POR, someone has forgotten to raise it or something has got delayed at one point, then like Derby can turn round and say "no, we're not paying that" and that's quite hard for us, because we're the face of the relationships with the school and you don't want to ruin that.  And it might only be a few hundred pounds, but schools don't even have that spare cash at all.” Hub team member

The managers within the central team were aware of the faults in the decision making process and had considered alternative approaches. They expressed a need for upskilling and decision making processes to be amended:

“[the project manager] is not a budget holder... we actually don’t have the power to spend any money. So everything goes through steering, it’s like another layer. So sometimes certainly for our project officers or for my team they will have to ask us for something and they will have to ask the project manager for something and she needs to – can technically approve it but not really and then steering has to approve it and it comes all the way back down. So I think if there was more autonomy not only just for us, I don’t feel, but almost upskilling the lead project officers even more…. but current processes sort of almost hinder that a little bit and sort of hinder some of our process decision making, don’t they? Because we know what decision we want to make but we’re not in the power to make it, almost. So, I guess, if we had total free reign I think that would speed everything up. And I know that that’s a definite frustration from teams. The nature of DANCOP is short term and so processes need to be fast because there is not time to behave so slowly”. Central team manager

The application process also suffers from a lack of clarity regarding what is required. Hubs indicated that the levels and sorts of information required on the application form weren’t particularly clear so applications had been sent back asking for details that could have been provided in the first draft. Related to this was a problem with ambiguity surrounding what could be funded as this had changed from phase 1 and wasn’t necessarily well articulated. Wiggans (2012) states that there is a need for clear communication regarding allocation of funding for collaborative partnerships to be able to operate effectively and there are indications here that there is room for improvement regarding the clarity and dissemination of such information. Wiggans also notes that the structural approach to decision making and collaboration has to be right in balancing devolving responsibility for delivery to institutes and achieving accountability for the use and impact of funding (Wiggans, 2012). There was also evidence that this might not be optimal in DANCOP with all responsibility for delivery devolved to the hubs and central teams but funding decision making and accountability being centralised.

### Crossover and competition

Whilst there has been no crossover or competition between the three hubs, there has been between the college partners and individual institute widening access teams. Some schools may have had three separate team sending three sets of messages out regarding activities.

“It's been confusing because I think the colleges weren't given any guidance to start with.  So, when I like originally got this role and I was like first in post, I was told there are eight DANCOP roles at the college and the college that, and there are, but they're DANCOP funded, some of them aren't DANCOP roles, but they call them DANCOP in the job title, so then when they email the school and they say I'm DANCOP, they think that they're the same as us and that's been really confusing.” Hub team member

The hubs have worked with individual institute widening access teams and this collaborative approach has worked:

It does work well with the outreach team.  So, for example, if schools at Ashfield which are huge schools, we've just both gone in and done sessions together so we can cover the whole year group with enough of us from each team.” Hub team member

Nonetheless differentiating teams and offerings for schools has been very difficult:

“..we try to clarify with schools, I know that recently the college teams have tried to be a bit more different, they've said this is what we do, this is what they do, DANCOP have got the money, we don't, and tried to explain things, its better, and I know we have as well, but some schools still don't get it do they?  And it's, can be quite difficult, I'd say it is pretty endemic isn't it?” Hub team member

Competition between college DANCOP roles or widening access teams and hubs exists:

“We've got similar programmes of activity which is quite hard, so in September, going into schools it was kind of a bit of like, who could arrange their meeting first?  … so, we've got schools we're struggling to work with because they've filled all their PSHE slots, or drop-down day slots with other stuff.  As well as the fact that they already work, probably already work with the local universities, which in this area would be Derby, Nottingham, Trent, Sheffield and Hallam, so we cover, we've got quite a big range of universities in a small area.” Hub team member

### Communication and coordination

Wiggans (2012) noted that effective collaborative partnerships have a sound partnership infrastructure with regular communication and coordinated processes which facilitate the engagement of learners with progression. The coordination of DANCOP activities and the communication of these to schools has not always been able to facilitate learner engagement – activities either have from time to time been coordinated too late or the communications regarding these have sometimes been too late for schools to be able to respond. There was a clear need for DANCOP to take a more proactive role with a planned timetable events as opposed to a reactive stance.

“.. being more organised, as well, because I feel like everything we send to schools, the deadline is too tight, it's too tight for them, we don't ever give them enough time… it's always like "oh there's this amazing opportunity, could you get back to us by the end of the week?  Or get back to us by the end of next week?"  It's just not realistic, we need to be giving schools a couple of months' notice and then sending the emails nearer the time… And, at the beginning of the year, so they're planning everything in, so if they're going to take kids out of school that they've got all of that… and if we'd got at least some key dates in… they can be planning that over the summer and in September they can book the whole year in, in theory.  That would be so much better.” Hub team member

As the collaborative partnership has grown from a small core team to over 50 members of staff, there has been a move from more informal methods of communication between the central and hubs teams to a need for more formal mechanisms with clearly articulated processes, procedures and channels. This is important when there are hub teams out with the central team and for effective collaboration. Whilst there have been attempts to formulate and implement these, they have not always been either well understood by all or indeed followed by all. Primarily this arises because:

  - A large number of original team members are homed together in the lead institute and so are able to engage in informal communication methods

  - Job roles have changed as DANCOP has grown with some staff changing roles completely (for example from administration to communications). Often these changes in job roles are not understood by all in the team.

### Summary of challenges

The key challenges that DANCOP have faced are unlikely to be unique to them:

- Short funding cycle programmes which don’t consider:

  - The time required to set up a complex collaborative partnership

  - The time required to recruit in FEI’s and HEI’s

  - The time required to establish and develop relationships with schools

  - The fact that schools have little time in the curriculum and have often planned activities a year in advance

- Uncertainty regarding length of the programme and funding amounts which:

  - Have a negative impact on staff

  - Have a negative impact on the relationships with schools

  - Reduce the number of activities which can be delivered

- Organisational/institutional level difficulties:

  - Support systems which are not fit for purpose and cause delays

  - Differences in employment practices which result in inequity and dissatisfaction

  - Differences in strategic objectives which may reduce sustainability

- Collaborative partnership structures and developing which facilitates decision making and communication

- Working with schools

  - They have little capacity to engage and can be difficult to communicate with

  - Work to different time lines

  - Have unique structures, roles and responsibilities

  - Have different requirements

## Innovations

### Network/collaboration

#### The LEP and the Opportunity ARea

Including in the network a representative from the LEP has proven to be extremely helpful. The broader view that this person can bring to the partnership has helped DANCOP identify gaps in WA provision rather than duplicating what is already there. Additionally, an enterprise advisor from the Careers and Enterprise Company has provided input which has been beneficial to DANCOP. Derby was given Opportunity Area (OA) status and allocated funding. There has been some overlap between the projects the OA wish to deliver and those of DANCOP but the two programmes have met and will work with each other where possible.

#### Pipeline Development

Colleges are focusing on educational pathways for development to create pipelines from FE into HE. This is involving consideration of FE curricula structure and content and development of these in terms of adding value through WA inclusion as opposed to creating new programmes.

#### Hub Embedding

DANCOP partner members have been able in some instances to go and embed themselves within other hubs to experience how different teams work and are managed.

### Activities

A number of potentially innovative projects have been funded particularly from colleges (Stephenson College’s lab kit; the STEM Centre).

The STEM bus was perceived to be unique and effective.

#### FE study skills coaches

These are institution posts which the IPG feel have been required within the FE sector for some time.

“They have made such a huge impact, they really have”. IPG member

“there are various parts of the pipeline where you intervene to make a difference, I think has been very useful.  And I think we've done it relatively well.” IPG member

### SUMMARY of innovations

The main way in which DANCOP has been innovative is through the development of the IPG which has facilitated inclusion of colleges in the partnership and reciprocal learning from HEI’s and FEI’s. There were a number of trialed activities which were novel and innovative but the key aspects have been longer term resources being developed such as the STEM Centre and the FE study skills coaches which have been perceived as being hugely effective and impactful.

# Conclusions

- The network is well established amongst the HEI’s, external stakeholders and FE colleges and has worked with a vast number of schools and learners which outstrips the targets set.

- It has taken DANCOP a long time to establish all its teams and roles, partly because of the policies and processes inherent in HEI’s and FE’s and partly because of the ambiguity in contract length.

- It has taken a long time to build awareness in schools and develop good working relationships so that activities can be delivered. Progress made has been jeopardised by ambiguity in funding provision

- DANCOP could work more quickly if legal and financial issues and executive sign off could be facilitated.

- Schools have missed out on some opportunities because of communication problems, school attitudes and attributes, decision making processes and lead time being too short

- Collaborative work has been supported by:

  - Representation of key partners across different management groups, in particular the IPG has permitted colleges to develop some innovative and effective schemes and input significantly to DANCOP

  - The structural and physical location of teams and individuals

  - An agile SG

  - ‘Blended Professionals’ who have significant experience, knowledge and skills and are able to cross boundaries to get work done

  - Differentiation of provision between DANCOP, colleges and universities over time

  - DANCOP funded roles in schools

- The factors which have made collaborative work difficult are not unique to DANCOP and stem largely from the nature of NCOP and OFS timelines, differences between institutions, poor supporting services and working with schools. They have been found by CFE in their interim evaluation of NCOP and elsewhere (e.g. Wiggans, 2012).

- Despite being a new collaboration and the difficulties described above, DANCOP has worked with all of the target schools and surpassed targets with respect to school and learner interactions

- Feedback from learners, teachers, staff in DANCOP funded roles and parents has typically been very positive with activities seen to be ‘excellent’, relevant, effective and to have value. The activities, in the short term at least, have a favourable impact on levels of knowledge, confidence, intentions to attend and motivation to work hard.

- Comparisons to non DANCOP learners suggest that DANCOP learners demonstrate a significant and positive change to aspirations, confidence, motivation, academic fit and knowledge of a range of aspects of HE.

# Recommendations

- Funding cycles for programmes such as NCOP need to be funded unambiguously for longer timeframes in order for:

  - Schools to develop a sound understanding of the programme and understand the opportunities they offer

  - Programme teams to develop effective working relationships with them

  - Programme teams to recruit, develop and retain the blended professionals that do most of the front line work with schools and learners

  - Sustained programmes of delivery to be available

  - Medium and long term outcomes to be assessed to identify longer term impacts

- Collaborative partnerships need supporting services that are fit for purpose; legal, financial and HR support needs to be agile.

- Employment contracts need to be owned by one central institute to ensure equity in employment in geographically or institute disparate hubs and teams. This would also support recruitment, particularly for roles housed in colleges.

- The level of responsibility and control with respect to provision of funding needs careful consideration. If centralised, then the mechanism for application of funding needs to be very clear, needs to be well communicated and must be agile.

- Colleges and hubs need to consider how to integrate their team members both within the institution (i.e. located structurally and physically within appropriate departments) and with each other to facilitate support, communication and collaboration.

- DANCOP funded roles in schools provide the school with capacity, expertise, or both, and provides an effective communication link to DANCOP. This model may be more effective than trying to establish a relationship with an individual in a school or may either miss opportunities because they are too busy to read emails or may miss opportunities because they do not have control over such decisions.

- Hubs can deliver a wide range of activities but frequently are not specialists in particular subjects (e.g. STEM). Where expertise is required in the delivery of activities, third parties should be used.

# References

Anderson, D.S. & Vernoon, A.E. (1983) Access to Privilege: patterns of participation in Australian post secondary education (Canberra), ANU Pres

Appadurai, A. (2004). The capacity to aspire. Culture and public action, 59-84. In D. Held & H. L. Moore with K. Young (Eds) Cultural politics in a global age: Ucertainty, Solidarity and Innovation. One World Press, Oxford.

Archer, L., Hollingworth, S. & Halsall, A. (2007) University's not for Me—I'm a Nike Person': Urban, Working-Class Young People's Negotiations of Style', Identity and Educational Engagement. Sociology, 41(2), pp.219-237.

Baars, S., Mulcahy, E., & Bernardes, E. (2016). The underrepresentation of white working class boys in higher education - the role of widening participation. Retrieved from https://www.lkmco.org/wp-content/uploads/ 2016/07/The-underrepresentation-of-white-working-class-boys-in-higher-education-baars-et-al-2016.pdf

Bok, D. (2010). The politics of happiness: What government can learn from the new research on well-being. Princeton University Press.

Booth, J. (2007) A rough guide to working in partnership, for Aimhigher Nottinghamshire. Aimhigher. Available from: http://www.heacademy.ac.uk/resources/detail/aim_higher/AHNotts_rough_guide_working_partnership.

Bourdieu, P. (1985). The genesis of the concepts of habitus and field. Sociocriticism, 2(2), 11-24.

Bourdieu, P., & Wacquant, L. (1992). Réponses. Paris: Seuil, 4.

Conlon, G., & Chevalier, A. (2003). Does it pay to attend a prestigious university? Centre for the Economics of Education (CEE) Discussion Paper, P0033.

Chowdry, H., Crawford, C., Dearden, L., Goodman, A., & Vignoles, A. (2013). Widening participation in higher education: analysis using linked administrative data. Journal of the Royal Statistical Society: Series A (Statistics in Society), 176(2), 431-457.

Connor, H. (2001). Deciding for or against participation in higher education: the views of young people from lower social class backgrounds. Higher Education Quarterly, 55(2), 204-224.

Cunningham, R., & Lewis, K. (2012). NFER Teacher Voice Omnibus February 2012 Survey: School Reform, Job Satisfaction, Performance Management, and Oxbridge. London: The National Foundation for Educational Research/The Sutton Trust.

DANCOP (2018) Derbyshire and Nottinghamshire Collaborative Outreach Programme. Accessed May 2018 [www.teamDANCOP.co.uk/about/]

Department for Business, Innovation & Skills (2011) Guidance to the Director of Fair Access. [https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/32404/11-728-guidance-to-director-fair-access.pdf

Department for Education (2017) Securing learner success: risk based regulation for teaching excellence, social mobility and informed choice in higher education.  Accessed May 2018. [https://consult.education.gov.uk/higher-education/higher-education-regulatory-framework/supporting_documents/B%20Regulatory%20Framework%20consultation%20guidance%20FINAL%2018%20October.pdf]

Department for Education (2017) Unlocking talent, fulfilling potential: A plan for improving social mobility through education. Accessed May 018. [https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/667690/Social_Mobility_Action_Plan_-_for_printing.pdf]

Dhillon, J. K. (2013). Senior managers’ perspectives of leading and managing effective, sustainable and successful partnerships. Educational Management Administration & Leadership, 41(6), 736-750.

Diamond, A., Roberts, J., Vorley, T., Birkin, G., Evans, J., Sheen, J. & Nathwani, T. (2014). UK Review of the provision of information about higher education: Advisory study and literature review. Report to the UK higher education funding bodies by CFE Research. Available at: http://dera.ioe.ac.uk/19857/1/2014_infoadvisory.pdf

Education Policy Institute (2018) Educational disadvantage: How does England compare? London. Accessed May 2018 [https://epi.org.uk/wp-content/uploads/2018/04/Educational-Disadvantage-England-EPI-IOE.pdf]

EKOS consulting. (2007) Aimhigher area studies: Final report to HEFCE, April.

Gale, T., Hattam, R., Comber, B., Tranter, D., Bills, D., Sellar, S., & Parker, S. (2010). Interventions early in school as a means to improve higher education outcomes for disadvantaged learners. National Centre for Learner Equity in Higher Education.

Gao, F., & Ng, J. C. K. (2017). Studying parental involvement and university access and choice: An ‘interacting multiple capitals’ model. British Educational Research Journal.

Gorard, S., Smith, E., May, H., Thomas, L., Adnett, N. & Slack, K. (2006). Review of Widening Participation Research: Addressing the Barriers to Participation in Higher Education. London: HEFCE.

Harker, R., (1990) "Education and Cultural Capital" in Harker, R., Mahar, C., & Wilkes, C., (eds) (1990) An Introduction to the Work of Pierre Bourdieu: the practice of theory, Macmillan Press, London

Harrison, N. & Hatt, S. (2012) Expensive and failing? The role of learner bursaries in widening participation and fair access in England. Studies in Higher Education, 37(6), pp.695-712.

Harvill, Eleanor L., Rebecca A. Maynard, Hoa T. Nguyen, Claire Robertson-Kraft, and Namrata Tognatta. 2012. “Effects of College Access Programs on College Readiness and Enrollment: A Meta-Analysis.” 142 Reports - Evaluative. Society for Research on Educational Effectiveness. 2040 Sheridan Road, Evanston, IL 60208. 1011395740; ED530404. ERIC.http://search.proquest.com/professional/docview/1011395740?accountid=14533

Hayton, A., & Bengry-Howell, A. (2016). Theory, evaluation, and practice in widening participation: A framework approach to assessing impact. London Review of Education, 14(3), 41-53.

Hayton, A., Mackintosh, M., & Warwick, E. (2017) Theory, Practice & Impact in Widening Participation: A praxis based framework. Access to Higher Education and Learner Success Summit 2017

Iftikhar, H., McNally, S., & Telhaj, S.  (2009) University Quality and Graduate Wages in the UK. Centre for Economics of Education.

Kendall, L. (2005). Excellence in cities: The national evaluation of a policy to raise standards in urban schools 2000-2003. Department for Education and Skills

Kettley, N.C. & Whitehead, J.M. (2012) Remapping the “landscape of choice”: patterns of social class convergence in the psycho-social factors shaping the higher education choice process. Educational Review, 64(4), pp.493-510.

Morris, M., Golden, S., Ireland, E., & Judkins, M. (2005). Evaluation of Aimhigher: Excellence Challenge: The views of partnership coordinators 2004. National Fund for Educational Research/Department for Education and Skills

Moore, L. J. Sanders and L. Higham 2013. Literature Review of Research into Widening Participation to Higher Education. Report to HEFCE and OFFA by ARC Network

Office For Learners (2018) National Collaborative Outreach Programme Accessed May, 2018. [https://www.officeforlearners.org.uk/advice-and-guidance/promoting-equal-opportunities/national-collaborative-outreach-programme-ncop/]

OECD (2005), Education at a Glance 2005: OECD Indicators, OECD Publishing, Paris, [http://dx.doi.org/10.1787/eag-2005-en]

Passy, R., & Morris, M. (2010). Evaluation of AimHigher: learner attainment and progression. Final report. Slough: NFER.

Perna, L.W. & Titus, M.A. (2005). The relationship between parental involvement as social capital and college enrollment: An examination of racial/ethnic group differences. The Journal of Higher Education, 76(5), pp.485-518.

Reay, D. (1998) ’Always knowing’ and ‘never being sure’: familial and institutional habituses and higher education choice. Journal of Education Policy, 13(4), pp.519-529.

Reay, D., David, M.E. & Ball, S.J. (2005) Degrees of choice: Class, race, gender and higher education. Stoke-On-Trent: Trentham Books.

Reed, R., King, A., & Whiteford, G. (2015). Re-conceptualising sustainable widening participation: evaluation, collaboration and evolution. Higher Education Research & Development, 34(2), 383-396.

See, Beng Huat, Gorard, S., & Torgerson, C. (2012). “Promoting Post-16 Participation of Ethnic Minority Learners from Disadvantaged Backgrounds: A Systematic Review of the Most Promising Interventions.” Research in Post-Compulsory Education, 17: 409–422.

Stevenson, J., McCaig, C., & Madriaga, M. (2017). Evaluation of the National Networks for Collaborative Outreach (NNCOs). HEFCE

Sutton Trust (2010) Higher Education access: Evidence of effectiveness of university access strategies and approaches. Accessed May 2018 [https://www.suttontrust.com/wp-content/uploads/2015/12/Higher-Education-Access-Report-1.pdf]

Torgerson, C., Gorard, S., Low,G., See, B.H., & Wright, K. (2008) What Are the Factors That Promote High Post-16 Participation of Many Minority Ethnic Groups? A Focused Review of the UK-Based Aspirations Literature. Social Science Research Unit, Institute of Education, University of London

Vignoles, A., & Murray, N. (2016). Widening participation in higher education. Educ. Sci., 6(2), 13.

West, A., Hind, A., & Pennell, H. (2005). Evaluation of AimHigher: Excellence Challenge: first survey of opportunity bursary applicants 2002/03: preliminary findings. Department for Education and Skills

What Works Clearinghouse. 2011. “Procedures and Standards Handbook (Version 2.1).” What Works Clearinghouse.http://ies.ed.gov/ncee/wwc/Docs/referenceresources/wwc_procedures_v2_1_standards_handbook.pdf

Whitty, G., Hayton, A., & Tang, S. (2015). Who you know, what you know and knowing the ropes: a review of evidence about access to higher education institutions in England. Review of Education, 3(1), 27-67.

Wiggans, J. (2012) Collaboration and partnership working in a competitive environment: A literature synthesis of the Widening Access, Learner Retention and Success National Programmes Archive. The Higher Education Academy [https://www.heacademy.ac.uk/knowledge-hub/collaboration-and-partnership-working-competitive-environment-literature-synthesis]

Wilkins, A., & Burke, P. J. (2015). Widening participation in higher education: the role of professional and social class identities and commitments. British Journal of Sociology of Education, 36(3), 434-452.

Wilshaw, M. (2016) High performing multi-academy trusts. Accessed May 2018 [https://www.gov.uk/government/speeches/hmcis-monthly-commentary-october-2016]

Younger, K., Gascoine, L., Menzies, V., & Torgerson, C. (2018). A systematic review of evidence on the effectiveness of interventions and strategies for widening participation in higher education. Journal of Further and Higher Education, 1-32.

www.gov.uk

http://www.smf.co.uk/publications/widening-participation/

# Appendices

## Focus Group Schedule (Think for the future mentoring)

- Can you tell us about the things you have been doing with Think for the future?

- What made you want to be involved?

- How do you feel about what you have been doing? For example has it been enjoyable? Boring? Scary? Difficult?

- What have you learned about yourself? Have you learned anything else?

- Have you thought more about your future since taking part?

- What sorts of thoughts do you now have about your future? Are these different to what you thought before you took part in these activities? How so?

- When you think about your future, how do you feel? For example do you feel happy, sad, scared, excited, worried?

- How likely do you think it is you can achieve what you want to?

- How likely do you think it is you will get grade C’s or above in your GCSE’s?

- How likely do you think it is that you will go on to do A Levels?

- How important do you think it is for you to do well in these exams or other qualifications?

- Do you think you might rather go into higher education (at a university, college or as a higher level or degree apprentice) than go straight into work after school or college?

- How much do you know about college, university and apprenticeships? Would you like to know more?

- If you could describe the Think for the Future mentoring programme in three words, what would they be?

## Interview Questions for the central project team/committees

### The Steering Group

- What are the primary aims and functions of the steering group?

- To what extent do you feel these are being met effectively?

- What are the relationships and lines of communication between yourselves and the other groups?

- What are the key issues and priorities that have been identified by the steering group?

- What have been the challenges in agreeing targets and apportioning funding?

- Have the number and timing of meetings been appropriate for the project?

- How did you decide what the central team needed to be comprised of?

- How did you set the central team up?

- What issues and challenges did you face when doing this?

- What progress do you feel DANCOP is making so far? How has it developed or expanded on what NEMCON had achieved?

- What has your role been in supporting the central team and how do you effectively do you feel they are working so far?

- What do you perceive the benefits and value of the programme to be so far?

- To what extent do you think the network has enabled economies of scale, efficiencies in operations and services and reduced duplication?

- What are the key issues or challenges that have been identified?

- How have you dealt with these?

- Overall what have been the key lessons learned?

### The Governance Board

- What are the primary functions and aims of the governance board and what progress do you feel you are making?

- What are the key issues and priorities that have been identified by the governance board?

- What are the lines of communication within the group and between yourselves and other groups?

- What kinds of support are you providing for the central project team and how effective do you think they are?

- What feedback and/or support have you provided regarding implementations of plans and progress against targets?

- What progress do you feel DANCOP is making so far? How has it developed or expanded on what NEMCON had achieved?

- What do you perceive the benefits and value of the programme to be so far?

- What are the main challenges that you have faced so far?

- How have you dealt with these?

- Overall what have been the key lessons learned?

### Innovations and Partner Group

- Who makes up the Innovations and Partner Group?

- What are the primary functions and aims of the IPG? What progress do you feel you are making?

- How often do you meet?

- What are the lines of communication within the group and with other project groups?

- What progress do you feel DANCOP is making so far? How has it developed or expanded on what NEMCON had achieved?

- How have small scale activities been identified and selected for funding?

- How have educational pathways for development been identified and selected?

- What new approaches to activities and collaboration have been developed and trialled?

- What do you perceive the benefits and value of the programme to be so far?

- What are the key issues or challenges that have been identified?

- How have you dealt with these?

- Overall what have been the key lessons learned?

### Central Project Team

- How was the central team established?

- What are the primary functions and aims of the central project team and what progress do you feel you are making?

- What other roles and responsibilities have come about since the programme was started?

- Who is now in the DANCOP network (groups, partners, providers, LEP’s, LA’s)

- What are the key features and characteristics of the DANCOP network? Are they different to NEMCON? What has been retained? What has been developed?

- What roles have the steering committee, governance board, IPG and operations group played in supporting the central team and how effective do you think they’ve been?

- What roles have the partner institutes played? (have they all been effective/equally distributed/some been more important than others?)

- What has been the division of roles been between partners, hubs and the central project team? How have you communicated and avoided duplication of work? What have the hubs enabled the programme to achieve?

- Do you think the network has enabled any economies of scale, efficiencies in operations and service, and reduction of duplication?

- To what extent has the network developed and piloted any innovative approaches to collaboration and outreach?

- What has the IPG’s role been in this?

- What processes did you use to contact the schools and encourage them to take part?

- What has the feedback from schools been so far? What appears to have been best received?

- In what ways has the outreach programme extended into remote areas and extended its diversity? Do you think this was effective?

- What has been the interplay/partnership between the HE/FE providers and the third party activity providers? Do you think they have complimented each other? Have the resources been distributed and used to their full potential?

- To what extent have deadlines been met to date?

- What have been the main strengths of the partnership so far?

- Have there been any challenges/issues so far?

- What could be further developed? How could this be achieved?

- How sustainable do you think the programme is?

### Hub Teams

- How have the hub teams been established?

- What are the primary functions and aims of the hub teams and what progress do you feel you are making?

- What other roles and responsibilities have come about since the hub team has started?

- Who in the DANCOP network (groups, partners, providers, LEP’s, LA’s) do you primarily work with?

- What roles have the steering committee, governance board, IPG, operations group and central project team played in supporting you and how effective do you think they’ve been?

- What sorts of interactions have you had with partner institutes?

- What has been the division of roles been between partners, hubs and the central project team?

- How have you communicated?

- What have the hubs enabled the programme to achieve?

- Do you think the network has enabled any economies of scale, efficiencies in operations and service, and reduction of duplication?

- To what extent has the network developed and piloted any innovative approaches to collaboration and outreach?

- What has the IPG’s role been in this?

- What processes did you use to contact the schools and encourage them to take part?

- What has the feedback from schools been so far? What appears to have been best received?

- In what ways has the outreach programme extended into remote areas and extended its diversity? Do you think this was effective?

- Have there been any challenges/issues so far?

- What could be further developed? How could this be achieved?

- How sustainable do you think the programme is?

### Interview/Questionnaire Questions for Teachers (and HE Progression Officers –not yet implemented)

- How were you approached and encouraged to take up DANCOP activities?

- What is your rationale for engaging with DANCOP activities? Does it align with school strategy/careers strategy etc)

- What activities have you engaged with and with which age groups/learners?

- How did you perceive the activities in terms of:

  - Relevance

  - Interest

  - Delivery

  - Effectiveness in achieving their aims

- How would you describe the learners who have taken part in the activities? (age, gender, SES, engagement with school, ability)

- What kind of attitudes do you think they had before the activities towards studying further after school?

- What kinds of aspirations do you think they had? How do you know?

- What kind of opportunities had they had before to learn about different career options and progression into HE?

- Did many of them know and understand what FE and HE are?

- Do you think any of the following have changed as a result of taking part in the activities?:

  - Attitudes (become more positive)

  - Aspirations

  - Motivation to attain

  - Knowledge of career options and progression into HE

- How do you know?

- What do you consider the value of this scheme to be?

- What have been the difficulties in working with DANCOP?

- What would you do think could be done differently?

- Have you been able to put a progression officer in place?

- Have you been able to produce a development plan?

  - Was this done on time?

  - How did you go about doing this?

  - What issues or challenges did you encounter?

  - What worked well?

  - What would you do differently next time?

- To what extent have the development plans been effectively constructed and deployed to your satisfaction?

  - How has this been done well?

  - How could it have been done more effectively?

- To what extent do you think the development plan targets have been met?

- Why do you think that has happened?

### Interview schedule for activity providers

- What is your organisation and what are its primary aims?

- What is your role?

- How long have you been working in this role?

- How has your involvement in DANCOP come about?

- Who have you worked with in DANCOP central team/hubs and have you worked with other partners in the network?

- Have you had any input/dealings from the Innovations and Partners Group?

- Have you developed/trialled any new approaches to outreach or collaboration?

- How easy have you found it to collaborate within DANCOP?

- When you work with schools how much of your activity comes about from being associated with DANCOP?

- Do you think the network has enabled any economies of scale, efficiencies in operations and service, and reduction of duplication?

- What do you think the value and benefits of DANCOP are for yourselves and for the schools and learners you work with?

- What do you think are the main reasons for learners not progressing into FE or HE?

- What activities have you delivered?

  - With how many learners?

  - Where?

  - What year(s) were the learners?

  - What were the specific aims?

- Did you go into remote schools? Did you access any schools you haven’t worked with before?

- Which activities do you think impact positively on learners?

- How do you know?

- What features of the activities do you think account for their success? Why?

- How could these be further developed and disseminated to other areas?

## HEFCE – NCOP Impact Evaluation: participant baseline survey – Older Learners (Years 12-13) – DANCOP

Guidance for staff:

Thank you for helping us, we really appreciate it.

Learners should take approximately 5-10 minutes to complete this short survey.

It asks about their knowledge and awareness of higher education as well as their future intentions. The survey is being used to help establish whether taking part in outreach activities influences any of these things and we hope to compare the findings of those who do take part to those who do not.

Learners should be encouraged to complete the survey without discussing their answers but should feel free to ask for help if they don’t understand any of the questions or the options given to them.

Please note we ask for some personal information so we can match their responses now to those on a later survey at the end of the academic year. Once responses are matched the personal information will be deleted and no individual will be identifiable.

#### Information and Consent

Please read the following information about the research to make sure you understand what data we are collecting, who can access it, and what will be done with it.

The purpose of this research
Please read the following information about the research to make sure you understand what data we are collecting, who can access it, and what will be done with it.

Who we are
CFE Research (CFE) is carrying out the evaluation of NCOP on behalf of The Higher Education Funding Council for England (HEFCE). This survey is being conducted by CFE, Derbyshire and Nottinghamshire Collaborative Outreach Programme (DANCOP) and the University of Derby.

About this survey
The survey will take 5 to 10 minutes to complete. We ask how much you know about higher education and what you would like to do in future. The results will help to support learners who are interested in applying.

What will happen with the information collected?
Data will be collected in this survey by CFE Research and DANCOP. The information you provide will only be used for the purpose of this research project.

C1) Do you agree for us to collect your data in this survey for use in this research?

- Yes

- No

| P1) Please provide the following personal information: |  |
| --- | --- |
| First name |  |
| Surname |  |
| Home postcode |  |
| Personal Email address |  |
| School/College that you attend |  |

| P2) Date of birth | day | month | year |
| --- | --- | --- | --- |

| P3) Date | day | month | year |
| --- | --- | --- | --- |

With your permission, we will use your personal details to match your survey answers with other data held by the following organisations:

University of Derby

EMWPREP (East Midlands Widening Participation Research and Evaluation Partnership)

Behavioural Insights Team

This will allow us to track your progress over time without having to ask you further questions. We will hold your data only until this research project ends in 2020. Whenever the research findings are published, all information will be anonymised.

C2) Do you agree to let us share your data with these organisations?

- Yes

- No

Your rights if you take part

You have the right to refuse to answer any question. You have the right to withdraw your consent at any point. You do not have to give a reason for withdrawing. To withdraw consent, use the contact details provided below.

If you have any questions about this research or about how your data will be used, please contact either the person responsible for collecting this information in your area:

Anna Davey
anna.davey@teamDANCOP.co.uk 
01332 591412

or the CFE team:

ncop@cfe.org.uk
0116 229 3300

Thank you for taking the time to read this information. You can now proceed to the survey.

#### Part 1 – Please place a tick in the circle next to the option that best represents your situation, thoughts or feelings

Q1) Which year of study are you in?

- Sixth form - year 12 (lower sixth)

- Sixth form - year 13 (upper sixth)

- College - level 3 - year 1

- College - level 3 - year 2

Q2b) When you finish your current studies, what would you most like to do next?

- Get a full-time job

- Get a part-time job

- Study at or stay in further education college

- Study higher education at a further education college or other further education provider

- Study at a local university or another higher education institution

- Study away from home at university or another higher education institution

- Get a job and study at the same time

- Begin an apprenticeship

- Begin a higher/degree apprenticeship

- Some other type of training

- Other (please specify)____________

- Don't know

Q3) Who has had the greatest influence on your decision about what to do next?

- Family

- Friend(s)

- Teacher(s)

- Careers adviser(s)

- Other (please specify)____________

Q4) How much do you agree with the following statements about your aspirations for the future?

|  | Strongly disagree | Disagree | Neither agree nor disagree | Agree | Strongly agree | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
| I am motivated to do well in my studies |  |  |  |  |  |  |
| I could get the grades I need for further study |  |  |  |  |  |  |
| I could gain a place on a good course if I wanted to |  |  |  |  |  |  |

The next few questions ask about higher education. 'Higher education' includes:

• university

• higher education qualifications in a further education college

• higher/degree apprenticeships

Q5) How much do you know about the following aspects of applying to higher education?

|  | Nothing | A little | A lot |
| --- | --- | --- | --- |
| The courses that are available |  |  |  |
| Different routes, such as: higher/degree apprenticeships, distance learning, and higher education in a further education setting |  |  |  |
| How to apply through UCAS |  |  |  |
| Where to find information about applying |  |  |  |
| The qualifications and grades needed to get into the course you want |  |  |  |

Q6) How much do you know about the following aspects of higher education study?

|  | Nothing | A little | A lot |
| --- | --- | --- | --- |
| What learner life would be like |  |  |  |
| How it leads to careers that you may be interested in |  |  |  |
| The costs of study |  |  |  |
| The financial support available |  |  |  |
| The options about where to live whilst studying |  |  |  |
| The support available |  |  |  |

If you are in Sixth form year 13 (upper sixth) or College level 3 (year 2), go to question 7, if not, skip to question 8.

Q7) Have you applied to study at higher education?

| Yes |  | Please go to question 11 |
| --- | --- | --- |
| No |  | Please go to question 8 |

Q8) How likely are you to apply to higher education at age 18 or 19?

| Definitely won't apply |  | Please go to question 9 |
| --- | --- | --- |
| Very unlikely |  | Please go to question 9 |
| Fairly unlikely |  | Please go to question 9 |
| Fairly likely |  | Please go to question 11 |
| Very likely |  | Please go to question 11 |
| Definitely will apply |  | Please go to question 11 |
| Don't know |  | Please go to question 9 |

Q9) What is the main reason you might NOT go on to study further?

- My current qualifications are enough

- I have decided on a specific career (that does not require further study)

- I want to work and earn money

- The cost is too much

- It depends on the grades I get

- I do not have the necessary study skills

- It does not appeal to me

- I want to travel

- I am still undecided

- There is nowhere close enough to home

- Other reason (please specify)____________

Q10) How likely are you to apply to higher education in the future?

| Definitely won't apply | Very unlikely | Fairly unlikely | Fairly likely | Very likely | Definitely will apply | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |

Q11) How much do you agree with the following statements about higher education?

|  | Strongly disagree | Disagree | Neither agree nor disagree | Agree | Strongly agree | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
| It is for people like me |  |  |  |  |  |  |
| I would fit in well with others |  |  |  |  |  |  |
| I have the academic ability to succeed |  |  |  |  |  |  |
| I could cope with the level of study required |  |  |  |  |  |  |

Q12) How much do you agree with the following statements about higher education?

|  | Strongly disagree | Disagree | Neither agree nor disagree | Agree | Strongly agree | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
| It will broaden my horizons |  |  |  |  |  |  |
| It will challenge me intellectually |  |  |  |  |  |  |
| It will give me valuable life skills |  |  |  |  |  |  |
| It will improve my social life |  |  |  |  |  |  |
| It will enable me to earn more |  |  |  |  |  |  |
| It will enable me to get a better job |  |  |  |  |  |  |

#### Personal information

Q13) If you go on to higher education, would you be the first person in your immediate family to go?

- Yes

- No - my grandparent(s) went first

- No - my parent(s) or guardian(s) went first

- No - my brother(s) or sister(s) went first

- Don't know

Q14) Do you know somebody else who has gone on to higher education?

Please select all that apply

- No

- Yes - another family member

- Yes - a friend

- Don't know

- Other (please specify)____________ [Other]

Q17) Do you have a disability, learning difficulty or long-term physical or mental health condition?

- Yes

- No

- Prefer not to say

Q18) What is your gender?

- Female

- Male

- Other

- Prefer not to say

Q19) Which of the following ethnic groups do you belong to?

- White - British

- White - Irish

- White - Scottish

- Other White background

- Black or Black British - Caribbean

- Black or Black British - African

- Other Black background

- Mixed White and Black Caribbean

- Mixed White and Black African

- Asian or Asian British - Indian

- Asian or Asian British - Pakistani

- Asian or Asian British – Bangladeshi

- Other Asian background

- Mixed White and Asian

- Chinese

- Arab

- Irish Traveller

- Gypsy or Traveller

- Other ethnic background

- Any other mixed background

- Prefer not to say

Q20) Do you agree to be contacted about this project in the future?

| Yes |  | Please go to question 21 |
| --- | --- | --- |
| No |  | Please skip question 21 |

Q21) Thank you. Please provide a mobile telephone number for us to contact you:

[Q43 for ECON only]

Q43) I would like to receive invitations to future events by email.

| Yes |  |
| --- | --- |
| No |  |

Many thanks for completing this survey.

## HEFCE – NCOP Impact Evaluation: participant baseline survey – Younger Learners (years 9 and 10) – DANCOP

#### Information and Consent

#### Please read the following information about the research to make sure you understand what data we are collecting, who can access it, and what will be done with it.

The purpose of this research
Please read the following information about the research to make sure you understand what data we are collecting, who can access it, and what will be done with it.

Who we are
CFE Research (CFE) is carrying out the evaluation of NCOP on behalf of The Higher Education Funding Council for England (HEFCE). This survey is being conducted by CFE, Derbyshire and Nottinghamshire Collaborative Outreach Programme (DANCOP) and the University of Derby.

About this survey
The survey will take 5 to 10 minutes to complete. We ask how much you know about higher education and what you would like to do in future. The results will help to support learners who are interested in applying.

What will happen with the information collected?
Data will be collected in this survey by CFE Research and DANCOP using. The information you provide will only be used for the purpose of this research project.

C1) Do you agree for us to collect your data in this survey for use in this research?

- Yes

- No

| P1) Please provide the following personal information: |  |
| --- | --- |
| First name |  |
| Surname |  |
| Home postcode |  |
| Personal Email address |  |
| School/College that you attend |  |

| P2) Date of birth |  |
| --- | --- |

| P3) Date |  |
| --- | --- |

With your permission, we will use your personal details to match your survey answers with other data held by the following organisations:

University of Derby

EMWPREP (East Midlands Widening Participation Research and Evaluation Partnership)

Behavioural Insights Team

This will allow us to track your progress over time without having to ask you further questions. We will hold your data only until this research project ends in 2020. Whenever the research findings are published, all information will be anonymised.

C2) Do you agree to let us share your data with these organisations?

- Yes

- No

Your rights if you take part

You have the right to refuse to answer any question. You have the right to withdraw your consent at any point. You do not have to give a reason for withdrawing. To withdraw consent, use the contact details provided below.

If you have any questions about this research or about how your data will be used, please contact either the person responsible for collecting this information in your area:

Anna Davey
anna.davey@teamDANCOP.co.uk 
01332 591412

or the CFE team:

ncop@cfe.org.uk
0116 229 3300

Thank you for taking the time to read this information. You can now proceed to the survey.

#### Part 1 – Please place a tick in the circle next to the option which best represents your situation, thoughts or feelings

Q1) Which year of study are you in?

- School - year 9

- School - year 10

- School - year 11

- College - level 2

Q2a) When you finish your current studies, what would you most like to do next?

- Study at school or a sixth-form college

- Study at a further education college

- Get a full-time job

- Get a part-time job

- Begin an apprenticeship

- Some other type of training

- Other (please specify)____________

- Don't know

Q3) Who has had the greatest influence on your decision about what to do next?

- Family

- Friend(s)

- Teacher(s)

- Careers adviser(s)

- Other (please specify)____________

Q4) How much do you agree with the following statements about your aspirations for the future?

|  | Strongly disagree | Disagree | Neither agree nor disagree | Agree | Strongly agree | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
| I am motivated to do well in my studies |  |  |  |  |  |  |
| I could get the grades I need for further study |  |  |  |  |  |  |
| I could gain a place on a good course if I wanted to |  |  |  |  |  |  |

The next few questions ask about higher education. 'Higher education' includes:

• university

• higher education qualifications in a further education college

• higher/degree apprenticeships

Q5) How much do you know about the following aspects of applying to higher education?

|  | Nothing | A little | A lot |
| --- | --- | --- | --- |
| The courses that are available |  |  |  |
| Different routes, such as: higher/degree apprenticeships, distance learning, and higher education in a further education setting |  |  |  |
| How to apply through UCAS |  |  |  |
| Where to find information about applying |  |  |  |
| The qualifications and grades needed to get into the course you want |  |  |  |

Q6) How much do you know about the following aspects of higher education study?

|  | Nothing | A little | A lot |
| --- | --- | --- | --- |
| What learner life would be like |  |  |  |
| How it leads to careers that you may be interested in |  |  |  |
| The costs of study |  |  |  |
| The financial support available |  |  |  |
| The options about where to live whilst studying |  |  |  |
| The support available |  |  |  |

Q8) How likely are you to apply to higher education at age 18 or 19?

| Definitely won't apply |  | Please go to question 9 |
| --- | --- | --- |
| Very unlikely |  | Please go to question 9 |
| Fairly unlikely |  | Please go to question 9 |
| Fairly likely |  | Please go to question 11 |
| Very likely |  | Please go to question 11 |
| Definitely will apply |  | Please go to question 11 |
| Don't know |  | Please go to question 9 |

Q9) What is the main reason you might NOT go on to study further?

- My current qualifications are enough

- I have decided on a specific career (that does not require further study)

- I want to work and earn money

- The cost is too much

- It depends on the grades I get

- I do not have the necessary study skills

- It does not appeal to me

- I want to travel

- I am still undecided

- There is nowhere close enough to home

- Other reason (please specify)____________

Q10) How likely are you to apply to higher education in the future?

| Definitely won't apply | Very unlikely | Fairly unlikely | Fairly likely | Very likely | Definitely will apply | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |

Q11) How much do you agree with the following statements about higher education?

|  | Strongly disagree | Disagree | Neither agree nor disagree | Agree | Strongly agree | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
| It is for people like me |  |  |  |  |  |  |
| I would fit in well with others |  |  |  |  |  |  |
| I have the academic ability to succeed |  |  |  |  |  |  |
| I could cope with the level of study required |  |  |  |  |  |  |

Q12) How much do you agree with the following statements about higher education?

|  | Strongly disagree | Disagree | Neither agree nor disagree | Agree | Strongly agree | Don't know |
| --- | --- | --- | --- | --- | --- | --- |
| It will broaden my horizons |  |  |  |  |  |  |
| It will challenge me intellectually |  |  |  |  |  |  |
| It will give me valuable life skills |  |  |  |  |  |  |
| It will improve my social life |  |  |  |  |  |  |
| It will enable me to earn more |  |  |  |  |  |  |
| It will enable me to get a better job |  |  |  |  |  |  |

#### Personal information

Q13) If you go on to higher education, would you be the first person in your immediate family to go?

- Yes

- No - my grandparent(s) went first

- No - my parent(s) or guardian(s) went first

- No - my brother(s) or sister(s) went first

- Don't know

Q14) Do you know somebody else who has gone on to higher education?

Please select all that apply

- No

- Yes - another family member

- Yes - a friend

- Don't know

- Other (please specify)____________

Q17) Do you have a disability, learning difficulty or long-term physical or mental health condition?

- Yes

- No

- Prefer not to say

Q18) What is your gender?

- Female

- Male

- Other

- Prefer not to say

Q19) Which of the following ethnic groups do you belong to?

- White - British

- White - Irish

- White - Scottish

- Other White background

- Black or Black British - Caribbean

- Black or Black British - African

- Other Black background

- Mixed White and Black Caribbean

- Mixed White and Black African

- Asian or Asian British - Indian

- Asian or Asian British - Pakistani

- Asian or Asian British – Bangladeshi

- Other Asian background

- Mixed White and Asian

- Chinese

- Arab

- Irish Traveller

- Gypsy or Traveller

- Other ethnic background

- Any other mixed background

- Prefer not to say

Q20) Do you agree to be contacted about this project in the future?

| Yes |  | Please go to question 21 |
| --- | --- | --- |
| No |  | Please skip question 21 |

Q21) Thank you. Please provide a mobile telephone number for us to contact you:

Many thanks for completing this survey.

DANCOP Activity Evaluation Form

DANCOP (Derbyshire & Nottinghamshire Collaborative Outreach Programme) use, hold and process the information you supply on this evaluation form in line with the Data Protection Act 1998 and GDPR.

We use this information to create registers, monitor participation, and evaluate the effectiveness of DANCOP activities.

We are legally obligated to share monitoring information with the Office for Learners (OfS). We are also obligated to share monitoring information with the East Midlands Widening Participation Research and Evaluation Partnership (EMWPREP) where you have previously engaged with them. OfS and EMWPREP only use your information for statistical analysis.

We share your feedback with the International Centre for Guidance Studies who are evaluating the effectiveness of DANCOP activities.

We will retain your information for the duration of DANCOP to enable ongoing reporting; after that time it is deleted securely.

I give my full permission for my details to be used in this manner:      Yes                  No

You can withdraw your permission or amend your data at any time by contacting gdpr@teamDANCOP.co.uk

Our Data Protection Officer (DPO) is James Eaglesfield on (01332) 591762. Our Deputy DPO is Helen Rishworth on (01332) 591954. Alternatively you can email gdpr@derby.ac.uk

| Name: |  |
| --- | --- |
| Date of Birth: | Home Postcode: |
| School: | Name of Event: pre-populated by facilitator of activity |

How would you rate the event today?

| Excellent | Good | Fair | Poor |
| --- | --- | --- | --- |

Thinking about what you already knew and what you have learnt from today, please indicate your level of agreement for the following statements:

1 = strongly disagree			3 = neither agree nor disagree			5 = strongly agree

| Before the event |  | After the event |
| --- | --- | --- |
| 1 2 3 4 5 | I know what higher education is (including university, higher education in a further education college and higher and degree apprenticeships) | 1 2 3 4 5 |
| 1 2 3 4 5 | I am thinking about applying to higher education in the future | 1 2 3 4 5 |
| 1 2 3 4 5 | I know enough about my future options to help me make a decision about what to do after school/college | 1 2 3 4 5 |
| 1 2 3 4 5 | Pick relevant question from question bank for your activity or delete this row. | 1 2 3 4 5 |

If you could describe the event today in three words, what would they be?

Please tell us something that you have learnt through taking part in this event

Following this session, have all of your questions been answered?

| Yes | No |
| --- | --- |

If no, please tell us your question(s) below